## Slide 1: Hasanuddin University Engineering Faculty Department Project
Equipment Discussion Note
July 2006
SAPROF Team

## Slide 2: Equipment discussion procedure
1. Preparation and confirmation of Equipment list (Draft)
Target schedule: By July 17 2006
2. Discussion based on “Equipment reference sheet” with Department, format is prepared by SAPROF team
Target schedule: By August 12 2006
3. Cost estimation (SAPROF team in charge)
Target schedule: By Middle of September 2006

## Slide 3: Necessary information on Equipment Discussion
Please provide information as below;
Equipment list（New, Major Existing Equipment to be moved)
Laboratory list (new campus)
Curriculum (It is necessary to finish discussion about curriculum with SAPROF team in advance.)
Research topics (It is necessary to finish discussion about research topics with SAPROF team in advance.)
Room assignment plan
Operation and maintenance plan

## Slide 4: Basic Policy on Equipment Selection-1
1. Planned Equipment shall be based on Research and education curriculum.
All equipment will be evaluated and examined linkage with research and education curriculum.
Result of linkage between equipment and curriculum will be summarized into “Equipment reference sheet”. (SAPROF team support to prepare this sheet.)
Necessity from
research and
education
Specified items and Quantity
→Equipment list

## Slide 5: Basic Policy on Equipment Selection-2
2. Planned Equipment shall be secured necessary installation space.
Installed laboratory and/or room shall be specified. It will be link with facility planning.
Result of linkage between equipment and laboratory and/or room will be summarized into “Equipment reference sheet”. (SAPROF team support to prepare this matrix.)
Space for
Equipment
Equipment and room assignment plan
Equipment layout plan

## Slide 6: Equipment Selection Criteria
Inclusion Criteria
Necessary for research and education curriculum implementation
Necessary for administrative activities
Necessary for University capacity enhancement
Exclusion Criteria
Not necessary for University’s activities
Usage/purpose not clearly defined
Small items, such as glass wares
Only consumables and spare parts

## Slide 7: Equipment Planning Strategy
Division on Category of equipment into 2
1. Major Equipment | -Obviously necessary to implement research and education (with curriculum evidence) -Large equipment, which is necessary to secure installation space. -Expensive equipment and high priority for research and education.
2. Minor Equipment | -Necessary in the future -Detailed specifications are not specified -Not specified

## Slide 8: Equipment list preparation
Major Equipment
Minor Equipment
Including “Equipment Reference sheet”
as a “item”,
Equipment name
Quantity
Installed room etc
Including “Equipment Reference sheet”
as a “general description”,
just making a pile of equipment such as;
“Equipment for Civil engineering A laboratory”
“Equipment for Energy engineering”
To be specified in the future

## Slide 9: Equipment reference sheet

## Slide 10: Procurement Policy
Package for Bidding (by ICB, LCB)
- ICB: International Competitive Bidding
- LCB: Local Competitive Bidding
Procurement schedule by Package (By year)