# Chapter II  STRENGTHENING THE EXISTING STUDY PROGRAM

# ELECTRICAL ENGINEERING STUDY PROGRAM

Chapter 2.1  ELECTRICAL ENGINEERING STUDY PROGRAM

- BACKGROUND

After it moved to the new campus with all new facilities in 1985, the Electrical Engineering Study Program of Hasanuddin University, Makassar (occasionally in this Chapter is referred to as "the Study Program") stated its vision and mission as follows:

The Study Program’s VISION is to be the Center of Development and Implementation of the Electrical Engineering Technology and to become a leading engineering education institution in the country. Its MISSION is to graduate professionals who are able to advance their own technical skills and knowledge, and to adopt the development of technology.

The mission was carried out very well especially when a 10-year-long project called the Engineering Acceleration Project (Proyek Percepatan Insinyur, PPI) was launched in 1986. However; since the project ended in 1996, the Study Program has been constantly suffering from the quality degradation. The vision has become so blurring and the mission is so impossible; so only its long history, the high quality it used to have and the perseverance of all staffs that have helped maintaining the Study Program's performance up to a certain level. Without a careful rescue plan, the Self-Evaluation Report has shown that the performance will not last long in the future.

As has been concluded from the SWOT and Force-Field Analysis in Revised-Self Evaluation Report (SER) Chapter III.B.1. (see page III.B.1-1 to III.B.1-4 of the Revised Sub-Project Proposal), there are 3 (three) major obstacles - among others - that are supposed to be controllable factors of  improving the quality of the Study Program, i.e.:

- The obsolescence of the laboratory equipment and laboratory course materials for advance laboratory courses,

- Inadequate quantity of the laboratory equipment and laboratory course materials for basic laboratory courses, and

- The problem of teaching staff composition and qualification.

Those 3 (three) main issues above are the core of problems the Study Program is facing, and have been translated into strategic issues to develop several proposed activities (see Strategic Issues in Chapter III.B.2 Revised Inception Plan on page III.B.2-1 of the Revised Sub-Project Proposal) that will be detailed in the following Chapter 2.2. IMPROVING RAISE++ .

- THE STRATEGY AND THE OBJECTIVES

All the staff's high motivation to work together is the primary asset the Study Program has. This has been shown by the staff's response to the announcement of this project (see Appendix III.2 on page III-Ap-3 of the Revised Sub-Project Proposal). At all socialization events mentioned, 90% of the staff were in attendance. Even in the very early stage of the Self-Evaluation Report preparation for the TPSDP Batch 1, the process has reflected the firm commitment to come together. This should be carried on to the next stage, i.e. the preparation of this Sub-Project Proposal of the TPSDP Batch 2 and - if the project is granted - to the implementation of the project. The main strategy is to harvest the participation of all components to produce a list of activities - not a "list of wants" or a "procurement list" - as early as possible. For instance, on the issues regarding the laboratories, each laboratory was asked to start by preparing the list of experiments for laboratory courses, then based on each experiment, a list of equipment required was developed (see Appendix II.H.I to IV on page II-Ap-11 to 20 of the Revised Sub-Project Proposal for details). No equipment procurement is supposed to be proposed by any laboratory without a proposed experiment for a laboratory course.

Implementation Plan

R

A

I

S

E

+

+

Performance Targets

Proposed Budget

PROJECT BENEFIT

and ECONOMIC ANALYSIS

SE-REPORT

SWOT

Force-Field

Analysis

R.1.

R.2.

R.3.

R.4.

R.5.

A.1.

A.2.

E.1.

E.2.

AE

IMO

PROPOSED ACTIVITIES

STRATEGIC

ISSUES

Figure II-1 Line of Thought of the Preparation of the Sub-Project Proposal

Figure II-1 shows the line of thought in preparing this Sub-Project Proposal. After a long series of discussions on the results of the self-evaluation process, including the discussions with the TPSDP reviewers during the site-visit and negotiations, the Study Program came up with 11 (eleven) proposed activities:

- To improve relevance: 5 (five) activities

- To improve academic atmosphere: 2 (two) activities

- To improve efficiency and productivity: 2 (two) activities

- To improve access and equity: 1 (one) activity

- To improve internal management and organization: 1 (one) activity

[Note: In the previous documents of this Sub-Project, one may notice that there used to be 4 (four) activities to improve relevance and 3 (three) activities to improve efficiency and productivity. After a long and intensive discussion, it was decided to change the main aspect of the activity of improving the staff qualification (activity E.3.) from improving the efficiency and productivity to improving the relevance].

C. PERFORMANCE INDICATORS

The general outcome of those eleven proposed activities will be quality improvements that are indicated by performance targets as shown in Table II-1. The increase of average NEM, for instance, is believed to be influenced mainly by improving access and equity as well as the quality enhancement as the consequences of the implementation of other activities. Hence, this indicator is omitted.

### Table II-1 Main Indicators for performance targets presented in their frequency ranges

| Indicator | Baseline |  | As 31 Oct 2004 | Midterm | Final |
| --- | --- | --- | --- | --- | --- |
|  | (%) |  |  |  |  |
| GPA |  |  |  |  |  |
| Percentage of graduates with GPA > 3.0 | 40.79 |  | 73.89 | 46.50 | 50.00 |
| Percentage of graduates with GPA between 2.5 and 3.0 | 56.35 |  | 22.93 | 52.50 | 49.50 |
| Percentage of graduates with GPA < 2.5 | 2.86 |  | 3.18 | 1.00 | 0.50 |
| TOEFL SCORE |  |  |  |  |  |
| Percentage of students with TOEFL score > 500 | 5.53 |  | 6.49 | 16.60 | 37.80 |
| Percentage of students with TOEFL score between 400 and 500 | 38.13 |  | 77.92 | 54.80 | 57.20 |
| Percentage of students with TOEFL score < 400 | 56.34 |  | 15.58 | 28.60 | 5.00 |
| LENGTH OF STUDY |  |  |  |  |  |
| Percentage of graduates with length of study > 5 years | 77.64 |  | 33.76 | 50.80 | 19.00 |
| Percentage of graduates with length of study between 4.5 and 5 years | 19.14 |  | 43.31 | 30.00 | 35.50 |
| Percentage of graduates with length of study < 4.5 years | 3.22 |  | 22.93 | 19.20 | 45.50 |
| WAITING TIME FOR THE FIRST JOB |  |  |  |  |  |
| Percentage of graduates who waited for their first jobs within 6 months | 13.60 |  | N/A | 25.00 | 50.00 |
| Percentage of graduates who waited for their first jobs within 6 to 11 months | 51.20 |  | N/A | 45.00 | 40.00 |
| Percentage of graduates who waited for their first jobs for more than 11 months | 35.20 |  | N/A | 30.00 | 10.00 |
| FIRST JOB MONTHLY SALARY |  |  |  |  |  |
| Percentage of graduates whose first job monthly salary > Rp. 1.2 millions |  | 7.20 | N/A | 45.00 | 70.00 |
| Percentage of graduates whose first job monthly salary between Rp. 0.6 and 1.2 millions |  | 50.40 | N/A | 35.00 | 20.00 |
| Percentage of graduates whose first job monthly salary < Rp. 0.6 millions |  | 42.40 | N/A | 20.00 | 10.00 |

Activities to improve efficiency and productivity will be directly and indirectly indicated by the increase of the graduates’ average GPA. These activities are also supposed to shorten the length of study as indicated by the average length of study. The average TOEFL scores, the graduates’ waiting time before getting the first job and the first job salary will indicate the improvement in relevance.

All proposed activities in this project are generally planned to boost most of the performance target indicators to yield a better result. Previously the performance targets were presented by the average values of the main indicators as suggested by the Guidelines. But, the incremental increase of the performance indicators have seemed “too modest” in comparison to the amount of capital invested in this project, and the average values may not really represent the actual condition. With a large student population, the presentation of the main indicators of the performance target in their frequency ranges or distribution – as presented in Table II-1 on page II-3 - will give a better perspective.

The average of NEM score's baseline data is 47.1 with standard of deviation 6.0. Improving the relevance (R) of the educational process to the job-market and industrial needs can increase the NEM scores of the admitted students. Naturally, when the relevance (R) is improving, the number of applicants to the Study Program will increase, resulting tougher competition at the new student admittance. A larger number of new students with high NEM scores will be admitted, and this will affect the academic atmosphere (A) at the Study Program. Another way of achieving this target is by creating some campaign programs about the Study Program to the High Schools at the surrounding area.

The average of graduates' GPA taken from the last 4 (four) academic years is 2.94, distributed as shown in Table II-1. It is targeted to improve the distribution. This performance target indicates the improvement of the academic atmosphere (A) (e.g. by upgrading teaching facilities and classroom-facilities, developing lecturers' teaching skills and students' learning skills and creating competitiveness among students).

Encouraging students to read more reference books in English and urging lecturers to use English in their classes - among others - will help to improve students' English proficiency indicated by their TOEFL scores. This is a part of activities that will improve the relevance (R) of the Study Program. At the beginning of the project, the average of TOEFL scores of students whose credit earnings are 120 sks or more is 403, this is fairly high, considering that the students did not make any preparation due to the very short notice before the test. The distribution of the TOEFL scores is targeted to be improved by the implementation of a special program proposed as one of the student co-curricular activities (see Activity R.4.1 on page II-11).

The average graduates' length of study is 5.67 years at the beginning of the project. This can be shortened at the end of project, and the distribution is expected to be better, by improving the efficiency and productivity (E) of the educational process.  This target can be achieved by improving the teaching and learning process (see Activity E.1. on page II-16) and to create more effective laboratory scheduling. In fact, the length of study has 2 (two) components, i.e. the classroom-courses study time and the final undergraduate project (skripsi) time. In order reduce the latter, the intensive interaction between supervisors and students should be enforced and the adequate laboratory equipment should be available. The baseline data of standard deviation can be reduced by continuous academic advisors' supervising on their students' study program planning and monitoring in order to detect the weak students. Special attention must be given to this kind of students to push them to study harder. Another factor that could influence the length of study time was the student academic leaves, which in most cases were caused by the lack of funding. Students' involvement in research and teaching grant activities are expected to be one of the possible remedies to reduce student academic leaves. An aggressive program to collect student scholarships (e.g. from alumni, industry, local and regional government) should be planned to help this problem out.

Survey and direct interviews have shown that the waiting time to get the first job is 11 months in average, which is a rather long time. This indicator is influenced heavily by the unemployment rate in the market, which is closely related to the country economic situation. Assuming a better economic growth, then additional efforts to improve the students' English proficiency and computer skills, as well as continuous adjustments of the curriculum toward industrial world orientation, will give the graduates a strong penetration to the job market.  This will automatically reduce the waiting time to the first job. It is expected that the waiting time to get the first job will be reduced and the distribution will look better also at the end of the project.

Table II-2.  Additional indicators for performance targets

| Indicator | Baseline | As 31 Oct 2004 | Midterm | Final |
| --- | --- | --- | --- | --- |
| Ratio between applicants and admissions | 9.3% | 6.8% | 9% | 8% |
| Average duration of completing skripsi | 9 months | 6 months | 8 months | 6 months |
| Average active students with GPA less than 2.5 | 4.8% | 0% | 4.6% | 4.3% |
| Average drop out students | 1.66% | 0.16 % | 1.60% | 1.50% |
| Productivity (Graduates/Population) | 11.08% | 29% | 15.5% | 17% |
| Average teachers attendance at classroom | 85% | 93% | 87% | 90% |

The factors that have affected the graduates' first job salary, such as the national and local economic growth, were beyond the Study Program's scope of control, but improving the relevance (R) of the Study Program in many ways will give the competitive advantages to the graduates so that they could ask for a higher salary on their first jobs.

The Study Program was accredited C in 1998, and only recently it was up-graded to B. It is strongly believed that if all activities are implemented in the TPSDP according to the proposed plans, the Study Program will be accredited A.

Additional indicators as presented in Table II-2 are thought to be the direct impact of all proposed activities as described in details in the following Chapter 2.2. IMPROVING RAISE++. In addition to that, each proposed activity has its own performance indicators also.

Chapter 2.2. IMPROVING RAISE++

1. Relevance

| Code | Name of Activity |  |
| --- | --- | --- |
| R.1. | Improving, updating and renewing the quality of the modules, materials and delivery of the advance laboratory courses: Laboratory III and Laboratory IV (including the improvement of the qualifications of the Laboratory Assistants). |  |
| R.2. | Enhancing the industrial relation in the surrounding area: |  |
|  | R.2.1. | Developing Apprenticeship Programs in Industry |
|  | R.2.2. | Developing Curriculum and Syllabus with a close cooperation with Industry |
|  | R.2.3. | Developing Industrial Training and Studies Programs |
| R.3. | Developing NEW Classroom/Laboratory Teaching Materials: |  |
|  | R.3.1. | Cellular Telecommunication |
|  | R.3.2. | CISCO Certified Network Associate Training Center Development |
| R.4. | Enhancing Students’ Co-Curricular Activities and Additional Skills and Competencies: |  |
|  | R.4.1. | English Competency: Technical and Engineering Writing Skills |
|  | R.4.2. | Computer and Internet Skills |
|  | R.4.3. | Student Electrical Workshop |
|  | R.4.4. | Students’ Personality Enhancement and Entrepreneurship Training Programs |
| R.5. | Improving the Teaching Staff’s academic qualifications and the Administrative Staff’s competency and skills: |  |
|  | R.5.1. | Domestic and Overseas Degree Programs S2, S3 |
|  | R.5.2. | Local Vocational Trainings for Administrative Staffs and Laboratory Technicians |
|  | R.5.3. | International Conferences and Domestic Special Non-Degree Programs |

1.1. Name of Activity: R.1. Improving, updating and renewing the quality of the modules, materials and delivery of the advance laboratory courses: Laboratory III and Laboratory IV (including the improvement of the Laboratory Assistants qualifications).

Background: The structure of curriculum requires advance laboratory courses Laboratory III and Laboratory IV to be taken at the fifth and the sixth semester by the students of different Sub-Study Programs in different 11 (eleven) laboratories. These two laboratory courses are designed to support the core and advance courses provided by each Sub-Study Program (see Chapter III.1.B. Section 11 Curriculum on page III.B.1-16 of the Revised Sub-Project Proposal). There has been no serious updating of both laboratory teaching materials and laboratory equipment since 15 years ago when the Study Program moved from the old campus. The obsolescence of both the teaching materials and the equipment is apparent, which makes the laboratory courses irrelevant to the rapid progress of electrical engineering technology as well as the demand of the job-market. Lack of sufficient funding to maintain and update old equipment has made most laboratory equipment and instruments are not functioning appropriately as they are supposed to be. After two years of the project implementation, The civil works of the first year term has been successfully implemented so

To be continued in the next page ……

| Activity R.1. (continued) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Background (cont’d): that most laboratories have their new room lay-out to accommodate the laboratory courses. The bidding process for the second year term is in progress. The laboratory furniture ordered for the first year term of the project has also been delivered, and the bidding process for the second year term is also in progress. The department has produced the draft of a new curriculum planned to be implemented beginning in 2005, to split the study prgram into 4 (four) study programs. The draft has been submitted to the university senate to get an approval. In the new curriculum there is a major change in the format of laboratory courses. Separate courses Laboratory I, II, III and IV will be integrated into classroom courses. About 25 to 50% laboratory experiment modules – especially those which are relevant - have been repaired and refurbished to accommodate a special D3 program called “Partnership D3 Program for PT. TELKOM employees”. These modules are also used by the S1 students while waiting for the delivery of new equipment from TPSDP procurement. To sum up, performance indicators of this activity does not show any significant improvement because most sub-activities are difficult to be implemented without new equipment that the study program has proposed to be procured in this project. The bidding process for the procurement of laboratory equipment is not completed yet. However, since some laboratories have been renewed their experiment module, hence, there is a slight improvement in the indicator of repaired, updated & renewed experiment modules and test instrument about 25%. (This improvement, of course, still below the midterm target (50%)). |  |  |  |  |  |
| Rationale: Upgrading, repairing and updating laboratory teaching materials in accordance with the rapid progress of electrical engineering technology will improve the competitiveness of the graduates These activities are necessary in order to develop the graduates’ technological and professional skills which are closely related to the job-market demand. |  |  |  |  |  |
| Objective : The improvement of the graduates’ competitiveness in the job-market. |  |  |  |  |  |
| Mechanism and design : R.1.1. Assessing the existing laboratories condition, mainly in terms of organizational and management aspects, environmental and utilities setting, and the quality of laboratory course materials. R.1.2. Preparing the standard workplace and required utilities in the laboratories. R.1.3. Repairing and renewing the existing experiment modules, instruments and parts. R.1.4. Commissioning test of the new laboratory equipment. R.1.5. Developing experiment guides and related laboratory assistant training materials. R.1.6. Implementing and evaluating the updated experiment modules for Laboratory III and IV courses |  |  |  |  |  |
| Resources required (Year 3 only): |  |  |  |  |  |
| Sub-activity | Cost Components | Rp | US $ | Source of Funding |  |
| R.1.1. | Program Development | 0,00 |  | TPSDP | DRK |
| R.1.2. | Furniture | 21.650.800,00 |  | TPSDP |  |
|  | Civil Works | 62.235.872,40 |  | TPSDP | DRK |
| R.1.3. | Equipment | 14.025.000,00 | 63.051,10 | TPSDP |  |
| R.1.4. |  |  |  |  |  |
| R.1.5. | Program Development | 0,00 |  | TPSDP |  |
|  | Total | 97.911.672,40 | 63.051,10 |  |  |
| To be continued in the next page …… |  |  |  |  |  |

| Activity R.1. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activity | Yr 1 |  |  |  | Yr 2 |  |  |  | Yr 3 |  |  |  |  |  | Yr 4 |  |  |  |  |  |
| R.1.1. |  |  |  | Re-scheduled, waiting for the delivery of the laboratory equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.6. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  |  | Baseline |  |  | Mid |  |  | Status |  |  | Final |  |
| Repaired, updated and renewed experiment modules and test instruments |  |  |  |  |  |  |  |  |  | 0% |  |  | 50% |  |  | 25-50% |  |  | 100% |  |
| Percentage of graduates working in their related fields |  |  |  |  |  |  |  |  |  | N/A |  |  | 40% |  |  | N/A |  |  | 60% |  |
| Sustainability : The sustainability of this activity will be guaranteed by establishing: - Routine maintenance and repair works by laboratory assistants and technicians who acquire the skills from appropriate training programs. - Practical training programs for technical high school and/or D-3/Polytechnic students in laboratory routine maintenance and repair works. - Cooperation with private universities in surrounding area for laboratory assistant training programs - Collaboration with industry in joint-research programs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. Hj. Nien K. Nauman |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1.2. Name of Activity: R.2. Enhancing the industrial relation in the surrounding area.

Background: - The Study Program has a very limited collaboration with local companies and industries yielding no solid linkage with the surrounding environment - Job-market in most industries requires industrial experience in the recruitment of fresh graduates - There is an indication that a number of alumni were fired from work right after their probation - Many fresh graduates were not sufficiently confident to enter the job-market due to their very low experience in industrial world The Study Program has successfully maintained its linkages with the industry. As an example, a one-day Workshop on “The Industrial Approach of Teaching Process Control & Instrumentation” was held in Hasanuddin University campus on May 1, 2004 by the Study Program for introducing the products of Syntek Group, Malaysia. This workshop was attended by the industrial practitioners from the surrounding area and has led to the submission of a USD 1.4 million project proposal to the Ministry of Energy and Natural Resources. Linkages with the industrial world are also established and maintained through channels created by the alumni network.

Rationale : - The apprenticeship program designed in this activity will enhance the industrial relation of the Study Program that will be expanded into close collaboration with industry in curriculum development, training and studies. - This activity will provide the students and the fresh graduates some industrial certifications that will be useful for entering the job-market - This activity will improve the fresh graduates’ self confidence in entering the job-market - Closer relation with industry will give a better shape of the curriculum design and course syllabi in terms of the industrial relevance.

To be continued in the next page ……

| Activity R.2. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective : The establishment of a strong industrial apprenticeship program in order to strengthen the industrial relation of the Study Program and to enhance relevance in terms of industrial relation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mechanism and design : - R.2.1. Developing Apprenticeship Programs in Industry - R.2.2. Developing Curriculum and Syllabus with a close industrial cooperation - R.2.3. Developing Industrial Training and Studies Programs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources required (Year 3 only): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activity | Cost Components |  |  |  |  | Rp. |  |  |  |  |  |  |  |  | Funding Source |  |  |  |  |  |  |  |  |  |
| R.2.1. | Program Development |  |  |  |  | 9.230.769,24 |  |  |  |  |  |  |  |  | TPSDP |  |  |  |  | DRK |  |  |  |  |
| R.2.2. | Program Development |  |  |  |  | 13.153.846,50 |  |  |  |  |  |  |  |  | TPSDP |  |  |  |  | DRK |  |  |  |  |
| R.2.3. | Program Development |  |  |  |  | 3.333.333,33 |  |  |  |  |  |  |  |  | TPSDP |  |  |  |  | DRK |  |  |  |  |
|  | TOTAL |  |  |  |  | 25.717.949,07 |  |  |  |  |  |  |  |  | TPSDP |  |  |  |  | DRK |  |  |  |  |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activities |  | Yr 1 Re-scheduled |  |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  | Yr 4 |  |  |  |  |  |
| R.2.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.2.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.2.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  | Baseline |  |  |  | Mid |  |  |  |  | Status |  |  |  |  | Final |  |  |
| Percentage of alumni participating in the industrial apprenticeship program every graduation |  |  |  |  |  |  |  | 0% |  |  |  | 5% |  |  |  |  | N/A |  |  |  |  | 10% |  |  |
| Number of implemented Memorandum of Agreements (MOUs) on curriculum development with industries |  |  |  |  |  |  |  | N/A |  |  |  | 4 |  |  |  |  | 1 |  |  |  |  | 10 |  |  |
| Graduates’ waiting time before getting the first job |  |  |  |  |  |  |  | 11 months |  |  |  | 9 months |  |  |  |  | N/A |  |  |  |  | 5 months |  |  |
| First job salary (in Rupiahs) |  |  |  |  |  |  |  | Rp.712.400 |  |  |  | Rp.1.000.000 |  |  |  |  | N/A |  |  |  |  | Rp.1.500.000 |  |  |
| Sustainability : To continue with this apprenticeship program and the industrial relation after the final year of the project term, the following efforts could be done: - Each participant is asked to contribute for this program - Alumni Association could adopt this program If the industrial world can be convinced that this program is beneficial, the collaboration with the industrial world will continue. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. A. Toyib Rahardjo, M.Sc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1.3. Name of Activity: R.3. Developing NEW Classroom/Laboratory Teaching Materials

## Background: Due to the lack of adequate courses materials, laboratory equipment, access of information and advance technology skills; the alumni seem to lose the self-confidence, especially when they have to penetrate job market. This activity is planned to be implemented in the third year.

## Rationale: With this activity, it is expected that the alumni will have more ability and knowledge to compete with others to get their jobs.

## Objective: The activity proposed below will provide an opportunity for the lecturers and students to keep up with the current technological development. The alumni will have some opportunity to get world wide accepted certificates.

To be continued in the next page ……

| Activity R.3. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ## Mechanism and design: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## R.3.1. Improving the knowledge and skills of staff and student in the progress of cellular technology development: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ## R.3.1.1: Improving the staff and students’ practical skills and knowledge through a related industrial apprenticeship program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ## R.3.1.2: Preparing the required hardware and software, including instructional materials and experimental guides. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ## R.3.1.3: Providing a competitive Teaching Grant for developing related laboratory course materials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ## R.3.1.4: Implementing the laboratory course on cellular technology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## R.3.2. Acquiring the CISCO Certified Network Associates (CCNA): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ## R.3.2.1: Instructors in-country training for CCNA. Candidates will be sent to an in-country CCNA Centre to participate in a two-month training program to obtain the Certificate of Instructor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R.3.2.2: Preparing the required hardware, software and Internet link necessary to establish the center. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R 3.2.3: Developing the instructional materials for the training program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R.3.2.4: Conducting the Local Assistants Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R.3.2.5: Implementing the regular training programs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R.3.2.6: Conducting the standard tests for certification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resource Required (Year 3 only): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Sub-Activity | Cost Component |  |  |  |  |  | Rp. |  |  |  |  |  |  | US$ |  |  |  |  | Funding Source |  |  |  |  |  |
| R 3.1 |  | R 3.1.1 | Program Dev. |  |  |  |  |  | At cost |  |  |  |  |  |  |  |  |  |  |  | R.2.1 |  |  |  |  |  |
|  |  | R 3.1.2 | Equipment |  |  |  |  |  |  |  |  |  |  |  |  | 21,230.00 |  |  |  |  | TPSDP |  |  |  |  |  |
|  |  | R 3.1.3 | Teaching Grant |  |  |  |  |  | 20.000.000,00 |  |  |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  |  |  |
| ###### R.3.2. |  | R 3.2.1 | Staff Dev. |  |  |  |  |  | 27.500.000,00 |  |  |  |  |  |  |  |  |  |  |  | TPSDP + DRK |  |  |  |  |  |
|  |  | R 3.2.2 | Equipment |  |  |  |  |  |  |  |  |  |  |  |  | 0.00 |  |  |  |  | TPSDP |  |  |  |  |  |
| Total Cost |  |  |  |  |  |  |  |  | 47.500.000,00 |  |  |  |  |  |  | 21,230.00 |  |  |  |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Sub-Activity |  | Yr 1 |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |  | Yr 4 |  |  |  |  |
| R 3.1 |  | R 3.1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R 3.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R 3.1.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R.3.1.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.3.2. |  | R 3.2.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R 3.2.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R 3.2.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R 3.2.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R.3.2.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R 3.2.6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Indicators |  |  |  |  |  |  |  |  | Baseline |  |  |  | Mid |  |  |  | Status |  |  |  |  | Final |  |  |
| R 3.1. |  | Number of Apprenticeship participants a. Staff b. Student |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  | 2 |  |  |  | 1 |  |  |  |  | 5 persons |  |  |
|  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  | 8 |  |  |  | 4 |  |  |  |  | 16 persons |  |  |
|  |  | Number of graduates working in cellular technology |  |  |  |  |  |  |  |  | N/A |  |  |  | 1 |  |  |  | N/A |  |  |  |  | 5 persons |  |  |
| R 3.2. |  | Number of CCNA Instructors |  |  |  |  |  |  |  |  | 0 |  |  |  | 2 |  |  |  | 0 |  |  |  |  | 2 persons |  |  |
|  |  | Number of CCNA certified associates |  |  |  |  |  |  |  |  | 0 |  |  |  | 20 |  |  |  | 0 |  |  |  |  | 80 persons |  |  |
| To be continued in the next page …… |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Activity R.3. (continued)

Sustainability: In the future, these activities will become sources of revenue for the Study Program. Local private universities and industries, as well as students and alumni, are expected to participate in the local training, to use the laboratories and to obtain the International Certification through these programs.

Person in charge : Dr.Ir.H.Rhiza S. Sadjad, MSEE

1.4. Name of Activity: R.4. Enhancing Students’ Co-Curricular Activities and Additional Skills and Competencies

Background: A plan to enhance the student additional skills and competence should be proposed to improve the students' English competency, vocational, computer and internet skills. The establishment of student workshop facilities is also a part of this plan. From the polling (see the analysis at the end of Section 2 Environmental Setting, page III.B.1-8 and appendix III.10, page III-Ap-9 of the Revised Sub-Project Proposal) only about little bit more than 10 % of the students intended to work as entrepreneurs (8,71 %) or freelance workers (2,70 %) after they graduated. Regular programs/activities should be proposed to enhance the students' personality entrepreneurship as another part of the plan. Up to now, several activities for example freshtech workshop funded under TPSDP project have been successfully undertaken during the last two years and improved significantly the computer skills of the students. This program has been adopted by the study program and will be continuously implemented as annual student activities. Based on this fact, the study program would establish other training programs for year III intended for student’ co-curricular activities. In the first year term of the project, this activity was implemented successfully. The SIP of the second year term of the project required the submission of only 1 (one) TOR for the 3 (three) Program Developments R.4.1., R.4.2. and R.4.3., which is not completely approved yet until this report is written, However; most sub-activities have been implemented using other sources of fundings and support (not from the project) and also most performance indicators of this activity have shown an improvement. Students’ Average TOEFL Score has increased slightly from score of 403 (Baseline) to 426. The students have participated in the National Technical and Scientific Contests/Competition every year. For the second time, students have participated and passed the pre-qualification in the Indonesian Robotic Contest in the University of Indonesia, Depok 2004. This indicates a high motivation among students to conduct a research and development in the field of robotics. Furthermore, the percentage of Internet users among students has increased significantly after the establisment of additional Internet connection in the Faculty of Engineering in the mid-2004. All laboratories have Internet connectivity and students can access the Internet almost for free and search references related to their taken courseworks. While waiting for the delivery of the equipment, the Student Electrical and Electronic Workshop has been established and gets contracts to work in several projects around the campus

Rationale: These programs/activities will assist students to improve their skills in English, computer, internet, vocational, entrepreneurship, and self-personality.

Objective: To produce graduates mastering English, computer, Internet, vocational, entrepreneurship, and self-personality that will enable them to compete in the job market.

Mechanism and design : - R.4.1. Developing regular programs/activities to improve the Students’ English Technical Writing and Conversational Skills. This program will be carried out through the improvement of staff capacity to manage such skill. A workshop will be performed where all staff and final year students will participate. - R.4.2. Developing regular training programs/activities to improve the Students’ Computer and Internet Skills

To be continued in the next page …

…

| Activity R.4. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mechanism and design (cont’d): - R.4.3. Establishing the Student Electrical and Electronic Workshop to improve the students’ vocational skills. - R.4.4. Developing regular programs/activities to enhance Students’ Personality and Entrepreneurship |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources required : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Cost Components |  |  |  |  |  |  |  |  | Rp. |  |  |  |  | Funding Source |  |  |  |  |  |  |  |  |  |
| R.4.1. |  | Program Development |  |  |  |  |  |  |  |  | 2.085.714,00 |  |  |  |  | TPSDP + DRK |  |  |  |  |  |  |  |  |  |
| R.4.2. |  | Program Development |  |  |  |  |  |  |  |  | 10.000.000,00 |  |  |  |  | TPSDP + DRK |  |  |  |  |  |  |  |  |  |
| R.4.3. |  | Equipment |  |  |  |  |  |  |  |  | 0,00 |  |  |  |  | TPSDP |  |  |  |  |  |  |  |  |  |
|  |  | Instructional Material |  |  |  |  |  |  |  |  | 0,00 |  |  |  |  | TPSDP |  |  |  |  |  |  |  |  |  |
| R.4.4. |  | Program Development |  |  |  |  |  |  |  |  | 6.837.142,86 |  |  |  |  | TPSDP + DRK |  |  |  |  |  |  |  |  |  |
|  |  | TOTAL: |  |  |  |  |  |  |  |  | 18,922,856.86 |  |  |  |  | TPSDP |  |  |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Activity |  | Yr 1 |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  |  | Yr 4 |  |  |  |  |  |  |
| R.4.1.(Developt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.1.(Implemt.) |  |  |  |  |  | Partly re-scheduled |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.2.(Developt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.2.(Implemt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.4.(Developt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.4.(Implemt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No. | Indicators |  |  |  |  |  |  |  | Baseline |  |  |  | Mid |  |  |  |  | Status |  |  | Final |  |  |  |  |
| 1 | TOEFL Score (average) |  |  |  |  |  |  |  | 403 |  |  |  | 450 |  |  |  |  | 426 |  |  | 500 |  |  |  |  |
| 2 | Percentage Internet users among students |  |  |  |  |  |  |  | no data |  |  |  | 50% |  |  |  |  | 60% |  |  | 95% |  |  |  |  |
| 3 | Participation in the National Technical and Scientific Contests/Competition |  |  |  |  |  |  |  | 0 |  |  |  | every other year |  |  |  |  | every year |  |  | every year |  |  |  |  |
| 4 | Percentage of students who are motivated to become entrepreneurs after graduations |  |  |  |  |  |  |  | < 10% |  |  |  | 30% |  |  |  |  | 15% |  |  | 40% |  |  |  |  |
| Sustainability : All activities would be a regular student activities, and expected to generate revenues to support the continuity of student extra-curricular activities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Faizal A. Samman, ST, MT. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1.5. Name of Activity: R.5. Improving the Teaching Staff’s academic qualifications and the Administrative Staff’s/Laboratory Technicians’ competency and skills

Background: 32.61% of the Study Program’s teaching staff are above 50 years old, 84.78% are alumni, only 4 (four) Ph.D.’s and only 2 (two) of those four Ph.D.'s are Professors. Teaching loads are very high due to the student-to-lecturer ratio, which is about 36.7. The composition and the qualifications of the teaching staffs do not support efficient and productive teaching and learning process. More importantly, most of the lecturers did not have any academic experiences other than their own college experience many years back. Consequently, all teaching materials and methods delivered by those lecturers are irrelevant to the progress of the electrical engineering technology. In the second year term of the project, this activity has taken most of the time and energy of the project management at the Study Program level due to the fact that the management at the higher level did not seem to give full support to the implementation of this activity. In fact, 1 (one) of the Ph.D. candidates for the Overseas Degree Program should be returned home because the project

To be continued in the next page …

| Activity R.5. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Background: (cont’d): management at the higher level did not hesitate to make a contract violation. Inspite the unwillingness of the project management at the university level to encourage all candidates, apparently most part of this activity has been successfully implemented. Apparently, most performance indicators of this activity have shown improvement The number of Ph.D holders has increased considerably from 4 staffs (Baseline) to 6 staffs (above the mid-term project target of 5 staffs) and the number of Master degree holders has increased dramatically from 16 staffs (Baseline) to 35 staffs (which is actually the final year target). Even though there has been no paper published in any international journal as targetted, but 3 (three) papers have been published in international conference proceedings. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Rationale: This activity will include both degree training and non-degree training programs, both domestic and overseas, for the teaching staff as well as for the administrative staff and laboratory technicians. Hence, this activity will be directly beneficial to the teaching and learning process – both classroom and laboratory courses – due to the improvement of the staff qualification, competency and skills. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective: Increasing the number of Master’s and Ph.D.-degree holders to make up the composition and the qualifications of the staff. In addition to the degree-program, the non-degree programs will provide a new academic experience for the staff that will surely enrich their teaching materials and methods. Non-degree programs for administrative staff and laboratory technicians will up-grade their skills and knowledge, so it will certainly improve their services to the study program. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mechanism and design: - R.5.1. Improving the staffs’ academic qualification by attending degree-programs both overseas and domestic. - R.5.2. Improving the administrative staffs’ and laboratory technicians’ knowledge and skills by attending local vocational training programs. - R.5.3. Enlarging the staffs’ academic perspectives by attending international conferences and special domestic non-degree programs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources required (Year 3 only): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity | Cost Components |  |  |  |  | Rp. |  |  |  |  |  |  | US $ |  |  |  |  |  |  | Funding Source |  |  |  |  |  |
| R.5.1. | Staff Development |  |  |  |  | 181.600.000,00 |  |  |  |  |  |  | 416,500.00 |  |  |  |  |  |  | TPSDP |  |  |  |  |  |
| R.5.2. | Staff Development |  |  |  |  | 18.000.000,00 |  |  |  |  |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  |  |  |
| R.5.3. | Staff Development |  |  |  |  | 52.350.000,00 |  |  |  |  |  |  | 4,800.00 |  |  |  |  |  |  | TPSDP |  |  |  |  |  |
|  | TOTAL: |  |  |  |  | 251.950.000,00 |  |  |  |  |  |  | 421,300.00 |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  |  | Yr 1 |  |  |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  | Yr 4 |  |  |  |  |
| R.5.1. |  | S3 (overseas) |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
|  |  | S3 (domestic) |  |  | 2 |  | Mostly Implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
|  |  | S2 (overseas) |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |
|  |  | S2 (domestic) |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |
| R.5.2. |  | Loc. Voc. Training |  | Re-scheduled, waiting for the lab.equipment delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.5.3. |  | Int’l Seminar/Tra. |  | 1 |  |  | Partly Implemented |  |  | 1 |  |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  |
|  |  | Dom.Non-Deg. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To be continued in the next page … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Activity R.5. (continued) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Performance indicators of Activity |  |  |  |  |  |
| Indicators | Baseline | Mid | Status | Final |  |
| Number of Ph.D. (S-3 Degrees) holders | 4 | 5 | 6 | 8 |  |
| Number of Masters Degree holders | 16 | 25 | 35 | 35 |  |
| Number of papers published in Int’l Journal | 0 | 1 | 0 | 4 |  |
| Number of self-repaired laboratory equipment | 0% | 25% | 25-50% | 70% |  |
| Service-time at the Department Office (e.g. the process of issuing academic transcripts) | 1 day |  | N/A | 5 min. |  |
| Sustainability : Staff Development is always a long term investment that will last. |  |  |  |  |  |
| Person in charge: Prof.DR.Ir.Muh.Tola, M.Eng |  |  |  |  |  |

2. Academic Atmosphere

| Code | Name of Activity |  |
| --- | --- | --- |
| A.1. | Special Events, Meetings and Dialogues: |  |
|  | A.1.1. | Improving teaching methods by providing Teaching Grants |
|  | A.1.2. | Improving the students’ research (skripsi) qualities by providing Student Grants |
|  | A.1.3. | Improving the staffs’ research qualities by providing Research Grants |
|  | A.1.4. | Developing a teaching and learning process evaluation system involving students |
|  | A.1.5. | Developing the staffs’ advising abilities by providing a Guidance and Counseling Training program. |
|  | A.1.6. | Academic Dialogue and other special events involving all staffs and students. |
|  | A.1.7. | Academic Meetings. |
| A.2. | Enhancing student's learning skills and reading habits |  |

2.1. Name of Activity: A.1. Special Events, Meetings and Dialogues

Background: The relation among students, lecturers and staff is an essential factor of academic atmosphere. Due to heavy loads and tight class schedule, the interaction between students and lecturers is generally very limited, except in the supervision of the skripsi. The relation between the Electrical Engineering Student Association (HME) and the academic staff does not seem as having created a conducive environment to build a high-quality teaching-learning process. This activity has performed very well. The success of the first year term has continued to the second year, indicated mainly by the enthusiatic participation of students and staff in the competitive Teaching, Research and Student Grants. The performance indicators have shown improvement as targetted for the mid-term achievement.

Rationale: Regular academic meetings between academic staff and students will enhance the relationship among all components of the Study Program. Developing staffs' abilities in advising students, i.e. by equipping the staffs with guidance and counseling skills, can strengthen this relationship. Competitive schemes in the process of awarding Teaching, Research and Student Grants are expected to enhance the healthy academic atmosphere. A fair teaching and learning process evaluation system with students' involvement shall be carried out to complete the activity.

Objective: To build a strong relationship among all components of the Study Program in order to improve the academic atmosphere.

To be continued in the next page …

| Activity A.1. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mechanism and design : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.1. | Improving teaching methods by providing Teaching Grants to the achievers in a competitive scheme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.2. | Improving the students’ research qualities by providing Student Grants to the achievers in a competitive scheme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.3. | Improving the staffs’ research qualities by providing Research Grants to the achievers in a competitive scheme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.4. | Developing a teaching and learning process evaluation system involving students |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.5. | Developing the staffs’ advising abilities by providing a Guidance and Counseling Training program. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.6. | Academic Dialogue and other special events involving all staffs and students, including sport tournaments, engineering expo, and special events to honor the best lecturers, the best students, the employee of the year, etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.7. | Academic Meetings: Staff and Teaching Assistants, Staff and Laboratory Technicians/Assistants. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources required (Year 3 only): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Cost Components |  |  |  |  |  |  |  |  |  |  | Cost (Rp.) |  |  |  |  |  | Source of Funding |  |  |  |  |
| A.1.1. |  | Teaching Grant (2 of Rp20,000,000) |  |  |  |  |  |  |  |  |  |  | 39.800.000,00 |  |  |  |  |  | TPSDP |  |  |  |  |
| A.1.2. |  | Student Grants (10 of Rp. 5,0000,000) |  |  |  |  |  |  |  |  |  |  | 50.000.000,00 |  |  |  |  |  | TPSDP |  |  |  |  |
| A.1.3. |  | Research Grants (2 of Rp30,000,000) |  |  |  |  |  |  |  |  |  |  | 60.000.000,00 |  |  |  |  |  | TPSDP |  |  |  |  |
| A.1.4. |  | Program Development |  |  |  |  |  |  |  |  |  |  | At Cost |  |  |  |  |  | Others |  |  |  |  |
| A.1.5. |  | Program Development |  |  |  |  |  |  |  |  |  |  | 4.000.000,00 |  |  |  |  |  | TPSDP + DRK |  |  |  |  |
| A.1.6. |  | Program Development |  |  |  |  |  |  |  |  |  |  | At Cost |  |  |  |  |  | Others |  |  |  |  |
| A.1.7. |  | Program Development |  |  |  |  |  |  |  |  |  |  | At Cost |  |  |  |  |  | Others |  |  |  |  |
|  |  | TOTAL |  |  |  |  |  |  |  |  |  |  | 153.800.000,00 |  |  |  |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter) : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities |  | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  |  |  | Yr 4 |  |  |  |  |  |
| A.1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  | Baseline |  |  | Mid |  |  |  | Status |  |  |  |  | Final |  |  |
| Frequency of the special events |  |  |  |  |  |  |  |  | Every other year |  |  | 1 per year |  |  |  | 1 per year |  |  |  |  | 2 per year |  |  |
| Participation in national academic/scientific events for students |  |  |  |  |  |  |  |  | N/A |  |  | Every other year |  |  |  | Every year |  |  |  |  | Every year |  |  |
| Number of scientific papers published in national and international journal per year |  |  |  |  |  |  |  |  | N/A |  |  | 4 |  |  |  | 11 |  |  |  |  | 8 |  |  |
| Number of academic seminars and conferences hosted by the Study Program |  |  |  |  |  |  |  |  | 1 – 2 per year |  |  | 3 per year |  |  |  | 1 per year |  |  |  |  | 6 per year |  |  |
| Sustainability : In order to keep up all activities running regularly and periodically, All components of study program are expected to participate in all activities regularly. Thus, these leads to the sustainability of the academic atmosphere. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. Zaenab Muslimin,M.T. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

2.2. Name of Activity: A.2. Enhancing student's learning skills and reading habits

| Background: The condition of the Study Program’s library is not favorable for the advancement of student’s learning skills and reading habits indicated by the low percentage of students coming in for reading or checking-out books. The explanation behind this condition is that the library has: - Very limited collections of references, those that are available are out of date (11 to 20 years old) - Limited capacity of bookshelves, so many collections are not kept in order. - Reading room is cold, humid and very inconvenient The budget for the civil works and procurement of furniture for this activity is allocated for the second year of project term. The bidding process is in progress. The bidding process for the procurement of instructional materials (books and journals) has been in progress since the first year of project term, but until tis report is written, no delivery has been made. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale : - The library needs to improve its collection to attract students to come and to improve their learning skills - The library needs more bookshelves to keep all book well and neat, otherwise there will be many books spread over the floor and on the table - The library needs fixing and renovation in order to create a better and more convenient learning environment. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective : To enhance the students’ learning skills and makes reading as their primary habit and to reduce the length of study |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mechanism and design : A.2.1. Preparing the library room condition for better reading convenience A.2.2. Making a better arrangement of book collections. A.2.3. Enriching book collections and the latest published journals.. A.2.4. Establishing and maintaining a computerized library database system integrated to the Department Network. A.2.5. Developing and enhancing the students’ learning skills. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources required(Year 3 only) : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Cost Components |  |  |  |  |  |  | Rp. |  |  |  |  | US$ |  |  |  |  | Funding Source |  |  |  |  |  |
| A.2.1. | Civil Works |  |  |  |  |  |  | 0,00 |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  | DRK |  |
| A.2.2. | Furniture |  |  |  |  |  |  | 0,00 |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  |  |  |
| A.2.3. | Instruction Materials |  |  |  |  |  |  | 10,728,045.50 |  |  |  |  | 24,586.00 |  |  |  |  | TPSDP |  |  |  |  |  |
| A.2.4. | Equipment |  |  |  |  |  |  | 0,00 |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  |  |  |
| A.2.5. | Program Development |  |  |  |  |  |  | 10.000.000,00 |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  | DRK |  |
|  | TOTAL |  |  |  |  |  |  | 20.728.045,50 |  |  |  |  | 24,586.00 |  |  |  |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  |  |  | Yr 4 |  |  |  |  |  |  |
| A.2.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.3. |  | Slightly Re-scheduled |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  | Baseline |  |  | Mid |  |  |  | Status |  |  |  | Final |  |  |  |
| The number of students visiting in the library (students/day) |  |  |  |  |  |  |  |  | 10 |  |  | 15 |  |  |  | 15 |  |  |  | 22 |  |  |  |
| The number of books check out(books/day) |  |  |  |  |  |  |  |  | 9 |  |  | 15 |  |  |  | 13 |  |  |  | 18 |  |  |  |
| The number of students reading in the library (students/day) |  |  |  |  |  |  |  |  | 2 |  |  | 5 |  |  |  | 7 |  |  |  | 10 |  |  |  |
| To be continued in the next page … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Activity A.2. (continued)

Sustainability: All facilities and infrastructures are a long term investment that will still exist even after the project is over. For the continuity of the learning skills training program after the project is over, contribution from the students’ parent is expected.

Person in charge: Ir. Dewiani, MT

3. Efficiency and Productivity

| Code | Name of Activity |
| --- | --- |
| E.1. | Improving the quality of the classroom teaching and learning process (including the improvement of the qualifications of the Teaching Assistants) |
| E.2. | Expanding the Capacity of the Basic Laboratory Courses: Laboratory I and Laboratory II (Including the Improvement of the Qualifications of the Laboratory Assistants) |

3.1. Name of Activity: E.1. Improving the quality of the classroom teaching and learning process (including the improvement of the qualifications of the Teaching Assistants)

| Background: Since the end of the Engineering Acceleration Project, the quality of the classroom teaching and learning process tends to decline. This is - among others - due to the increasing number of student population. Moreover, the bureaucracy of the university does not allocate sufficient funding for lecturers’ overtime and incentives. For this particular reason, lecturers used to try to avoid burden they have by accommodating larger students in one class. The performance indicators have shown an improvement, for example the student-to-lecturer ratio has declined considerably from 25:1 (Baseline) to 14:1 which is better than the mid-term target (18:1). Furthermore, the number of classrooms is increased from 5 rooms to 9 rooms, which is actually the final target. Most classrooms are air-conditioned to create a better teaching and learning environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale : The first thing to do to increase the quality of the classroom teaching and learning process is to socialize the vision and mission of the Study Program to all part of departments (lecturers, students, and staffs). Providing high quality classroom facilities, upgrading students-to-lecturer ratio gradually, and decreasing the number of incoming students may also help the situation. In addition to that, high quality teaching-assistantship is a very important factor to support the quality improvement effort. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective: To develop effective classroom teaching and learning process that will produce higher quality graduates. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mechanism and design : E.1.1. Identifying problems and socialize them to all components in meetings and discussions. E.1.2. Establishing a solid teaching-assistantship. E.1.3. Improving the quality of teaching and learning process, especially in the utilization of Internet for education, communication media and educational technology. E.1.4. Optimizing room utilization. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources required (Year 3 only) : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity | Cost Components |  |  |  |  |  |  | Rp |  |  |  |  | US$ |  |  |  |  | Funding Source |  |  |  |  |  |
| E.1.1. | Program Development |  |  |  |  |  |  | At Cost |  |  |  |  |  |  |  |  |  | Others |  |  |  |  |  |
| E.1.2. | Program Development |  |  |  |  |  |  | 10.000.000,00 |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  | DRK |  |
| E.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Equipment |  |  |  |  |  |  | 0,00 |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  |  |  |
| E.1.4. | Civil Works |  |  |  |  |  |  | 0,00 |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  | DRK |  |
|  | Furniture |  |  |  |  |  |  | 0,00 |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  | 10.000.000,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To be continued in the next page … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity E.1. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity | Yr 1 |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  | Yr 4 |  |  |  |  |  |  |
| E.1.1. | Slightly Re-scheduled |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.1.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.1.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  |  | Baseline |  |  |  |  | Mid |  |  | Status |  |  | Final |  |  |
| Meeting and discussion (times/month) |  |  |  |  |  |  |  |  |  | - |  |  |  |  | 2 |  |  | 1 |  |  | 4 |  |  |
| Recruited Teaching Assistants (students/year) |  |  |  |  |  |  |  |  |  | - |  |  |  |  | 30 |  |  | 3 |  |  | 50 |  |  |
| Participation in trainings (persons/year) |  |  |  |  |  |  |  |  |  | - |  |  |  |  | 20 |  |  | 3 |  |  | 40 |  |  |
| Student-to-lecturer ratio |  |  |  |  |  |  |  |  |  | 25:1 |  |  |  |  | 18:1 |  |  | 14:1 |  |  | 12:1 |  |  |
| Excess loads per semester (SKS) |  |  |  |  |  |  |  |  |  | 150 |  |  |  |  | 75 |  |  | 1.5 |  |  | 0 |  |  |
| Classrooms (rooms) |  |  |  |  |  |  |  |  |  | 5 |  |  |  |  | 9 |  |  | 9 |  |  | 9 |  |  |
| Percentage of students who are satisfied with the teaching and learning process. |  |  |  |  |  |  |  |  |  | N/A |  |  |  |  | 50% |  |  | N/A |  |  | 95% |  |  |
| Sustainability: The improvement of efficiency and productivity of the classroom teaching and learning process will reduce educational costs, so in the long run the benefit will return to the Study Program and to the community. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir.H.Subaer Kanata |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

3.2. Name of Activity: E.2. Expanding the Capacity of the Basic Laboratory Courses: Laboratory I and Laboratory II (Including the Improvement of the Qualifications of the Laboratory Assistants).

Background: Basic laboratory courses (Laboratory I and II) provide 31 experiments in 4 (four) laboratories, i.e. Basic Circuit Laboratory (9 exp.), Radio Telecommunication and Microwave Laboratory (10 exp.), Computer Software Laboratory (3 exp.), and Electrical Machines Laboratory (6 exp.) [see Appendix III.37 on page III-Ap-20]. These laboratory courses are very crowded, they are always conducted in 1 or 2 shifts per day by a group of 4 to 10 students per experiment using very limited modules and equipment – both in terms of the quantity and quality – and limited laboratory spaces experiments. The facilities were intended to accommodate only 100 admitted student per year, but since 1995 have been forced to accept three times the capacity. Moreover, the schedule of those laboratory courses is very tight causing Laboratory I and III (odd semester) and Laboratory II and IV (even semester) unable to be committed at the same time, as the consequence of that, supported equipments should be used almost continuously. The laboratory courses do not serve their purpose to provide students with practical experiences because they have very short time in the laboratory. Upgrading and repairing the number of modules, equipment and renovation and reposition of the room's function will enable the provision of laboratory courses to reach an almost ideal circumstances, for instance: the lab courses can be conducted by 1 shift/day, 3 students/group, and Laboratory I and III (odd semester) and Laboratory II and IV (odd semester) can be conducted at the same time. The sub-activities of this Activity E.2. is similar to those of Activity R.1.. The difference is in the laboratory courses taken care of. The Activity R.1. discussed previously was designed to update the course materials of advance Laboratory III and IV, while this Activity E.2. was proposed to expand the capacity of basic Laboratory I and II.

Rationale - Repairing/increasing/additional number of modules/equipment will enable: - to improve the number of shifts from 2 to 1 shift per day. - to improve the number of students per group from (4-10) students to (3-6) students per group.

To be continued in the next page …

| Activity E.2.(continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale (cont’d): - Renovating and reposition of room's function will enable: - to increase the number of groups/experiment/day from 1 group/experiment/day to 2 groups/experiment/day. - to make shorter time range of experiments because Laboratory (I and III) and laboratory (II and IV) are running together. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective: To equip of graduates with a practical understanding of Basic Electrical Engineering courses. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mechanism and design : E.2.1. Assessing the existing laboratories condition, mainly in terms of organizational and management aspects, environmental and utilities setting, and the quality of laboratory course materials. E.2.2. Preparing the standard workplace and required utilities in the laboratories. E.2.3. Repairing and renewing the existing experiment modules, instruments and parts. Expanding the capacity of the laboratories serving the Laboratory I and II courses. E.2.4. Commissioning test of the new laboratory equipment. E.2.5. Developing experiment guides and related laboratory assistant training materials. E.2.6. Implementing and evaluating the updated experiment modules for Laboratory I and II courses |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources required (Year 3 only): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activity | Cost Components |  |  |  |  |  |  | Rp |  |  |  |  |  | US $ |  |  |  |  | Source of Funding |  |  |  |  |  |  |  |
| E.2.1. | Program Development |  |  |  |  |  |  | 0,00 |  |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  | DRK |  |  |  |
| E.2.2. | Furniture |  |  |  |  |  |  | 0,00 |  |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  |  |  |  |  |
|  | Civil Works |  |  |  |  |  |  | 0,00 |  |  |  |  |  |  |  |  |  |  | TPSDP |  |  |  | DRK |  |  |  |
| E.2.3. | Equipment |  |  |  |  |  |  | 0,00 |  |  |  |  |  | 0.00 |  |  |  |  | TPSDP |  |  |  |  |  |  |  |
| E.2.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.5. | Program Development |  |  |  |  |  |  | 10.000.000,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DRK |  |  |  |
| Total |  |  |  |  |  |  |  | 10.000.000,00 |  |  |  |  |  | 0.00 |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activity |  | Yr 1 |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |  | Yr 4 |  |  |  |  |  |  |
| E.2.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.2. |  | Delayed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.6. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  |  | Baseline |  |  |  |  | Mid |  |  | Status |  |  |  | Final |  |  |  |  |
| Number of students per-group |  |  |  |  |  |  |  |  |  | 4-10 |  |  |  |  | 3-6 |  |  | 3-6 |  |  |  | 2-4 |  |  |  |  |
| Repaired, updated and renewed experiment modules and test instruments |  |  |  |  |  |  |  |  |  | 0% |  |  |  |  | 50% |  |  | 25%-50% |  |  |  | 100% |  |  |  |  |
| Sustainability : Staff, students and laboratory assistants are expected to maintain and develop these basic laboratory in the long run. They should be self-sufficient in repair and maintenance. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. H.A. Rasjid Muhammad |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

4. Access and Equity

| Code | Name of Activity |  |
| --- | --- | --- |
| AE. | Improving the access and equity of the Study Program for students originated from remote areas in the Eastern Region of Indonesia and other less economically advantageous communities. |  |
|  | AE.1 | Recruiting and Socializing in Remote Areas in the Region of Indonesia |
|  | AE.2. | Developing a Matriculation Program for New Students from Remote Areas |
|  | AE.3 | Administering and Mediating Student Financial Aids Programs |

4.1. Name of Activity:  AE. Improving the access and equity of the Study Program for students originated from remote areas in the Eastern Region of Indonesia and other less economically advantageous communities.

| Background: The function of a higher education institution is to accommodate the needs of the people to acquire the skills and knowledge. This should include the people from the less economically advantageous and from remote areas. It is a well known fact that there is a significant gap in the mastery of basic sciences between potential students from suburb and rural area, from down-town and remote places. This gap has made a inequality of opportunity among people to access a higher institution. Note: This Activity AE has been taken care of at the university level under a program called “Partnership Program” (Program Kemitraan). In this program, the university - in cooperation with the surrounding county governments (Pemerintah Kabupaten) - is recruiting new students from various area in the region. Those new students are admitted without having to participate in the traditional admission test (SPMB a.k.a. UMPTN). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale: It is a social obligation for the Study Program to make an effort to close the gap mention in the background. Socialization of the Study Program will open the opportunity wider to any potential student coming from the remote area and lower economic level, particularly in the Eastern Regionof Indonesia. Developing materials and methods of matriculation sessions intended primarily for recruited students are necessary to be committed in order to equalize their basic scientific knowledge. Negotiating and persuading local government or companies to set up funding for those student is also needed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective: To close the gap of opportunity among people in acquiring knowledge and skills from a higher education institution. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mechanism and design : - AE.1. Recruiting and Socializing in Remote Areas in the Eastern Region of Indonesia - AE.2. Developing a Matriculation Program for New Students from Remote Areas - AE.3. Administering and Mediating Student Financial Aids Programs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources required : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  |  | Cost Components |  |  |  |  |  | Rp. |  |  |  |  |  |  | Funding Source |  |  |  |
| AE.1., 2 and 3 |  |  | Program Development |  |  |  |  |  | At Cost |  |  |  |  |  |  | Others |  |  |  |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Yr 1 |  |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  | Yr 4 |  |  |  |  |
| AE.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AE.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AE.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To be continued in the next page … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Activity AE(continued) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Performance indicators of Activity : |  |  |  |  |  |
| Indicators | Baseline | Mid | Status | Final |  |
| Percentage of students admitted from remote areas | No data | 5% | N/A | 10% |  |
| Academic performance of matriculation program participants (average first year GPA) | No data | 2.75 | N/A | 3.00 |  |
| Number of fellowships for students from remote area | 0 | 4 | N/A | 8 |  |
| Sustainability: At the end of the project, it is expected that co-operations with the external parties such as provincial governments, NGOs, companies, alumni, professional association, etc. to take care of this program will continue. |  |  |  |  |  |
| Person in charge: Ir. H. Gassing, MT |  |  |  |  |  |

5. Internal Management and Organization

| Code | Name of Activity |  |
| --- | --- | --- |
| IMO | Improving the Department’s administration system |  |
|  | IMO.1. | Establishing the Study Program’s Management Information System and Database |
|  | IMO.2. | Establishing an Effective Teaching-Learning Process Monitoring and Evaluation System |

5.1. Name of Activity: IMO Improving the Department’s administration system

| Background: One of the problems faced by the Study Program is in handling and processing data for academics and students administration needs. Only 5 (five) department administrative staffs daily serve the needs of around 1000 students. Data lost, improper handling and inaccuracy are not uncommon problems. The resources required for this Activity are all in the form of procurement of equipment included in the Year 1 International Shopping package. The bidding progress is still in. progress and at the final stage. The expected date of delivery is early 2005. At the university level, an ISS TPSDP project entitled “Management Information Systems” (MIS) is in progress. According to the Project Coordinator of the MIS Project, the Study Program will be one of the participating sites of his project. Any development of information system in the Study Program should be under the MIS project coordination |  |  |  |
| --- | --- | --- | --- |
| Rationale: The advantages of having an automatic and integrated management information system and database are: - Easier to make data updating. - Faster academic data processing - Accessible from the network |  |  |  |
| Objective: To develop a management information system and database for academics and students. |  |  |  |
| Mechanism and design : - IMO.1. Establishing the Study Program’s Management Information System and Database - IMO.2. Establishing an Effective Teaching-Learning Process Monitoring and Evaluation System |  |  |  |
| Resources required (Year 3 only) : |  |  |  |
| Activity | Cost Components | Rp | Funding Source |
| IMO.1. | Equipment | 0,00 | TPSDP |
| IMO.2. | Equipment | 0,00 | TPSDP |
|  | TOTAL: | 0,00 |  |
| To be continued in the next page … |  |  |  |

| Activity IMO(continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Yr 1 |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  | Yr 4 |  |  |  |  |  |
| IMO.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IMO.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  | Baseline |  |  |  | Mid |  |  |  | Status |  |  | Final |  |  |  |  |
| Service time |  |  |  |  |  | 1 day |  |  |  | - |  |  |  | 30 minutes |  |  | 5 minutes |  |  |  |  |
| Data Archive Update |  |  |  |  |  | 14 days |  |  |  | - |  |  |  | Every Minute |  |  | Every Minute |  |  |  |  |
| Monitoring and Evaluation |  |  |  |  |  | N/A |  |  |  | - |  |  |  | Available |  |  | Available |  |  |  |  |
| Sustainability : Students participation in system maintenance and development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. Indrajaya M, MT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Chapter 2.3. THIRD YEAR IMPLEMENTATION PLAN

2.3.1. PROJECT ORGANIZATION

The organizational set-up of the Project will reflect the on-going process that has been started since the preparation of the Self-Evaluation Report of the TPSDP Batch 1 in the year 2000. The structure of the organization is clearly described in Figure II-2. There are 11 (eleven) Persons in Charge, each one for each activity. Those Persons in Charge produced the list of sub-activities to improve RAISE++ as elaborated previously in Chapter 2.2, so it is clear that they have been involved since the planning stages of this project.

Quality Assurance

Prof. Dr. Ir. H. Nadjamuddin Harun, MS

Prof. Dr. Ir. H.M. Arief, Dipl.Ing.

|  |  | The Study Program Project Coordinator Ir. H. Tahir Ali |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Project Secretary: Muhammad Niswar, ST, MIT |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  |  |  |  |  | PERSONS IN CHARGE: |  |  |
| R.1. Advance Laboratory Courses Update |  |  |  |  |  |  |  |  |  | Ir. Hj. Nien K. Nauman |  |  |
| R.2. Industrial Relation Programs |  |  |  |  |  |  |  |  |  | Ir. A. Toyib Rahardjo, M.Sc |  |  |
| R.3. NEW Teaching/Laboratory Courses Development |  |  |  |  |  |  |  |  |  | Dr.Ir.H. Rhiza S. Sadjad, MSEE |  |  |
| R.4. Student Co-Curricular Activities |  |  |  |  |  |  |  |  |  | Faizal A. Samman, ST, MT |  |  |
| R.5. Staff Composition and Qualification Improvement |  |  |  |  |  |  |  |  |  | Prof. Dr. Ir. H.M. Tola, M.Eng. |  |  |
| A.1. Departmental Meeting and Dialogue |  |  |  |  |  |  |  |  |  | Ir. Zaenab Muslimin, MT |  |  |
| A.2. Student’s Learning and Reading Skills Enhancement |  |  |  |  |  |  |  |  |  | Ir. Dewiani, MT |  |  |
| E.1. Classroom Teaching-Learning Process Improvement |  |  |  |  |  |  |  |  |  | Ir. H. Subaer Kanata |  |  |
| E.2. Basic Laboratory Courses Expansion and Quality Improvement |  |  |  |  |  |  |  |  |  | Ir. H.A. Rasjid Muhammad |  |  |
| AE Remote Area “Reaching-Out” Program |  |  |  |  |  |  |  |  |  | Ir. H.Gassing, MT |  |  |
| IMO Department’s MIS and Database Development |  |  |  |  |  |  |  |  |  | Ir. Indra Jaya Mansyur, MT |  |  |
|  | Figure II-2 The Organizational Structure of the Project at the Study Program level |  |  |  |  |  |  |  |  |  |  |  |

There is a slight change in the position of the Project Coordinator. Former Project Coordinator is proposed to take over the position of the Person In Charge (PIC) of Activity R.3., and his place is taken by the former PIC of Activity R.3. The purpose of this exchange is to solve the problem of coordination and communication with the Director of SPMU at the university level who is clearly indicated not in favor of the former Project Coordinator.  The PIC of activity A.2. also resigned and her place is proposed to be taken over by a new PIC.

2.3.2. ACTIVITY and SCHEDULING

Details of all planned activities in this project have been thoroughly discussed in previous sections in terms of the sub-activities. Basically at the third year term of the implementation of this project, most activities will be scheduled as the continuation of the activities originally planned to be implemented at the first and second year term. The activities that were already planned to be implemented in the third year term of the project are to be implemented as planned.

2.3.3. MONITORING and EVALUATION MECHANISM

The principle of the "Total Quality Management" (TQM) will be applied in all monitoring and evaluation mechanism of this project. It means that all monitoring and evaluation mechanism will be embedded in all sub-activities without exception.

There are at least 2 (two) categories of monitoring activities, namely the monitoring of the physical implementation of the proposed project itself, and the monitoring of the educational process as the result of the project. The latter (including monitoring of the laboratory activities, classroom activities, the teaching and learning process, student extra-curricular and co-curricular activities, etc.) will become parts of the Activity IMO (see page Revised-SPP II-17), and the follow-up of this activity will be taken care of by Activity E.1. (see Revised SPP page II-12). The results of this monitoring mechanism will be the mid-term and the final-term data to compute the performance indicators discussed previously.

A built-in mechanism will be applied to all activities led by each Person in Charge, including the procurement process of all laboratory equipment and experiment modules, the implementation of staff development sub-activities, administration, civil works and teaching facilities improvement. All procurement within the project plan should be monitored closely. This will include the process of annual budget revisions, the preparation of bidding documents, the bidder selection, up to testing and commissioning and after sales services and user training if necessary. The monitoring mechanism for all civil works implementation, for instance, should include the selection of building consultants, the physical design and cost-estimation, the bidding and selection of contractors, the implementation supervisory activities and commissioning.

A continuous (at least weekly, or more often if necessary) evaluation mechanism should be applied to the project implementation. All Persons in Charge should prepare their reports at least in a weekly basis to the Project Coordinator. All performance indicators should be compiled every semester and presented in a general staff meeting to determine any progress made. The fourth general staff meeting will be the mid-term project. All mid-term performance targets will be evaluated to determine whether the project should be continued to the next half term or just terminated there. If the project continues, then over-all revisions should be made to secure the achievement of all final performance targets and the sustainability of this project.

At the end of the fourth year of the project implementation, a thorough evaluation should be made in order to guarantee the public accountability of this project. This evaluation may have to involve all stakeholders, including the students' parental-representatives, the industrial world, the local and central government, and all other concerned parties. The Study Program may be planning to implement the international standard of higher education accreditation systems - such as the ABET criteria - at this stage.  The final evaluation will be the commencement of the end of the project and at the same time it will become a mechanism to build the commitment to work together for the long future of the Study Program. The Quality Assurance Team will closely supervise all those mechanisms.

Chapter 2.4. PROPOSED BUDGET

Figure II-3 shows the budget plan for the third year term, which is detailed in terms of activities in Figure II-5.

| Eligible Cost Components |  | YEAR3 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | ADB |  | GOI (Rp) |  | DRK |
|  |  | US$ | Rp | US$ | TPSDP | Rp |
| 1. | Staff Development |  |  |  |  |  |
|  | Domestic degree training |  | 0.00 |  | 39,600,000.00 |  |
|  | Domestic non degree training |  | 0.00 |  | 56,650,000.00 |  |
|  | Overseas degree training | 118,700.00 |  |  |  |  |
|  | Overseas non degree training | 0.00 |  |  |  |  |
| 2. | Civil Works |  | 19,630,511.60 |  | 42,605,360.80 | 0.00 |
| 3. | Furniture and Equipment |  |  |  |  |  |
|  | Furniture |  | 0.00 |  | 0.00 |  |
|  | Equipment | 36,281.10 | 4,199,000.00 | 48,000.00 | 9,826,000.00 |  |
| 4. | Program Development |  |  |  | 24,150,325.50 | 38,139,674.50 |
| 5. | Instructional Materials | 13,207.24 | 10,728,045.50 | 11,378.76 | 0.00 |  |
| 6. | Consultant Services |  |  |  |  |  |
|  | International |  |  |  |  |  |
|  | Domestic |  |  |  |  |  |
| 7. | Research and Studies |  | 50,000,000.00 |  | 130,000,000.00 |  |
| 8. | Project Management |  |  |  |  |  |
|  | Operational support |  |  |  |  | 30,000,000.00 |
|  | O&M of Facilities |  |  |  |  | 38,978,116.50 |
|  | Sub-PIU Operation |  |  |  |  | 94,770,000.00 |
| TOTAL |  | 168,188.34 | 84,557,557.10 | 59,378.76 | 302,831,686.30 | 201,887,791.00 |
|  |  | 60.00% |  | 32.00% |  | 8.00% |

Figure II-5

Proposed Budget for the Third Year Term 2005

| Eligible Cost Components |  | YEAR3 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | ADB |  | GOI |  | DRK |
|  |  | US$ | Rp | US$ | TPSDP Rp | Rp |
| 1. | Staff Development |  |  |  |  |  |
|  | Domestic degree training |  | 0.00 |  | 39,600,000.00 |  |
|  | Domestic non degree training |  | 0.00 |  | 56,650,000.00 |  |
|  | Overseas degree training | 118,700.00 |  |  |  |  |
|  | Overseas non degree training | 0.00 |  |  |  |  |
| 2. | Civil Works |  | 19,630,511.60 |  | 42,605,360.80 | 0.00 |
|  | R.1 |  | 19,630,511.60 |  | 42,605,360.80 | 0.00 |
|  | A.2 |  | 0.00 |  | 0.00 | 0.00 |
|  | E.1 |  | 0.00 |  | 0.00 | 0.00 |
|  | E.2 |  | 0.00 |  | 0.00 | 0.00 |
| 3. | Furniture and Equipment |  |  |  |  |  |
|  | Furniture |  | 0.00 |  | 0.00 |  |
|  | R.1 |  |  |  |  |  |
|  | A.2 |  |  |  |  |  |
|  | E.1 |  |  |  |  |  |
|  | E.2 |  |  |  |  |  |
|  | Equipment | 36,281.10 | 4,199,000.00 | 48,000.00 | 9,826,000.00 | 0.00 |
|  | R.1 | 15,051.10 | 4,199,000.00 | 48,000.00 | 9,826,000.00 | 0.00 |
|  | R.3.1 | 21,230.00 | 0.00 |  | 0.00 | 0.00 |
|  | R.3.2 | 0.00 | 0.00 |  | 0.00 | 0.00 |
|  | R.4 | 0.00 | 0.00 |  | 0.00 | 0.00 |
|  | A.2 | 0.00 | 0.00 |  | 0.00 | 0.00 |
|  | E.1 | 0.00 | 0.00 |  | 0.00 | 0.00 |
|  | E.2 | 0.00 | 0.00 |  | 0.00 | 0.00 |
|  | IMO.1 | 0.00 | 0.00 |  | 0.00 | 0.00 |
|  | IMO.2 | 0.00 | 0.00 |  | 0.00 | 0.00 |
| 4. | Program Development |  |  |  | 24,150,325.50 | 38,139,674.50 |
|  | R.1.1 |  |  |  | 0.00 | 0.00 |
|  | R.1.5 |  |  |  | 2,000,000.00 | 3,000,000.00 |
|  | R.2.1 |  |  |  | 8,000,000.00 | 12,000,000.00 |
|  | R.2.2 |  |  |  | 0.00 | 0.00 |
|  | R.2.3. |  |  |  | 0.00 | 0.00 |
|  | R.4.1 |  |  |  | 0.00 | 0.00 |
|  | R.4.2 |  |  |  | 3,600,000.00 | 4,400,000.00 |
|  | R.4.4 |  |  |  | 650,325.50 | 6,639,674.50 |
|  | A.1.5 |  |  |  | 1,800,000.00 | 2,200,000.00 |
|  | A.2.5 |  |  |  | 3,600,000.00 | 4,400,000.00 |
|  | E.1.2/3 |  |  |  | 4,500,000.00 | 5,500,000.00 |
|  | E.2.1 |  |  |  | 0.00 | 0.00 |
|  | E.2.5. |  |  |  | 0.00 | 0.00 |
| 5. | Instructional Materials | 13,207.24 | 10,728,045.50 | 11,378.76 | 0.00 |  |
|  | R.4.3 | 0.00 | 0.00 |  | 0.00 |  |
|  | A.2.3 | 13,207.24 | 10,728,045.50 | 11,378.76 | 0.00 |  |
| 6. | Consultant Services |  |  |  |  |  |
|  | International |  |  |  |  |  |
|  | Domestic |  |  |  |  |  |
| 7. | Research and Studies |  | 50,000,000.00 |  | 130,000,000.00 |  |
|  | R.3.1 |  | 20,000,000.00 |  | 0.00 |  |
|  | A.1.1 |  | 0.00 |  | 20,000,000.00 |  |
|  | A.1.2 |  | 0.00 |  | 50,000,000.00 |  |
|  | A.1.3 |  | 30,000,000.00 |  | 60,000,000.00 |  |
| 8. | Project Management |  |  |  |  | 163,748,116.50 |
|  | Operational support |  |  |  |  | 30,000,000.00 |
|  | O&M of Facilities |  |  |  |  | 38,978,116.50 |
|  | Sub-PIU Operation |  |  |  |  | 94,770,000.00 |
| TOTAL |  | 168,188.34 | 84,557,557.10 | 59,378.76 | 302,831,686.30 | 201,887,791.00 |
|  |  | 60.00% |  | 32.00% |  | 8.00% |

Figure II-6

Proposed Budget for the Third Year Term 2005 (per-Activity)

Appendix - 1

| Detailed Specifications : Staff Development - Domestic Degree Training - Year 3 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of Tentative Candidates |  | Field Of Study | Targeted University to apply |  | Estimated Length Of study |  | Estimated Cost (Rp.) | Program |  |  |  |
| Indra Bayu |  | Telecommunication | ITS |  | Expected to complete by Sept. 2005 |  | 9,950,000.00 | S2 |  |  |  |
|  |  |  |  |  | Total Cost : |  | 9.950.000,00 |  |  |  |  |

Appendix – 2

| Detailed Specifications : Staff Development - Domestic Non - Degree Training-year 3 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of Tentative Lectures | Field Of Study | Targeted University/Institution to Apply | Estimated Length of Study (months) | Estimated Cost |
| Christoforus Y. | Computer Engineering | ITB | 2 | 13,750,000.00 |
| M.Niswar | Computer Engineering | INIXINDO, Surabaya | 1 | 13,750,000.00 |
| Amil A Ilham | Computer Engineering | INIXINDO, Surabaya | 1 | 13,750,000.00 |
| M.Tola | Electrical Power | UI | 1 | 7,700,000.00 |
| Nadjamuddin Harun | Control System | UGM | 1 | 7,700,000.00 |
|  |  |  | Total Cost : | 56,650,000.00 |

| Name of Tentative | Field Of Study | Targeted University/Institution to Apply | Estimated Length (month) | Estimated Cost (Rp) |
| --- | --- | --- | --- | --- |
| Laboratory Technicians : |  |  |  |  |
| Suleman Lebang | Laboratory Maintenance | Pusdiklat PLN Wilayah VIII | 1 | *2,000,000.00 |
| Cornelius Pelluk | Laboratory Maintenance | Pusdiklat PLN Wilayah VIII | 1 | *2,000,000.00 |
| Idris Hamid | Laboratory Maintenance | Pusdiklat PLN Wilayah VIII | 1 | *2,000,000.00 |
| Mustakim,ST | Laboratory Maintenance | BLK Makassar | 1 | *2,250,000.00 |
| Amsal Salim,ST | Laboratory Maintenance | BLK Makassar | 1 | *2,250,000.00 |
| Sampara,ST | Computer Networking | Cordova Computer | 1 | *2,250,000.00 |
| Administrative Staff : |  |  |  |  |
| Hasrawati | Office Management | LPM Fajar | 1 | *1,750,000.00 |
| Hasdiana | Office Management | LPM Fajar | 1 | *1,750,000.00 |
| Mustawil | Computer Networking | Cordova Computer | 1 | *2,250,000.00 |
| Ruslan | Maintenance | BLK Makassar | 1 | *2,250,000.00 |
| Samsiah | Office Management | LPM Fajar | 1 | *1,750,000.00 |
| Zainuddin | Maintenance | BLK Makassar | 1 | *2,250,000.00 |
|  |  |  | Total Cost : | 23,725,000.00 |

- Budget updated

Appendix – 3

| Detailed Specifications : Staff Development - Overseas Degree training - year 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of Tentative |  |  | Field Of Study |  |  | Targeted University |  | Estimated Length |  |  |  | Estimated |  | Program |  |  |  |  |  |
| Candidates |  |  |  |  |  | to apply |  | of study(years) |  |  |  | Cost |  |  |  |  |  |  |  |
| Tadjuddin Waris |  |  | Electrical Power |  |  | Curtin University, Australia |  | 1.00 |  |  |  | 21000 |  | S3 |  |  |  |  |  |
| Elyas Palantei |  |  | Telecommunication |  |  | Griffith University, Australia |  | 1.00 |  |  |  | 21000 |  | S3 |  |  |  |  |  |
| Samuel Panggalo |  |  | Telecommunication |  |  | University of Newcastle, Australia |  | 1.00 |  |  |  | 21000 |  | S3 |  |  |  |  |  |
| Hasniaty |  |  | Telecommunication |  |  | UTM, Malaysia |  | 1.00 |  |  |  | 13200 |  | S3 |  |  |  |  |  |
| Wardi |  |  | Telecommunication |  |  | University of South Australia, Australia |  | 1.00 |  |  |  | 21500 |  | S2 |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  | Total Cost : |  |  |  | 97700 |  |  |  |  |  |  |  |
|  | Appendix-4 Detailed Specifications : Staff Development - Overseas non-Degree Training – Year 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Name of Tentative |  |  | Field Of Study |  |  | Targeted University/Institution |  |  | Estimated Length |  |  |  |  | Estimated |  |  |  |  |
|  | Candidates |  |  |  |  |  | to apply |  |  | of study(days) |  |  |  |  | Cost (US$) |  |  |  |  |
|  | Muhammad Niswar |  |  | Telecommunication |  |  | International Conference, Hongkong |  |  | 3 |  |  |  |  | 1600 |  |  |  |  |
|  | Appendix-5 Detailed Specifications : Civil Works |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | No. | Facilities |  |  | Requirment |  |  |  | Function |  | Quantity |  | Estimated |  |  | Remark |  |  |  |
|  |  |  |  |  | Specification |  |  |  |  |  | (m2) |  | Cost (Rp) |  |  |  |  |  |  |
|  |  | Laboratory |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Basic Laboratory |  |  | Building repair and minor |  |  |  | Quality |  | 618 |  | 57165000 |  |  | E.2 |  |  |  |
|  |  |  |  |  | renovation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Advanced Laboratory |  |  | Building repair , minor |  |  |  | Expanding and |  | 969.14 |  | 1.56E+08 |  |  | R.1 |  |  |  |
|  |  |  |  |  | and mayor renovation |  |  |  | quality |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Class room |  |  | Building repair , minor |  |  |  | Expanding and |  | 649 |  | 2.15E+08 |  |  | E.1 |  |  |  |
|  |  |  |  |  | and mayor renovation |  |  |  | quality |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Library |  |  | Building repair , minor |  |  |  | Quality |  | 84 |  | 16540000 |  |  | A.2 |  |  |  |
|  |  |  |  |  | and mayor renovation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | TOTAL |  | 2320.14 |  | 4.45E+08 |  |  |  |  |  |  |

| NO | FACILITIES | SPESIFICATION | UNIT | UNIT COST | TOTAL | TOTAL |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | (Rp,-) |  | COST (Rp) |
| A.2 | LIBRARY |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 20000 | 110 | 2200000 |
| 2 | Lighting installation and armature | TL: 2X36 W, recessed type | unit | 250000 | 12 | 3000000 |
| 3 | Ceiling,support & acces. | plywod,steel support | M2 | 135000 | 84 | 11340000 |
|  |  |  |  |  | TOTAL A.2 | 16540000 |
| E.1 | CLASS ROOM: HL-X |  |  |  |  |  |
| 1 | Concrete for colum | K.225 | M3 | 1900000 | 16 | 30400000 |
| 2 | Concrete for beam | K.225 | M3 | 1900000 | 12 | 22800000 |
| 3 | Concrete for floor | K.225 | M3 | 1900000 | 16 | 30400000 |
| 4 | Brick | Local product, hight quality | M3 | 300000 | 20.55 | 6165000 |
| 5 | Covered with plaster 1:5 |  | M2 | 30000 | 112 | 3360000 |
| 6 | Pour Cement fondation | K.225 | M3 | 2000000 | 5 | 10000000 |
| 7 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 133 | 6650000 |
| 8 | Wall painting | Like as ICI | M2 | 20000 | 110 | 2200000 |
| 9 | Door with frame | Bayam wood | unit | 400000 | 2 | 800000 |
| 10 | Window with frame | Bayam wood | unit | 300000 | 8 | 2400000 |
| 11 | Lighting installation and armature | TL 2x36 W,recessed type ref:Philips | unit | 250000 | 12 | 3000000 |
| 12 | Power Instalation and acces. | Receptacle ref : MK | unit | 150000 | 4 | 600000 |
| 13 | Partition | wood | M2 | 100000 | 40 | 4000000 |
| 14 | Ceiling | Ply wood , with hanger steel | M2 | 135000 | 133 | 17955000 |
| 15 | Railing | Medium pipe,dia. 3 inci | M2 | 35000 | 38 | 1330000 |
|  |  |  |  |  | Sub.Total | 142060000 |
|  | CLASS ROOM: PBT 301 |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 250 | 3750000 |
| 2 | Door repairment |  | M2 | 75000 | 1 | 75000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 0 | 60 | 0 |
| 4 | Electrical Installatian repairment | Quality like as : Philips | unit | 50000 | 0 | 0 |
| 5 | Door potection | Steel | unit | 500000 | 0 |  |
|  |  |  |  |  | Sub Total | 3825000 |
|  | CLASS ROOM: PBT 302 |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 250 | 3750000 |
| 2 | Door repairment |  | unit | 75000 | 1 | 75000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 0 | 60 | 0 |
| 4 | Electrical Installatian repairment | Quality like as : Philips | unit | 50000 | 0 | 0 |
| 5 | Door potection |  | unit | 500000 | 0 | 0 |
|  |  |  |  |  | Sub Total | 3825000 |
|  | CLASS ROOM: PBT 303 |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 250 | 3750000 |
| 2 | Door repairment |  | unit | 75000 | 1 | 75000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 0 | 60 | 0 |
| 4 | Electrical Installatian repairment | Quality like as : Philips | unit | 50000 | 0 | 0 |
| 5 | Door potection |  | unit | 500000 | 0 | 0 |
|  |  |  |  |  | Sub Total | 3825000 |
|  | CLASS ROOM: PBT 304 |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 356.67 | 5350019 |
| 2 | Door repairment |  | unit | 75000 | 1 | 75000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 0 | 80 | 0 |
| 4 | Electrical Installatian repairment | Quality like as : Philips | unit | 50000 | 0 | 0 |
| 5 | Door potection |  | unit | 500000 | 0 | 0 |
|  |  |  |  |  | Sub Total | 5425019 |
|  | CLASS ROOM: PBT 401-A.B.C |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 1369 | 20535000 |
| 2 | Door repairment |  | unit | 75000 | 4 | 300000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 0 | 256 | 0 |
| 4 | Electrical Installatian repairment | Quality like as : Philips | unit | 150000 | 10 | 1500000 |
| 5 | Door potection |  | unit | 500000 | 0 | 0 |
| 6 | Partition , support and acces | portable,gipsun | M2 | 325000 | 96 | 31200000 |
|  |  |  |  |  | Sub Total | 53535000 |
|  | STUDENT SERV. FACILITIES |  |  |  |  |  |
|  | TOILET (Repairment) |  | unit | 1000000 | 3 | 3000000 |
| 1 | Electrical Installatian repairment |  | lot |  |  |  |
| 2 | Plumbing Installatian repairment |  | lot |  |  |  |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 0 | 48 |  |
| 4 | Urinoir, etc |  | lot |  | Sub Total | 3000000 |
|  |  |  |  |  | TOTAL E1. | 215495019 |
| E.2 | DEVELOPMENT QUALITY |  |  |  |  |  |
|  | BASIC CIRCUIT LABORATORY |  |  |  |  |  |
| 1 | Wall painting | Like as ICI |  | 15000 | 144 | 2160000 |
| 2 | Door repairment |  | unit | 75000 | 2 | 150000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 180 | 9000000 |
| 4 | Electrical Installatian repairment | lihgting fixture & recep. | unit | 150000 | 20 | 3000000 |
| 5 | Door potection |  | unit | 500000 | 2 | 1000000 |
| 7 | Partition , support and acces | portable,gipsun | M2 | 400000 | 0 | 0 |
|  |  |  |  |  | Sub Total | 15310000 |
|  | ELECTRICAL MACHINE LAB. |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 333 | 4995000 |
| 2 | Door repairment |  | unit | 75000 | 2 | 150000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 216 | 10800000 |
| 4 | Electrical Installatian lighting fixture | Exposed type TL: 2x36 W | unit | 250000 | 10 | 2500000 |
| 5 | Door potection |  | unit | 500000 | 2 | 1000000 |
| 7 | Partition , support and acces |  | M2 | 100000 | 20 | 2000000 |
|  |  |  |  |  | Sub Total | 21445000 |
|  | PREPARATION CLASS |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 100 | 1500000 |
| 2 | Door repairment |  | unit | 100000 | 0 | 0 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 112 | 5600000 |
| 4 | Electrical Installatian lighting fixture | Exposed type TL: 2x36 W | unit | 250000 | 0 | 0 |
| 5 | Rolling door |  | unit | 1E+07 | 0 | 0 |
| 6 | Partition , support and acces |  | M2 | 100000 | 0 | 0 |
| 7 | Roop repair |  | M2 | 20000 | 0 | 0 |
|  |  |  |  |  | Sub Total | 7100000 |
|  | SOFTWARE LABORATORY(HME) |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 144 | 2160000 |
| 2 | Door repairment |  | unit | 75000 | 2 | 150000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 110 | 5500000 |
| 4 | Electrical Installatian repairment | lihgting fixture & recep. | unit | 150000 | 10 | 1500000 |
| 5 | Door potection |  | unit | 500000 | 0 | 0 |
| 6 | Partition , support and acces |  | M2 | 100000 | 40 | 4000000 |
|  |  |  |  |  | Sub Total | 13310000 |
|  |  |  |  |  | TOTAL E.2 | 57165000 |
| R.1 | ADVANCED LABORATORY |  |  |  |  |  |
|  | RADIO TEL.& MICROWAVE |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 144 | 2160000 |
| 2 | Door repairment |  | unit | 75000 | 1 | 75000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 152 | 7600000 |
| 4 | Electrical Installatian repairment | lihgting fixture & recep. | unit | 150000 | 12 | 1800000 |
| 5 | Door potection |  | unit | 500000 | 1 | 500000 |
| 6 | Partition , support and acces |  | M2 | 100000 | 0 | 0 |
|  |  |  |  |  | Sub Total | 12135000 |
|  | TELEMATICS |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 100 | 1500000 |
| 2 | Door repairment |  | unit | 75000 | 1 | 75000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 152 | 7600000 |
| 4 | Electrical Installatian repairment | lihgting fixture & recep. | unit | 150000 | 4 | 600000 |
| 5 | Door potection |  | unit | 500000 | 1 | 500000 |
| 6 | Partition , support and acces |  | M2 | 100000 | 0 | 0 |
|  |  |  |  |  | Sub Total | 10275000 |
|  | POWER ELECTRONICS LAB. |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 154 | 2310000 |
| 2 | Door repairment |  | unit | 75000 | 2 | 150000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 110 | 5500000 |
| 4 | Electrical Installatian repairment | lihgting fixture & recep. | unit | 150000 | 6 | 900000 |
| 5 | Door potection |  | unit | 500000 | 2 | 1000000 |
| 6 | Cost renovation and doors |  | lot | 1500000 | 1 | 1500000 |
|  |  |  |  |  | Sub Total | 11360000 |
|  | CONTROL COMP. & INSTRUMENT |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 150 | 2250000 |
| 2 | Door repairment |  | unit | 75000 | 2 | 150000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 152 | 7600000 |
| 4 | Electrical Installatian repairment | lihgting fixture & recep. | unit | 150000 | 12 | 1800000 |
| 5 | Door potection |  | unit | 500000 | 2 | 1000000 |
| 6 | Partition , support and acces |  | M2 | 100000 | 0 | 0 |
|  |  |  |  |  | Sub Total | 12800000 |
|  | ELECTRONIC AND DEVICE |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 150 | 2250000 |
| 2 | Door repairment |  | unit | 75000 | 1 | 75000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 75.5 | 3775000 |
| 4 | Electrical Installatian repairment | lihgting fixture & recep. | unit | 150000 | 5 | 750000 |
| 5 | Door potection |  | unit | 500000 | 1 | 500000 |
| 6 | Partition , support and acces |  | M2 | 100000 | 0 | 0 |
|  |  |  |  |  | Sub Total | 7350000 |
|  | HIGH VOLTAGE LAB. |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 168.332 | 2524981 |
| 2 | Door repairment |  | unit | 75000 | 1 | 75000 |
| 3 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 139.64 | 6982000 |
| 4 | Electrical Installatian | lihgting fixture | unit | 250000 | 6 | 1500000 |
| 5 | Door potection |  | unit | 500000 | 0 | 0 |
| 6 | Partition , support and acces |  | M2 | 100000 | 20 | 2000000 |
| 7 | Jar equipment repairment |  | unit | 1500000 | 1 | 1500000 |
|  |  |  |  |  | Sub Total | 14581981 |
|  | RELEY & MEASURE. LAB. |  |  |  |  |  |
| 1 | Wall painting | Like as ICI | M2 | 15000 | 102.3 | 1535000 |
| 2 | Door repairment |  | unit | 100000 | 0 | 0 |
| 3 | Ceramic tiles | WHITE 30X30 | m2 | 0 | 84 | 0 |
| 4 | Electrical Installatian repairment | lihgting fixture & recep. | unit | 150000 | 0 | 0 |
| 5 | Door potection |  | unit | 500000 | 0 | 0 |
| 6 | Partition , support and acces | bayam /teak wood | M2 | 100000 | 0 | 0 |
|  |  |  |  |  | Sub Total | 1535000 |
|  | DISTRIBUTION & INSTL. LAB. |  |  |  |  |  |
| 1 | Concrete for colum | K.225 | M3 | 1900000 | 12.49 | 22358700 |
| 2 | Concrete for beam | K.225 | M3 | 1900000 | 9.2 | 17480000 |
| 3 | Concrete for floor | K.225 | M3 | 1900000 | 9.412 | 17882800 |
| 4 | Brick | Local product | M3 | 300000 | 6 | 1800000 |
| 5 | Covered with plaster 1:5 |  | M2 | 30000 | 48 | 1440000 |
| 6 | Pour Cement fondation | K.225 | M3 | 2000000 | 2 | 4000000 |
| 7 | Ceramic tiles | WHITE 30X30 | M2 | 50000 | 104 | 5200000 |
| 8 | Wall painting | Like as ICI | M2 | 20000 | 99.56 | 1991200 |
| 9 | Door with frame | bayam wood | unit | 500000 | 2 | 1000000 |
| 10 | Window with frame | bayam wood | unit | 300000 | 2 | 600000 |
| 11 | Lighting installation and armature | ref: Phillips | unit | 250000 | 6 | 1500000 |
| 12 | Power Instalation and acces. |  | unit | 150000 | 4 | 600000 |
| 13 | Room Partition | wood | M2 | 100000 | 0 | 0 |
| 14 | Ceiling and support & acces. | plywood | M2 | 135000 | 62 | 8370000 |
| 15 | Railing | Medium pipe,dia. 3 inci | M2 | 35000 | 38 | 1330000 |
|  |  |  |  |  | Sub.Total | 85,552,700.00 |
|  |  |  |  |  | TOTAL R.1 | 155,589,681.00 |

| Appendix - 7 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Detailed specification : Equipment & Furniture - Equipment Year 3 |  |  |  |  |  |
| Equipment | Spesification | QTY | Unit Cost | Estimated Cost | Remark |
|  |  |  | (US $) | (US $) |  |
| Bacis Exp. For Optical Transmission Tech. |  |  |  |  | R.1.IV.2.1.1 |
| (Equiv. MTS 7.2.6.1 Leybold) Consist of : |  |  |  |  | R.1.IV.2.1.1.1 |
| Fiber - Optic Transmitter | Equiv. 736411 Leybold | 1 | 255.42 | 255.42 | R.1.IV.2.1.1.2 |
| Fiber - Optic Receiver | Equiv. 736412 Leybold | 1 | 197.08 | 197.08 | R.1.IV.2.1.1.3 |
| Fiber Micropositioner | Equiv. 736415 Leybold | 1 | 536.25 | 536.25 | R.1.IV.2.1.1.4 |
| Mode Scrambler | Equiv. 736416 Leybold | 1 | 31.25 | 31.25 | R.1.IV.2.1.1.5 |
| Set of Fiber- Optic Waveguides & Accessoris | Equiv. 736421 Leybold | 1 | 294.58 | 294.58 | R.1.IV.2.1.1.6 |
| Fiber-Optic Microscope | Equiv. 736429 Leybold | 1 | 118.33 | 118.33 | R.1.IV.2.1.1.7 |
| Hand-Held Power Meter, Optical | Equiv. 736435 Leybold | 1 | 473.33 | 473.33 | R.1.IV.2.1.1.8 |
| Coil 1000 Turns | Equiv. 59084 Leybold | 1 | 24.17 | 24.17 | R.1.IV.2.1.1.9 |
| Iron Core 18 x 18 x 55 mm | Equiv. 59085 Leybold | 1 | 12.29 | 12.29 | R.1.IV.2.1.1.10 |
| Data Transmission With Fibre Optic Lines |  |  |  |  | R.1.IV.2.1.2 |
| (Equiv. PTS 7.2.6.2 Leybold ) consist of : |  |  |  |  | R.1.IV.2.1.2.1 |
| Fiber Optic Adapter | Equiv. 736401 Leybold | 1 | 637.08 | 637.08 | R.1.IV.2.1.2.2 |
| Fiber Micropositioner | Equiv. 736415 Leybold | 1 | 536.25 | 536.25 | R.1.IV.2.1.2.3 |
| Mode Scrambler | Equiv. 736416 Leybold | 1 | 31.25 | 31.25 | R.1.IV.2.1.2.4 |
| Set of FSMA Optical Fibers | Equiv. 736425 Leybold | 1 | 435.00 | 435.00 | R.1.IV.2.1.2.5 |
| Hand-Held Power Meter, Optical | Equiv. 736435 Leybold | 1 | 473.33 | 473.33 | R.1.IV.2.1.2.6 |
| Fiber-Optic Microscope | Equiv. 736429 Leybold | 1 | 118.33 | 118.33 | R.1.IV.2.1.2.7 |
| Accessories : |  |  |  |  | R.1.IV.2.1.2.8 |
| c. Panel Frame | Equiv. 726063 Leybold | 1 | 157.92 | 157.92 | R.1.IV.2.1.2.9 |
| d. Connecting Lead 25 cm Black | Equiv. 500414 Leybold | 1 | 2.58 | 2.58 | R.1.IV.2.1.2.10 |
| e. Connecting Lead 200 cm Black | Equiv. 500454 Leybold | 4 | 3.00 | 12.00 | R.1.IV.2.1.2.11 |
| h. Set 10 Bridging Plugs Black | Equiv. 501511 Leybold | 2 | 17.13 | 34.26 | R.1.IV.2.1.2.12 |
| Digital Multimeter C. A. 5220 | Equiv. 53117 Leybold | 2 | 116.67 | 233.34 | R.1.IV.2.1.2.13 |
| Probe 100 MHz 1:1/10:1 | Equiv. 578231 Leybold | 2 | 27.50 | 55.00 | R.1.IV.2.1.2.14 |
| Screened Cable BNC / 4mm Plug | Equiv. 57524 Leybold | 2 | 15.00 | 30.00 | R.1.IV.2.1.2.15 |
| Adapter BNC / 4 mm Socket, 2 pole | Equiv. 57535 Leybold | 1 | 9.58 | 9.58 | R.1.IV.2.1.2.16 |
| BNC Cable L = 2 m | Equiv. 501022 Leybold | 1 | 16.29 | 16.29 | R.1.IV.2.1.2.17 |
| Plug-In Power Supply 230 V, 20 W | Equiv. 562791 Leybold | 2 | 30.42 | 60.84 | R.1.IV.2.1.2.18 |
| DC -PowerSupply 15V / 3 A | Equiv. 72886 Leybold | 1 | 404.58 | 404.58 | R.1.IV.2.1.2.19 |
| Manual : Basic Experiments In FO Comm. Eng. | Equiv. 564482 Leybold | 1 | 40.83 | 40.83 | R.1.IV.2.1.2.20 |
| Manual : Data Trans. With FO Waveguides | Equiv. 564492 Leybold | 1 | 43.75 | 43.75 | R.1.IV.2.1.2.21 |
| Microwave Technology |  |  |  |  | R.1.IV.2.1.3 |
| (Equiv. MTS 7.4.1 Leybold) Consist of: |  |  |  |  | R.1.IV.2.1.3.1 |
| Gunn Oscillator | Equiv. 73701 Leybold | 1 | 560.83 | 560.83 | R.1.IV.2.1.3.2 |
| Gunn Power Supply with SWR Meter | Equiv. 737021 Leybold | 1 | 1,445.42 | 1,445.42 | R.1.IV.2.1.3.3 |
| Large Horn Antenna | Equiv. 73721 Leybold | 1 | 112.50 | 112.50 | R.1.IV.2.1.3.4 |
| Physics Microwave Accessories I | Equiv. 73727 Leybold | 1 | 201.25 | 201.25 | R.1.IV.2.1.3.5 |
| E - Field Probe | Equiv. 73735 Leybold | 1 | 287.92 | 287.92 | R.1.IV.2.1.3.6 |
| Parallel Plate Line | Equiv. 73707 Leybold | 1 | 909.17 | 909.17 | R.1.IV.2.1.3.7 |
| Measuring Carriage for Parallel Plate Line | Equiv. 737071 Leybold | 1 | 639.58 | 639.58 | R.1.IV.2.1.3.8 |
| Parallel Plate Accessories Line | Equiv. 73728 Leybold | 1 | 458.33 | 458.33 | R.1.IV.2.1.3.9 |
| Coax Detector | Equiv. 73703 Leybold | 1 | 419.17 | 419.17 | R.1.IV.2.1.3.10 |
| Transition Waveguide/Coax | Equiv. 737035 Leybold | 1 | 424.58 | 424.58 | R.1.IV.2.1.3.11 |
| Variable attenuator | Equiv. 73709 Leybold | 1 | 585.00 | 585.00 | R.1.IV.2.1.3.12 |
| Fixed Attenuator | Equiv. 737095 Leybold | 1 | 174.17 | 174.17 | R.1.IV.2.1.3.13 |
| Moveable Short | Equiv. 73710 Leybold | 1 | 546.25 | 546.25 | R.1.IV.2.1.3.14 |
| Slotted Measuring Line | Equiv. 737111 Leybold | 1 | 645.42 | 645.42 | R.1.IV.2.1.3.15 |
| Waveguide 200 mm | Equiv. 73714 Leybold | 1 | 126.67 | 126.67 | R.1.IV.2.1.3.16 |
| 3-Screw Transformer | Equiv. 737135 Leybold | 1 | 254.17 | 254.17 | R.1.IV.2.1.3.17 |
| Waveguide Terminatin | Equiv. 73714 Leybold | 2 | 219.58 | 439.17 | R.1.IV.2.1.3.18 |
| Cross Directional Coupler | Equiv. 73718 Leybold | 1 | 390.00 | 390.00 | R.1.IV.2.1.3.19 |
| Set of 4 Diaphragms with Slits And Holder | Equiv. 73722 Leybold | 1 | 93.75 | 93.75 | R.1.IV.2.1.3.20 |
| Waveguide Propagation Accessories | Equiv. 73729 Leybold | 1 | 224.58 | 224.58 | R.1.IV.2.1.3.21 |
| Set of 10 Thumb Screw M4 | Equiv. 737399 Leybold | 1 | 14.17 | 14.17 | R.1.IV.2.1.3.22 |
| Pin Modulator | Equiv. 73705 Leybold | 1 | 455.83 | 455.83 | R.1.IV.2.1.3.23 |
| Isolator | Equiv. 73706 Leybold | 1 | 365.83 | 365.83 | R.1.IV.2.1.3.24 |
| Slide Screw Transformer | Equiv. 73713 Leybold | 1 | 780.00 | 780.00 | R.1.IV.2.1.3.25 |
| E - Field Probe | Equiv. 73735 Leybold | 1 | 287.92 | 287.92 | R.1.IV.2.1.3.26 |
| Pin Modulator | Equiv. 73705 Leybold | 1 | 455.83 | 455.83 | R.1.IV.2.1.3.27 |
| Isolator | Equiv. 73706 Leybold | 1 | 365.83 | 365.83 | R.1.IV.2.1.3.28 |
| Circulator | Equiv. 737065 Leybold | 1 | 373.75 | 373.75 | R.1.IV.2.1.3.29 |
| Waveguide Detector | Equiv. 73708 Leybold | 1 | 497.92 | 497.92 | R.1.IV.2.1.3.30 |
| Waveguide 200 mm | Equiv. 73712 Leybold | 1 | 126.67 | 126.67 | R.1.IV.2.1.3.31 |
| Waveguide termination | Equiv. 73714 Leybold | 1 | 219.58 | 219.58 | R.1.IV.2.1.3.32 |
| Phase Shifter | Equiv. 73717 Leybold | 1 | 633.75 | 633.75 | R.1.IV.2.1.3.33 |
| Magic T | Equiv. 737195 Leybold | 1 | 358.75 | 358.75 | R.1.IV.2.1.3.34 |
| Gunn Oscillator | Equiv. 73701 Leybold | 1 | 560.83 | 560.83 | R.1.IV.2.1.3.35 |
| Dielectric Tunning Unit | Equiv. 737015 Leybold | 1 | 132.08 | 132.08 | R.1.IV.2.1.3.36 |
| Varactor Tuning Unit | Equiv. 737017 Leybold | 1 | 482.50 | 482.50 | R.1.IV.2.1.3.37 |
| Gunn Power Supply with Modulator Control | Equiv. 737025 Leybold | 1 | 1,034.17 | 1,034.17 | R.1.IV.2.1.3.38 |
| Frequency Meter | Equiv. 73716 Leybold | 1 | 780.00 | 780.00 | R.1.IV.2.1.3.39 |
| Large Horn Antenna | Equiv. 73721 Leybold | 2 | 112.50 | 225.00 | R.1.IV.2.1.3.40 |
| Accessories : |  |  |  |  | R.1.IV.2.1.3.41 |
| a. Dig. Storage Oscilloscope | Equiv. 575293 Leybold | 1 | 800.00 | 800.00 | R.1.IV.2.1.3.42 |
| b. BNC Cable L = 1 m | Equiv. 501022 Leybold | 1 | 16.29 | 16.29 | R.1.IV.2.1.3.43 |
| c. BNC Cable L = 2 m | Equiv. 501022 Leybold | 6 | 16.29 | 97.74 | R.1.IV.2.1.3.44 |
| d. BNC T Adapter | Equiv. 501091 Leybold | 1 | 11.46 | 11.46 | R.1.IV.2.1.3.45 |
| e. Stand Base MF | Equiv. 30121 Leybold | 3 | 16.67 | 50.01 | R.1.IV.2.1.3.46 |
| f. Stand Rod L = 25 cm D = 10 mm | Equiv. 30126 Leybold | 2 | 4.58 | 9.16 | R.1.IV.2.1.3.47 |
| g. Support for Waveguide Components | Equiv. 73715 Leybold | 3 | 52.08 | 156.24 | R.1.IV.2.1.3.48 |
| h. 3HU Softcase 63PU 220V | Equiv. 72644 Leybold | 1 | 221.67 | 221.67 | R.1.IV.2.1.3.49 |
| Manual : Phy. Fund. of Micr. Technology I | Equiv. 568722 Leybold | 1 | 36.67 | 36.67 | R.1.IV.2.1.3.50 |
| Manual : Phy. Fund. of Micr. Technology II | Equiv. 568662 Leybold | 1 | 49.58 | 49.58 | R.1.IV.2.1.3.51 |
| Manual : Ferrite Comp., Power Divid. & Active Comp. | Equiv. 568752 Leybold | 1 | 36.67 | 36.67 | R.1.IV.2.1.3.52 |
| Manual : Prop. of Microwave In Waveguides | Equiv. 568732 Leybold | 1 | 49.17 | 49.17 | R.1.IV.2.1.3.53 |
| Manual : Circuitry with Waveguide Component | Equiv. 568692 Leybold | 1 | 28.75 | 28.75 | R.1.IV.2.1.3.54 |
| Antenna Technology |  |  |  |  | R.1.IV.2.1.4 |
| (Equiv. MTS 7.6.1 Leybold) Consist of : |  |  |  |  | R.1.IV.2.1.4.1 |
| Rotating antenna Platform | Equiv. 737400 Leybold | 1 | 1,302.08 | 1,302.08 | R.1.IV.2.1.4.2 |
| Gunn Power Supply with SWR Meter | Equiv. 737021 Leybold | 1 | 1,445.42 | 1,445.42 | R.1.IV.2.1.4.3 |
| Gunn Oscillator | Equiv. 73701 Leybold | 1 | 560.83 | 560.83 | R.1.IV.2.1.4.4 |
| Large Horn Antenna | Equiv. 73721 Leybold | 1 | 112.50 | 112.50 | R.1.IV.2.1.4.5 |
| Support for Waveguide Components | Equiv. 73721 Leybold | 2 | 52.08 | 104.17 | R.1.IV.2.1.4.6 |
| Stand Base MF | Equiv. 30121 Leybold | 2 | 16.67 | 33.33 | R.1.IV.2.1.4.7 |
| BNC Cable L = 1 m | Equiv. 50102 Leybold | 2 | 16.29 | 32.58 | R.1.IV.2.1.4.8 |
| Set of Microwave Absorbers | Equiv. 737390 Leybold | 1 | 424.17 | 424.17 | R.1.IV.2.1.4.9 |
| Set of 10 Thumb Screws M4 | Equiv. 737399 Leybold | 1 | 14.17 | 14.17 | R.1.IV.2.1.4.10 |
| Pin Modulator | Equiv. 73705 Leybold | 1 | 455.83 | 455.83 | R.1.IV.2.1.4.11 |
| Isolator | Equiv. 73706 Leybold | 1 | 365.83 | 365.83 | R.1.IV.2.1.4.12 |
| Disk : Directional Patterns | Equiv. 524782 Leybold | 1 | 120.42 | 120.42 | R.1.IV.2.1.4.13 |
| Cassypack-E | Equiv. 524007 Leybold | 1 | 825.00 | 825.00 | R.1.IV.2.1.4.14 |
| Screened cable BNC 4 mm Plug | Equiv. 57524 Leybold | 1 | 15.00 | 15.00 | R.1.IV.2.1.4.15 |
| Matrix printer 24 Needle | Equiv. 728062 Leybold | 1 | 475.83 | 475.83 | R.1.IV.2.1.4.16 |
| PC Printer Cable | Equiv. 728069 Leybold | 1 | 22.50 | 22.50 | R.1.IV.2.1.4.17 |
| Case for Antenna Technology | Equiv. 737382 Leybold | 1 | 308.75 | 308.75 | R.1.IV.2.1.4.18 |
| Personal Computer(Branded) | 1. Intel Pentium IV 1.7 GHz (Branded) | 1 | 1,100.00 | 1,100.00 | R.1.IV.2.1.4.19 |
| Remote Control for rotating Antenna Platform | Equiv. 737401 Leybold | 1 | 259.17 | 259.17 | R.1.IV.2.1.4.20 |
| Dipole Antenna Kit | Equiv. 737411 Leybold | 1 | 492.50 | 492.50 | R.1.IV.2.1.4.21 |
| Yagi Antenna Kit | Equiv. 737431 Leybold | 1 | 67.92 | 67.92 | R.1.IV.2.1.4.22 |
| Large Horn Antenna | Equiv. 73721 Leybold | 1 | 112.50 | 112.50 | R.1.IV.2.1.4.23 |
| Small Horn Antenna | Equiv. 73720 Leybold | 1 | 112.92 | 112.92 | R.1.IV.2.1.4.24 |
| Waveguide 200 mm | Equiv. 73712 Leybold | 1 | 126.67 | 126.67 | R.1.IV.2.1.4.25 |
| Coax Detector | Equiv. 73703 Leybold | 1 | 419.17 | 419.17 | R.1.IV.2.1.4.26 |
| Transition Waveguide/Coax | Equiv. 737035 Leybold | 1 | 424.58 | 424.58 | R.1.IV.2.1.4.27 |
| 3-Screw Transformer | Equiv. 737135 Leybold | 1 | 254.17 | 254.17 | R.1.IV.2.1.4.28 |
| Reflector for Diaphragms with Slit | Equiv. 737420 Leybold | 1 | 30.83 | 30.83 | R.1.IV.2.1.4.29 |
| Physics Microwave Accessories I | Equiv. 73727 Leybold | 1 | 201.25 | 201.25 | R.1.IV.2.1.4.30 |
| Support for Waveguide Components | Equiv. 73715 Leybold | 2 | 52.08 | 104.17 | R.1.IV.2.1.4.31 |
| Stand Base MF | Equiv. 30121 Leybold | 3 | 16.67 | 50.00 | R.1.IV.2.1.4.32 |
| BNC Cable L = 1 m | Equiv. 50102 Leybold | 1 | 16.29 | 16.29 | R.1.IV.2.1.4.33 |
| Helical Antenna Kit | Equiv. 737440 Leybold | 2 | 274.58 | 549.17 | R.1.IV.2.1.4.34 |
| E - Bend | Equiv. 737197 Leybold | 2 | 224.17 | 448.33 | R.1.IV.2.1.4.35 |
| Coax Transition Male/Female N, 50 Ohm | Equiv. 737033 Leybold | 2 | 19.17 | 38.33 | R.1.IV.2.1.4.36 |
| Variable attenuator | Equiv. 73709 Leybold | 2 | 585.00 | 1,170.00 | R.1.IV.2.1.4.37 |
| Steel Tape Measure L = 2M/78" | Equiv. 31177 Leybold | 1 | 5.63 | 5.63 | R.1.IV.2.1.4.38 |
| Dish antenna Kit | Equiv. 737450 Leybold | 1 | 274.17 | 274.17 | R.1.IV.2.1.4.39 |
| Slot Antenna | Equiv. 737424 Leybold. | 1 | 317.50 | 317.50 | R.1.IV.2.1.4.40 |
| Strip-Line Antenna | Equiv. 737427 Leybold | 2 | 317.50 | 635.00 | R.1.IV.2.1.4.41 |
| Waveguide termination | Equiv. 73714 Leybold | 1 | 219.58 | 219.58 | R.1.IV.2.1.4.42 |
| Moveable short | Equiv. 73710 Leybold | 1 | 546.25 | 546.25 | R.1.IV.2.1.4.43 |
| Stand Rod L = 25 cm D = 10 mm | Equiv. 30126 Leybold | 1 | 4.58 | 4.58 | R.1.IV.2.1.4.44 |
| Frequency Meter | Equiv. 73716 Leybold | 1 | 780.00 | 780.00 | R.1.IV.2.1.4.45 |
| Coax Detector | Equiv. 73703 Leybold | 1 | 419.17 | 419.17 | R.1.IV.2.1.4.46 |
| Transition Waveguide/Coax | Equiv. 737035 Leybold | 1 | 424.58 | 424.58 | R.1.IV.2.1.4.47 |
| Variable Attenuator | Equiv. 73709 Leybold | 1 | 585.00 | 585.00 | R.1.IV.2.1.4.48 |
| 3-Screw Transformer | Equiv. 737135 Leybold | 1 | 254.17 | 254.17 | R.1.IV.2.1.4.49 |
| Waveguide Termination | Equiv. 73714 Leybold | 1 | 219.58 | 219.58 | R.1.IV.2.1.4.50 |
| Cross Directional Coupler | Equiv. 73718 Leybold | 1 | 390.00 | 390.00 | R.1.IV.2.1.4.51 |
| Waveguides 200 mm | Equiv. 73712 Leybold | 1 | 126.67 | 126.67 | R.1.IV.2.1.4.52 |
| Support for Waveguide Components | Equiv. 73712 Leybold | 2 | 52.08 | 104.17 | R.1.IV.2.1.4.53 |
| Set of 4 Diaphragms with Slits And Holder | Equiv. 73722 Leybold | 1 | 93.75 | 93.75 | R.1.IV.2.1.4.54 |
| Reflector for Diaphragms with Slit | Equiv. 737420 Leybold | 1 | 30.83 | 30.83 | R.1.IV.2.1.4.55 |
| Stand Base MF | Equiv. 30121 Leybold | 2 | 16.67 | 33.33 | R.1.IV.2.1.4.56 |
| BNC Cable L = 1 m | Equiv. 50102 Leybold | 2 | 16.29 | 32.58 | R.1.IV.2.1.4.57 |
| Manual : Student Exp. In Antenna Tech. | Equiv. 568712 Leybold | 1 | 49.58 | 49.58 | R.1.IV.2.1.4.58 |
| Manual : Antenna Technology | Equiv. 568702 Leybold | 1 | 143.75 | 143.75 | R.1.IV.2.1.4.59 |
| Personal Computer | 1. Intel Pentium IV 1.7 GHz | 1 | 550.00 | 550.00 | R.1.IV.2.1.4.60 |
| Digital Oscilloscope | DC to 100MHz, 2 CH, 500MHz | 2 | 1,575.00 | 3,150.00 | R.1.III.3.1 |
| 8031 Kit |  | 5 | 525.00 | 2,625.00 | R.1.III.3.2 |
| Experimental Kit: |  |  |  |  | R.1.III.3.3.1 |
| a. LabVIEW Full Development for Windows |  | 1 | 2,045.70 | 2,045.70 | R.1.III.3.3.2 |
| b. WebDAQ built in web server |  | 1 | 1,200.00 | 1,200.00 | R.1.III.3.3.3 |
| c. PCI-488 controller |  | 1 | 600.00 | 600.00 | R.1.III.3.3.4 |
| d. Fast & continues data acquisition (ADC) |  | 2 | 1,000.00 | 2,000.00 | R.1.III.3.3.5 |
| e. DAC 12 bit |  | 2 | 400.00 | 800.00 | R.1.III.3.3.6 |
| f. GPIB Board |  | 1 | 750.00 | 750.00 | R.1.III.3.3.7 |
| Servo motor Kit |  | 2 | 2,100.00 | 4,200.00 | R.1.III.3.4 |
| Differential Relay (Percentage/2 Winding) | Type MBCH 12 / MRD1-T2 | 1 | 4,410.00 | 4,410.00 | R.1.IV.8.1 |
| Power Source | 110 Vdc 20 A | 1 | 157.50 | 157.50 | R.1.IV.8.2 |
| 1. Real Time Mesurements of Wireless |  | 1 | 5,541.17 | 5,541.17 | R.3.1.1.1 |
| (Equiv. TOM Package) Completed with |  |  |  |  | R.3.1.1.2 |
| Software for Analyzing Measurements |  |  |  |  | R.3.1.1.3 |
| Equiv. SAM Version 3:0) Consist of: |  |  |  |  | R.3.1.1.4 |
| a. Personal Computer | With Windows® 95/98/NT® Operating System |  |  |  | R.3.1.1.5 |
|  | Pentium III Processor, Minimum of 500 MHz |  |  |  | R.3.1.1.6 |
|  | 128 MB RAM Minimum |  |  |  | R.3.1.1.7 |
|  | 40 GB of Free Hard Disk Space for Installation, |  |  |  | R.3.1.1.8 |
|  | 100 MB Recommended, with Speed at 7000 rpm |  |  |  | R.3.1.1.9 |
|  | SVGA Display, XGA Recommended |  |  |  | R.3.1.1.10 |
|  | Parallel Port for Copy Protection Module |  |  |  | R.3.1.1.11 |
|  | Two RS 232 Serial Ports |  |  |  | R.3.1.1.12 |
| b. TOM Compliant |  |  |  |  | R.3.1.1.13 |
| Equiv. Nokia Mobile Telephone |  |  |  |  | R.3.1.1.14 |
| c. Multi DMAC Unit Called MUD |  |  |  |  | R.3.1.1.15 |
| d. PCMCIA Adapter Card |  |  |  |  | R.3.1.1.16 |
| e. GPS Receiver | (Centennial PCMCIA Satriav (NMEA 0183) |  |  |  | R.3.1.1.17 |
|  | and GPS Antenna Unit) or Garmin GPS II / |  |  |  | R.3.1.1.18 |
|  | Garmin GPS II Plus/ Garmin GPS III /III Plus/ |  |  |  | R.3.1.1.19 |
|  | Garmin GPS 35/(Rockwell NavCard LP PCMCIA |  |  |  | R.3.1.1.20 |
|  | (NMEA 0183) and GP anlenna Unit / Trimble |  |  |  | R.3.1.1.21 |
|  | Placer 450/455(TAIP) and GPS antenna Unit)/ |  |  |  | R.3.1.1.22 |
|  | (Trimble Scout Master(NMEA m0183) nd GPS |  |  |  | R.3.1.1.23 |
|  | antenna Unit)/(Most Other GPS Receivers with |  |  |  | R.3.1.1.24 |
|  | NMEA 0183 Compatible Output) |  |  |  | R.3.1.1.25 |
| f. Fast Frequency Scanner | GSM 900 Scanner (Channels:1-124) |  |  |  | R.3.1.1.26 |
|  | GSM 1800 Scanner (Channels:512-885) |  |  |  | R.3.1.1.27 |
|  | GSM 900/1800 Scanner (Channels 1-124,512-885) |  |  |  | R.3.1.1.28 |
|  | PCS 1900 Scanner (Channels 512-810) |  |  |  | R.3.1.1.29 |
| g. Software for Analyzing Measurements | PC with a Pentium III Processor, 500MHz |  |  |  | R.3.1.1.30 |
| Equiv. SAM Version 3:0) | SVGA Display (Monitor) |  |  |  | R.3.1.1.31 |
|  | 128 MB of RAM (256 MB recommended) |  |  |  | R.3.1.1.32 |
|  | 20 GB Hard disk Drive Recommended |  |  |  | R.3.1.1.33 |
|  | CD-ROM Drive for Installation |  |  |  | R.3.1.1.34 |
|  | Microsoft® Windows® 95, Windows® 98 |  |  |  | R.3.1.1.35 |
|  | or Windows NT® 3.51 or Higher |  |  |  | R.3.1.1.36 |
|  | Microsoft® Excel Installation |  |  |  | R.3.1.1.37 |
| 2. Cellular Network Planning Based PC |  | 1 | 3,000.00 | 3,000.00 | R.3.1.2.1 |
| Consist of : |  |  |  |  | R.3.1.2.2 |
| a. IBM PC - Caompatible Computer | A windows NT® Operating System |  |  |  | R.3.1.2.3 |
|  | PC with a Pentium III Processor, 500MHz |  |  |  | R.3.1.2.4 |
|  | SVGA Display (Monitor) |  |  |  | R.3.1.2.5 |
|  | 128 MB of RAM (256 MB recommended) |  |  |  | R.3.1.2.6 |
|  | 40 GB Hardisk of RAM (256 MB Recommended) |  |  |  | R.3.1.2.7 |
|  | CD-ROM Drive for Installation |  |  |  | R.3.1.2.8 |
| b. Software of Cellular Network Planning | Equiv. Nokia Network Planning System NPS/X tools) |  |  |  | R.3.1.2.9 |
| c. Map of Macassar City and Surrounding | Size 20 KM by 25 Km Installed to PC |  |  |  | R.3.1.2.10 |
| Regency wiyh the area |  |  |  |  | R.3.1.2.11 |
| 3. DS-SS CDMA Training System II | Equiv. ED - 2940 | 1 | 11,213.00 | 11,213.00 | R.3.1.3 |
| 4. 3HU Sweep Function Generator 2 MHz | Equiv. 725501 Leybold | 1 | 1,475.83 | 1,475.83 | R.3.1.4 |
|  | TOTAL |  | $ | 85,931.10 |  |

Appendix – 8

| Detailed Specifications : Program Development - year 3 |  |  |  |
| --- | --- | --- | --- |
| Name of Program | Quantity | Unit Cost | Total |
| R.2.1. Apprenticeship Programs in Industry | 1 month, 17 persons | 542,986.43 | 9,230,769.24 |
| R.2.2 .Workshop on Curriculum Development with Industrial Participation | 4 days, 25 persons | 131,538.47 | 13,153,846.50 |
| R.2.3. Industrial Training and Studies Programs Development | 9 days | 370,370.37 | 3,333,333.33 |
| R.4.1 Students’ English Technical Writing and Conversational Skills Development | 5 days, 20 persons | 20,857.14 | 2,085,714.29 |
| R.4.2.Students’ Computer and Internet Skills Development | 12 days | 833,333.33 | 10,000,000.00 |
| R.4.4.Students’ Personality and Entrepreneurship Development | 9 days | 759,682.54 | 6,837,142.86 |
| A.2 5.Learning Skills Training Program | 2 days, 40 persons | 125,000.00 | 10,000,000.00 |
| E.1.2/E.1.3.Teaching Improvement Workshops | 2 days, 40 persons | 125,000.00 | 7,649,193.78 |
|  |  | Total Cost: | 62,290,000.00 |

Appendix – 9

| Detailed Specifications : Instructional Materials ( year 3 ) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Type of Instructional | Technical/bidding | Qty | Unit | Utilities | Estimated | Remark |
| Materials | specification |  | Cost |  | Cost |  |
|  | C++ for Programmer,2/e | 2 | 42.95 |  | 85.90 |  |
|  | C++ Effective Object -Oriented Software Constructions | 2 | 49.99 |  | 99.98 |  |
|  | Building Electronic Commerce With Web-Driven Database | 2 | 85 |  | 170.00 |  |
|  | Communications Technologies | 2 | 46.67 |  | 93.34 |  |
|  | Data Base Systems Using Oracle : A Simplified to SQL and PL/SQL | 2 | 53.27 |  | 106.54 |  |
|  | Developing Distributed and E-Commerce Applications | 2 | 50.99 |  | 101.98 |  |
|  | Distributed Database Systems | 2 | 48.99 |  | 97.98 |  |
|  | Electronic Commerce | 2 | 60 |  | 120.00 |  |
|  | Internetworking with TCP/IP Vol.III | 2 | 68 |  | 136.00 |  |
|  | Linux Firewalls, 2/e | 2 | 44.99 |  | 89.98 |  |
|  | Linux TCP/IP Network Administration | 2 | 44.99 |  | 89.98 |  |
|  | Local and Metropolitan Area Networks 6/e | 2 | 82 |  | 164.00 |  |
|  | MySQL Building User Interface | 2 | 49.99 |  | 99.98 |  |
|  | TCP/IP 2/e | 2 | 56.5 |  | 113.00 |  |
|  | Data Structures in C++ | 2 | 80 |  | 160.00 |  |
|  | Data Structures in Java | 3 | 73 |  | 219.00 |  |
|  | E-Commerce : Business, Techlogy, Society | 2 | 82.67 |  | 165.34 |  |
|  | IBM PC Assembly Language and Programming 5/e | 2 | 73 |  | 146.00 |  |
|  | Multimedia lnformation Networking | 2 | 106 |  | 212.00 |  |
|  | Telecommunications for Managers 5/e | 2 | 104 |  | 208.00 |  |
|  | The Linus A - Z | 5 | 42.99 |  | 214.95 |  |
|  | The Object Of Java | 2 | 68 |  | 136.00 |  |
|  | Structured C for Engineeringand Technology 4/e | 2 | 85 |  | 170.00 |  |
|  | Synergy Hardware Software | 2 | 37.95 |  | 75.90 |  |
|  | System Analysis and Design 5/e | 2 | 90.67 |  | 181.34 |  |
|  | The Art of Electronics | 2 | 70 |  | 140.00 |  |
|  | The Essential Guide to Telecommunications | 3 | 27.99 |  | 83.97 |  |
|  | Security Analysis | 2 | 40 |  | 80.00 |  |
|  | Physics for Scientists and Engineers : Volume II Electricity | 2 | 48.95 |  | 97.90 |  |
|  | magnetism and Light |  |  |  | 0.00 |  |
|  | Basic Electric Circuit Analysis: Student Problem Set With Solutions | 2 | 31.75 |  | 63.50 |  |
|  | Powering the Future: The Ballard Fuel Cell and The race to changes | 2 | 17.95 |  | 35.90 |  |
|  | the world |  |  |  | 0.00 |  |
|  | The Electrical Power Engineering Handbook | 2 | 103.96 |  | 207.92 |  |
|  | Field and Wave Electromagnetics | 2 | 102 |  | 204.00 |  |
|  | Teach Yourself Electricity and Electronics | 2 | 27.96 |  | 55.92 |  |
|  | Fiber Optics Technician's Manual | 2 | 46.95 |  | 93.90 |  |
|  | Basic Electronic | 2 | 76.5 |  | 153.00 |  |
|  | Protective Relaying : Principles and Applications | 2 | 59.75 |  | 119.50 |  |
|  | Small Electric Motors : Use,Selection,Operation,Repair, and | 2 | 24 |  | 48.00 |  |
|  | Maintenance |  |  |  |  |  |
|  | Introduction Fiber Otics | 3 | 32.95 |  | 98.85 |  |
|  | Switch Engineering Handbook | 2 | 64.5 |  | 129.00 |  |
|  | Power Generation Handbook | 2 | 99.95 |  | 199.90 |  |
|  | Antenna Theory : Analysis and Design | 2 | 111.75 |  | 223.50 |  |
|  | Protective Relaying Theory and Applications | 2 | 99.75 |  | 199.50 |  |
|  | Data Communications 3/e : From Basic to Broadband | 2 | 55 |  | 110.00 |  |
|  | Data Communications for Engineers | 2 | 44.99 |  | 89.98 |  |
|  | Data Communications Computer Networks And Open System4/e | 2 | 44.95 |  | 89.90 |  |
|  | Multimedia Communications : Applications Networks, Protocol | 2 | 50.99 |  | 101.98 |  |
|  | and Standard |  |  |  |  |  |
|  | MySQL and Perl for the Web | 2 | 44.99 |  | 89.98 |  |
|  | Fundementals of Convolutional Coding | 2 | 72.95 |  | 145.90 |  |
|  | Electricity and Electronics Interactve Software Site License | 2 | 300 |  | 600.00 |  |
|  | Industrial and Commersial Power System Handbook | 2 | 69.65 |  | 139.30 |  |
|  | The Electric Power Engineering Handbook | 2 | 139.95 |  | 279.90 |  |
|  | Power Quality Solutions : Case Studies for Troubleshooters | 2 | 82 |  | 164.00 |  |
|  | Power System Stability and Control | 2 | 95 |  | 190.00 |  |
|  | Energy efficient Transformers | 2 | 59.95 |  | 119.90 |  |
|  | Analysis of Multiconductor Transmissions Line | 2 | 149.5 |  | 299.00 |  |
|  | Digital Modulation techniques | 3 | 102 |  | 306.00 |  |
|  | Geographic Information System : A Management Perspective | 2 | 48.95 |  | 97.90 |  |
|  | Computer Processing of Remotely Sensed Images | 2 | 59.95 |  | 119.90 |  |
|  | Remote Sensing Digital Image Analysis : An Introduction | 2 | 43.95 |  | 87.90 |  |
|  | Geographic Information System : An Introduction | 2 | 49.95 |  | 99.90 |  |
|  | Remote sensing : The Quantitative Approach | 2 | 35.45 |  | 70.90 |  |
|  | Digital Signa Processing : Principle, Algorithm and Application | 2 | 102.95 |  | 205.90 |  |
|  | Signal and Linier System | 2 | 92 |  | 184.00 |  |
|  | Signal and Noise in Communication System | 2 | 42.95 |  | 85.90 |  |
|  | Voice and Speech Processing | 2 | 36.95 |  | 73.90 |  |
|  | Numerical Methods for Computer Science, Engineering and | 2 | 36.5 |  | 73.00 |  |
|  | mathematics |  |  |  |  |  |
| Journal | IEEE Power Engineering, etc | 1 | 250.00 |  | 250.00 |  |
| Journal | IEEE Telecommunication Engineering, etc | 1 | 250.00 |  | 250.00 |  |
| Journal | IEEE Control Engineering, etc | 1 | 250.00 |  | 250.00 |  |
|  | Total Cost: |  |  |  | 10,266.49 |  |

| Appendix-10 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Detailed Specifications : Consultants Services - Internasional ( year 3 ) |  |  |  |  |
| Qualification | Major Assignment | Estimated length of visit ( month ) | Estimated Cost | Major field |
| N/A |  |  |  |  |

| Appendix - 11 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Detailed Specifications : Consultants Services - Domestic ( year 1 to year 4 ) |  |  |  |  |
| Qualification | Major Assignment | Estimated length of visit ( month ) | Estimated Cost | Major field |
| N/A |  |  |  |  |

Appendix – 12

| Detailed Specifications : Project Management - Operational Support – year 3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activities | Purpose | Scope | Quantity | Unit Cost | Estimated Cost |
| Telephone (LS) |  |  | 12 | 1,000,000.00 | 12,000,000.00 |
| Couries Services (LS) |  |  | 1 | 2,000,000.00 | 2,000,000.00 |
| Regular Meetings (LS) |  |  | 1 | 6,000,000.00 | 6,000,000.00 |
| Tender committee (LS) |  |  | 1 | 6,000,000.00 | 6,000,000.00 |
| Copy and Printing (LS) |  |  | 1 | 4,000,000.00 | 4,000,000.00 |
|  |  |  |  | Total Cost: | 30,000,000.00 |

Appendix - 13

| Detailed Specifications : Project Management - O & M of Facilities - year 3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Program/Activities | Purpose | Description/Scope | Quantity | Unit Cost | Estimated Cost |
| Laboratory | Consumable Requirement | Precurement of | 1 | 19,938,904.50 | 19,938,904.50 |
|  |  | consumable material |  | 0.00 | 0.00 |
|  |  | for 4 years |  | 0.00 | 0.00 |
| Administration Support Operational & Maintenance | For Office and Laboratories | O & M laboratory, | 1 | 19,039,212.00 | 19,039,212.00 |
|  | activities to support operational | teaching and office equipment |  | 0.00 |  |
|  |  |  |  | Total Cost : | 38,978,116.50 |

Appendix - 14

| Detailed Specifications : Project Management - Sub-Project Management Unit Operation - year 3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Program/Activities | Number Person | Duration | Quantity | Unit Cost | Estimated Cost |
|  | Involved |  |  |  |  |
| Coordinator Project | 1 | 12 | 12 | 675,000.00 | 8,100,000.00 |
| Secretary project | 1 | 12 | 12 | 540,000.00 | 6,480,000.00 |
| Person in charge | 11 | 7 | 77 | 405,000.00 | 31,185,000.00 |
| Additional support staff | 4 | 10.5 | 42 | 135,000.00 | 5,670,000.00 |
| Consumables (LS) | 1 | 1 | 1 | 23,232,000.00 | 23,232,000.00 |
| Tender committee | 1 | 1 | 1 | 1,500,000.00 | 1,500,000.00 |
| expenses per-program |  |  |  | 0.00 |  |
| Travel allowance | 2 | 3 | 6 | 3,100,500.00 | 18,603,000.00 |
| ( per-trip) |  |  |  |  |  |
|  |  |  |  | Total Cost: | 94,770,000.00 |