Summary of SIP 2005 Revision

Electrical Engineering Study Program-Hasanuddin University

1. Study Program Organizational Structure:

We proposed to reshuffle the organizational structure of the project at the study program level. After meeting with all staffs in organizational structure which held on 07/01/2005 in study program, the forum recommend/propose that Dr.Ir.H. Rhiza S. Sadjad, MSEE as a recent project coordinator should be replaced by Ir.H.Tahir Ali (PIC of R.3 activity) and Person In charge of R.3 activity should be occupied by Dr.Ir.H.Rhiza S. Sadjad. The reshuffle the organizational structure is needed in order to solve our internal management problem. Mr.Rhiza realize that during the second year project term, performance of the study program in running the project has degraded because the SPMU Director could not maintain well coordination and communication with the study program level particularly with Mr.Rhiza as a project coordinator. Therefore, Mr.Rhiza request to resign from his position as a project coordinator and asking Mr.Tahir Ali to replaced him for the shake of the project. We and Mr.Rhiza believe that Mr.Tahir Ali could maintain well coordination and communication with SPMU level in order to keep the project run well.

2. Overseas Degree Training:

Appendix – 3

| Detailed Specifications : Staff Development - Overseas Degree training - year 3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name of Tentative | Field Of Study | Targeted University | Estimated Length | Estimated | Program |
| Candidates |  | to apply | of study(years) | Cost |  |
| Tadjuddin Waris | Electrical Power | Curtin University, Australia | 1.00 | 21000 | S3 |
| Dewiani * | Telecommunication | Curtin University, Australia | 1.00 | 21000 | S3 |
| Elyas Palantei | Telecommunication | Griffith University, Australia | 1.00 | 21000 | S3 |
| Samuel Panggalo | Telecommunication | Curtin University, Australia | 1.00 | 21000 | S3 |
| Hasniaty | Telecommunication | UTM, Malaysia | 1.00 | 13200 | S3 |
| Wardi | Telecommunication | University of South Australia, Australia | 1.00 | 21500 | S2 |
| 6 |  |  | Total Cost : | 118700 |  |

*) Since Miss Dewiani has failed to attend Ph.D program, we proposed to reallocate remain unused budget allocated for her to another activities such as Overseas Non-Degree Training.

Overseas Non-Degree Training:

| Detailed Specifications : Staff Development - Overseas non-Degree Training-year 3 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of Tentative | Field Of Study | Targeted University/Institution | Estimated Length | Estimated |
| Candidates |  | to apply | of study(days) | Cost |
| Muhammad Niswar | Telecommunication | International Conference, Hongkong | 3 | 1600 |
|  |  |  | Total Cost : | 1600 |

Since the international conference attended by Mr.Tola was not approved by CPMU, hence, we propose to reallocate the budget for him to another international conference in the third year project term.

3. Domestic Degree Training:

Appendix - 1

| Detailed Specifications : Staff Development - Domestic Degree Training - year 3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name of Tentative | Field Of Study | Targeted University | Estimated Length | Estimated | Program |
| Candidates |  | to apply | of study(years) | Cost |  |
| Indar K. Gunadin * | Electrical System | ITS | 1 | 19,800,000.00 | S2 |
| Yusran ** | Electrical System | UGM | 1 | 19,800,000.00 | S3 |
| Indra Bayu | Telecommunication | ITS | 1 | 19,900,000.00 | S2 |
|  |  |  | Total Cost : | 59,500,000.00 |  |

* awarded BPPS Scholarship, withdrawn TPSDP

** attending apprenticeship program in PT.INCO

Two domestic degree training for Ph.D and Master program (Mr.Yusran and Mr.Indar KG, respectively) are not implemented yet because both proposed candidate for attending this degree training have withdrawn from candidacy and until now we have not alternative candidate to replace them. Therefore, we proposed to reallocate the budget of two domestic degree training to another activity such as Domestic Non-Degree Training or Overseas Non-Degree Training.

4. Domestic Non-Degree Training:

Appendix – 2

| Detailed Specifications : Staff Development - Domestic Non - Degree Training-year 3 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of Tentative Lectures | Field Of Study | Targeted University/Institution to Apply | Estimated Length of Study (months) | Estimated Cost |
| Christoforus Y. | Computer Engineering | INIXINDO | 1 | 13,750,000.00 |
| M.Niswar | Computer Engineering | INIXINDO | 1 | 13,750,000.00 |
| Amil A.Ilham | Computer Engineering | INIXINDO | 1 | 13,750,000.00 |
| M.Tola | Electrical Power | UI | 1 | 7,700,000.00 |
| Nadjamuddin Harun | Control System | UGM | 1 | 7,700,000.00 |
|  |  |  | Total Cost : | 56,650,000.00 |

We request to increase the one month budget for three items of CISCO Training. This is because the tuition fee of this training is approximately Rp.7.450.000, of course, this amount is almost equal to total budget for one month training. Since this activity is part of R.3 activity and it has significant contribution to performance indicator of R.3 activity, therefore, we expect to get approval for this request.

R.2.3 Activity:

According to letter from CPMU (letter number: 107/TPSDP/PD/X/03), TOR of this activity has been approved, however, there is a mistake on written total budget in approved TOR.