# Chapter II  STRENGTHENING THE EXISTING STUDY PROGRAM

# ELECTRICAL ENGINEERING STUDY PROGRAM

Chapter 2.1  ELECTRICAL ENGINEERING STUDY PROGRAM

- BACKGROUND

After it moved to the new campus with all new facilities in 1985, the Electrical Engineering Study Program of Hasanuddin University, Makassar (occasionally in this Chapter is referred to as "the Study Program") stated its vision and mission as follows:

The Study Program’s VISION is to be the Center of Development and Implementation of the Electrical Engineering Technology and to become a leading engineering education institution in the country. Its MISSION is to graduate professionals who are able to advance their own technical skills and knowledge, and to adopt the development of technology.

The mission was carried out very well especially when a 10-year-long project called the Engineering Acceleration Project (Proyek Percepatan Insinyur, PPI) was launched in 1986. However; since the project ended in 1996, the Study Program has been constantly suffering from the quality degradation. The vision has become so blurring and the mission is so impossible; so only its long history, the high quality it used to have and the perseverance of all staffs that have helped maintaining the Study Program's performance up to a certain level. Without a careful rescue plan, the Self-Evaluation Report has shown that the performance will not last long in the future.

As has been concluded from the SWOT and Force-Field Analysis in Revised-Self Evaluation Report (SER) Chapter III.B.1. (see page III.B.1-1 to III.B.1-4 of the Revised Sub-Project Proposal), there are 3 (three) major obstacles - among others - that are supposed to be controllable factors of  improving the quality of the Study Program, i.e.:

- The obsolescence of the laboratory equipment and laboratory course materials for advance laboratory courses,

- Inadequate quantity of the laboratory equipment and laboratory course materials for basic laboratory courses, and

- The problem of teaching staff composition and qualification.

Those 3 (three) main issues above are the core of problems the Study Program is facing, and have been translated into strategic issues to develop several proposed activities (see Strategic Issues in Chapter III.B.2 Revised Inception Plan on page III.B.2-1 of the Revised Sub-Project Proposal) that will be detailed in the following Chapter 2.2. IMPROVING RAISE++ . The project was granted and the contract was finally signed at the end of October 2002.

At the end of the first year of the implementation of this project, not much has been accomplished that can be seen physically. As has been reported in the 2003 Annual Report, all activities are out of schedule. The fundamental reason is the late starting point. Even though the contract was signed at the end of October 2002, the Rector’s Decree concerning the organizational structure of the project was not signed until late March 2003. Therefore, the first 4 (four) months of the project term had been vacuum. The renovation of the Study Program’s office to accommodate the TPSDP activities was not completed until July 2003, which also contributed to the slow beginning of the project at the Study Program level. As the initial draft of the Annual Report was written, none of the 11 (eleven) Term of References (TORs) of Program Development and 1 (one) of the Staff Development planned for the Year 1 has been entirely approved. The approval of 4 (four) TORs finally arrived from the CPMU during the  site-visit. The PICs of all activities had difficulties in writing TORs for their Program Development because there has been no clear guidance from the SPMU level in writing those TORs. In fact, 4 (four) of submitted TORs were known missing on their way to the CPMU a month after submission, and should be re-submitted.

By the way, many aspects and progress of this project at the Study Program level is accessible via Internet by visiting its URL address:

http://www.unhas.ac.id/~tpsdp/elektro/.

- THE STRATEGY AND THE OBJECTIVES

All the staff's high motivation to work together is the primary asset the Study Program has. This has been shown by the staff's response to the announcement of this project (see Appendix III.2 on page III-Ap-3 of the Revised Sub-Project Proposal). At all socialization events mentioned, 90% of the staff were in attendance. Even in the very early stage of the Self-Evaluation Report preparation for the TPSDP Batch 1, the process has reflected the firm commitment to come together. This should be carried on to the next stage, i.e. the preparation of the Sub-Project Proposal of the TPSDP Batch 2 and - after the project is granted - to the implementation of the project. The main strategy is to harvest the participation of all components to produce a list of activities - not a "list of wants" or a "procurement list" - as early as possible. For instance, on the issues regarding the laboratories, each laboratory was asked to start by preparing the list of experiments for laboratory courses, then based on each experiment, a list of equipment required was developed (see Appendix II.H.I to IV on page II-Ap-11 to 20 of the Revised Sub-Project Proposal for details). No equipment procurement is supposed to be proposed by any laboratory without a proposed experiment for a laboratory course.

Figure II-1 shows the line of thought in preparing the Sub-Project Proposal. After a long series of discussions on the results of the self-evaluation process, including the discussions with the TPSDP reviewers during the site-visit and negotiations, the Study Program came up with 11 (eleven) proposed activities:

- To improve relevance: 5 (five) activities

- To improve academic atmosphere: 2 (two) activities

- To improve efficiency and productivity: 2 (two) activities

- To improve access and equity: 1 (one) activity

- To improve internal management and organization: 1 (one) activity

[Note: In the previous documents of this Sub-Project, one may notice that there used to be 4 (four) activities to improve relevance and 3 (three) activities to improve efficiency and productivity. After a long and intensive discussion, it was decided to change the main aspect of the activity of improving the staff qualification (activity E.3.) from improving the efficiency and productivity to improving the relevance].

C. PERFORMANCE INDICATORS

The general outcome of those eleven proposed activities will be quality improvements that are indicated by performance targets as shown in Table II-1. The increase of average NEM, for instance, is believed to be influenced mainly by improving access and equity as well as the quality enhancement as the consequences of the implementation of other activities. Hence, this indicator is omitted. The progress as of December 31 2003 is shown in the Table II-1.

Implementation Plan

R

A

I

S

E

+

+

Performance Targets

Proposed Budget

PROJECT BENEFIT

and ECONOMIC ANALYSIS

SE-REPORT

SWOT

Force-Field

Analysis

R.1.

R.2.

R.3.

R.4.

R.5.

A.1.

A.2.

E.1.

E.2.

AE

IMO

PROPOSED ACTIVITIES

STRATEGIC

ISSUES

Figure II-1 Line of Thought of the Preparation of the Sub-Project Proposal

Activities to improve efficiency and productivity will be directly and indirectly indicated by the increase of the graduates’ average GPA. These activities are also supposed to shorten the length of study as indicated by the average length of study. The average TOEFL scores, the graduates’ waiting time before getting the first job and the first job salary will indicate the improvement in relevance.

All proposed activities in this project are generally planned to boost most of the performance target indicators to yield a better result. Previously the performance targets were presented by the average values of the main indicators as suggested by the Guidelines. But, the incremental increase of the performance indicators have seemed “too modest” in comparison to the amount of capital invested in this project, and the average values may not really represent the actual condition. With a large student population, the presentation of the main indicators of the performance target in their frequency ranges or distribution – as presented in Table II-1 on page II-4 - will give a better perspective.

The average of NEM score's baseline data is 47.1 with standard of deviation 6.0. Improving the relevance (R) of the educational process to the job-market and industrial needs can increase the NEM scores of the admitted students. Naturally, when the relevance (R) is improving, the number of applicants to the Study Program will increase, resulting tougher competition at the new student admittance. A larger number of new students with high NEM scores will be admitted, and this will affect the academic atmosphere (A) at the Study Program. Another way of achieving this target is by creating some campaign programs about the Study Program to the High Schools at the surrounding area.

### Table II-1 Main Indicators for performance targets presented in their frequency ranges

| Indicator | Baseline | As 31/10/2003 | Midterm | Final |
| --- | --- | --- | --- | --- |
|  | % |  |  |  |
| # GPA |  |  |  |  |
| Percentage of graduates with GPA > 3.0 | 40.79 | 71.88 | 46.50 | 50.00 |
| Percentage of graduates with GPA between 2.5 and 3.0 | 56.35 | 23.83 | 52.50 | 49.50 |
| Percentage of graduates with GPA < 2.5 | 2.86 | 4.30 | 1.00 | 0.50 |
| TOEFL Score |  |  |  |  |
| Percentage of students with TOEFL score > 500 | 5.53 | # 6.49 | 16.60 | 37.80 |
| Percentage of students with TOEFL score between 400 and 500 | 38.13 | # 77.92 | 54.80 | 57.20 |
| Percentage of students with TOEFL score < 400 | 56.34 | 15.58 | 28.60 | 5.00 |
| LENGTH OF STUDY |  |  |  |  |
| Percentage of graduates with length of study > 5 years | 77.64 | 39.84 | 50.80 | 19.00 |
| Percentage of graduates with length of study between 4.5 and 5 years | 19.14 | 39.06 | 30.00 | 35.50 |
| Percentage of graduates with length of study < 4.5 years | 3.22 | 21.09 | 19.20 | 45.50 |
| WAITING TIME FOR THE FIRST JOB |  |  |  |  |
| Percentage of graduates who waited for their first jobs within 6 months | 13.60 | # N/A | 25.00 | 50.00 |
| Percentage of graduates who waited for their first jobs within 6 to 11 months | 51.20 | N/A | 45.00 | 40.00 |
| Percentage of graduates who waited for their first jobs for more than 11 months | 35.20 | N/A | 30.00 | 10.00 |
| FIRST JOB MONTHLY SALARY |  |  |  |  |
| Percentage of graduates whose first job monthly salary > Rp. 1.2 millions | 7.20 | # N/A | 45.00 | 70.00 |
| Percentage of graduates whose first job monthly salary between Rp. 0.6 and 1.2 millions | 50.40 | N/A | 35.00 | 20.00 |
| Percentage of graduates whose first job monthly salary < Rp. 0.6 millions | 42.40 | N/A | 20.00 | 10.00 |

The average of graduates' GPA taken from the last 4 (four) academic years is 2.94, distributed as shown in Table II-1. It is targeted to improve the distribution. This performance target indicates the improvement of the academic atmosphere (A) (e.g. by upgrading teaching facilities and classroom-facilities, developing lecturers' teaching skills and students' learning skills and creating competitiveness among students).

Encouraging students to read more reference books in English and urging lecturers to use English in their classes - among others - will help to improve students' English proficiency indicated by their TOEFL scores. This is a part of activities that will improve the relevance (R) of the Study Program. At the beginning of the project, the average of TOEFL scores of students whose credit earnings are 120 sks or more is 403, this is fairly high, considering that the students did not make any preparation due to the very short notice before the test. The distribution of the TOEFL scores is targeted to be improved by the implementation of a special program proposed as one of the student co-curricular activities (see Activity R.4.1).

The average graduates' length of study is 5.67 years at the beginning of the project. This can be shortened at the end of project, and the distribution is expected to be better, by improving the efficiency and productivity (E) of the educational process.  This target can be achieved by improving the teaching and learning process (see Activity E.1.) and to create more effective laboratory scheduling. In fact, the length of study has 2 (two) components, i.e. the classroom-courses study time and the final undergraduate project (skripsi) time. In order reduce the latter, the intensive interaction between supervisors and students should be enforced and the adequate laboratory equipment should be available. The baseline data of standard deviation can be reduced by continuous academic advisors' supervising on their students' study program planning and monitoring in order to detect the weak students. Special attention must be given to this kind of students to push them to study harder. Another factor that could influence the length of study time was the student academic leaves, which in most cases were caused by the lack of funding. Students' involvement in research and teaching grant activities are expected to be one of the possible remedies to reduce student academic leaves. An aggressive program to collect student scholarships (e.g. from alumni, industry, local and regional government) should be planned to help this problem out.

Survey and direct interviews have shown that the waiting time to get the first job is 11 months in average, which is a rather long time. This indicator is influenced heavily by the unemployment rate in the market, which is closely related to the country economic situation. Assuming a better economic growth, then additional efforts to improve the students' English proficiency and computer skills, as well as continuous adjustments of the curriculum toward industrial world orientation, will give the graduates a strong penetration to the job market.  This will automatically reduce the waiting time to the first job. It is expected that the waiting time to get the first job will be reduced and the distribution will look better also at the end of the project.

Table II-2.  Additional indicators for performance targets

| Indicator | Baseline | As 31/10/2003 | Midterm | Final |
| --- | --- | --- | --- | --- |
| Ratio between applicants and admissions | 9.3% | 7% | 9% | 8% |
| Average duration of completing skripsi | 9 months | 6 months | 8 months | 6 months |
| Average active students with GPA less than 2.5 | 4.8% | 0% | 4.6% | 4.3% |
| Average drop out students | 1.66% | 0.5% | 1.60% | 1.50% |
| Productivity (Graduates/Population) | 11.08% | 29% | 15.5% | 17% |
| Average teachers attendance at classroom | 85% | 93% | 87% | 90% |

The factors that have affected the graduates' first job salary, such as the national and local economic growth, were beyond the Study Program's scope of control, but improving the relevance (R) of the Study Program in many ways will give the competitive advantages to the graduates so that they could ask for a higher salary on their first jobs.

The Study Program was accredited C in 1998, and only recently it was up-graded to B. It is strongly believed that if all activities are implemented in the TPSDP according to the proposed plans, the Study Program will be accredited A.

Additional indicators as presented in Table II-2 are thought to be the direct impact of all proposed activities as described in details in the following Chapter 2.2. IMPROVING RAISE++. In addition to that, each proposed activity has its own performance indicators also.

Chapter 2.2. IMPROVING RAISE++

1. Relevance

| Code | Name of Activity |  |
| --- | --- | --- |
| R.1. | Improving, updating and renewing the quality of the modules, materials and delivery of the advance laboratory courses: Laboratory III and Laboratory IV (including the improvement of the qualifications of the Laboratory Assistants). |  |
| R.2. | Enhancing the industrial relation in the surrounding area: |  |
|  | R.2.1. | Developing Apprenticeship Programs in Industry |
|  | R.2.2. | Developing Curriculum and Syllabus with a close cooperation with Industry |
|  | R.2.3. | Developing Industrial Training and Studies Programs |
| R.3. | Developing NEW Classroom/Laboratory Teaching Materials: |  |
|  | R.3.1. | Cellular Telecommunication |
|  | R.3.2. | CISCO Certified Network Associate Training Center Development |
| R.4. | Enhancing Students’ Co-Curricular Activities and Additional Skills and Competencies: |  |
|  | R.4.1. | English Competency: Technical and Engineering Writing Skills |
|  | R.4.2. | Computer and Internet Skills |
|  | R.4.3. | Student Electrical Workshop |
|  | R.4.4. | Students’ Personality Enhancement and Entrepreneurship Training Programs |
| R.5. | Improving the Teaching Staff’s academic qualifications and the Administrative Staff’s competency and skills: |  |
|  | R.5.1. | Domestic and Overseas Degree Programs S2, S3 |
|  | R.5.2. | Local Vocational Trainings for Administrative Staffs and Laboratory Technicians |
|  | R.5.3. | International Conferences and Domestic Special Non-Degree Programs |

1.1. Name of Activity: R.1. Improving, updating and renewing the quality of the modules, materials and delivery of the advance laboratory courses: Laboratory III and Laboratory IV (including the improvement of the Laboratory Assistants qualifications).

Background: The structure of curriculum requires advance laboratory courses Laboratory III and Laboratory IV to be taken at the fifth and the sixth semester by the students of different Sub-Study Programs in different 11 (eleven) laboratories. These two laboratory courses are designed to support the core and advance courses provided by each Sub-Study Program (see Chapter III.1.B. Section 11 Curriculum on page III.B.1-16 of the Revised Sub-Project Proposal). There has been no serious updating of both laboratory teaching materials and laboratory equipment since 15 years ago when the Study Program moved from the old campus. The obsolescence of both the teaching materials and the equipment is apparent, which makes the laboratory courses irrelevant to the rapid progress of electrical engineering technology as well as the demand of the job-market. Lack of sufficient funding to maintain and update old equipment has made most laboratory equipment and instruments are not functioning appropriately as they are supposed to be. In the first year of implementation, there have been some progress that can be reported for each activities as follows: R.1.1. Assessing the existing laboratories condition, mainly in terms of organizational and management aspects, environmental and utilities setting, and the quality of laboratory course materials. The Term of Reference (TOR) of the Program Development related to this sub-activity R.1.1. has not been approved until the beginning of October 2003 when the draft of this report is written, but this sub-activity has indicated some progress to be reported here. The Person in Charge (PIC) of this Activity R.1., in cooperation with the PIC of Activity R.2. and E.2, has carried out a “Workshop on Curriculum of Electrical Engineering Study Program Development” along the year 2003. The workshop is planned to be held all year long – including a series of open discussions via the alumni mailing-list (see http://groups.yahoo.com/group/iatel-unhas/messages/ for details) in the Internet participated by alumni who mostly work in industry - to produce a renewed curriculum of the Study Program implemented in 2004. This new curriculum will accommodate the TPSDP plan to renew the advance laboratory courses Laboratory III and Laboratory IV, which are the main targets of this Activity R.1. So far, the workshop has produced an initial draft of the new curriculum. R.1.2. Preparing the standard workplace and required utilities in the laboratories. The bidding process of the procurement of the laboratory furniture has been proceeding smoothly at the SPMU level and while this report is written, the bidding committee is still evaluating the bidding documents submitted by several bidders. The recommendation will be soon submitted to the CPMU. Concerning the civil works related to this Activity R.1., the bidding process is almost completed, the renovation of the laboratory building facilities is planned to begin in January 2004 at the latest. R.1.3. Repairing and renewing the existing experiment modules, instruments and parts. R.1.4. Commissioning test of the new laboratory equipment. The two sub-activities above are related to the procurement of the laboratory equipment implemented in the second year of this project. Apparently, the bidding process for the procurement of the equipment for the second year has been combined with the procurement for the first year in an ICB package.. Therefore the equipment are expected to be delivered early next year. R.1.5. Developing experiment guides and related laboratory assistant training materials. R.1.6. Implementing and evaluating the updated experiment modules for Laboratory III and IV courses Both sub-activities above are to be implemented in the second year of this project after the new curriculum is established, right before the delivery of the laboratory equipment is on the way.

To be continued in the next page ……

| Activity R.1. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Resources required for year 2: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activity | Cost Components |  |  |  | Rp |  |  | US $ |  |  | Source of Funding |  |  |  |  |  |
| R.1.1. | Program Development |  |  |  | 4.000.000,00 |  |  |  |  |  | TPSDP |  |  | DRK |  |  |
| R.1.2. | Furniture |  |  |  | 0,00 (Implemented) |  |  |  |  |  | TPSDP |  |  |  |  |  |
|  | Civil Works |  |  |  | 0,00 (Implemented) |  |  |  |  |  | TPSDP |  |  | DRK |  |  |
| R.1.3. | Equipment |  |  |  | 290.147.500,00 |  |  | 148.586,86 (Implemented) |  |  | TPSDP |  |  |  |  |  |
| R.1.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.5. | Program Development |  |  |  | 5.000.000,00 |  |  |  |  |  | TPSDP |  |  |  |  |  |
|  | Total |  |  |  | 299.147.500,00 |  |  | 148.586,86 |  |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activity |  | Yr 1 |  |  |  |  | Yr 2 |  |  |  |  |  |  |  |  |  |
| R.1.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.2. |  | Re-scheduled |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.6. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  | Baseline |  |  |  | Mid |  |  | Final |
| Repaired, updated and renewed experiment modules and test instruments |  |  |  |  |  |  |  |  | 0% |  |  |  | 50% |  |  | 100% |
| Percentage of graduates working in their related fields |  |  |  |  |  |  |  |  | N/A |  |  |  | 40% |  |  | 60% |
| Sustainability : The sustainability of this activity will be guaranteed by establishing: - Routine maintenance and repair works by laboratory assistants and technicians who acquire the skills from appropriate training programs. - Practical training programs for technical high school and/or D-3/Polytechnic students in laboratory routine maintenance and repair works. - Cooperation with private universities in surrounding area for laboratory assistant training programs - Collaboration with industry in joint-research programs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. Hj. Nien K. Nauman |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1.2. Name of Activity: R.2. Enhancing the industrial relation in the surrounding area.

Background: - The Study Program has a very limited collaboration with local companies and industries yielding no solid linkage with the surrounding environment - Job-market in most industries requires industrial experience in the recruitment of fresh graduates - There is an indication that a number of alumni were fired from work right after their probation - Many fresh graduates were not sufficiently confident to enter the job-market due to their very low experience in industrial world The progress after the first year of implementation can be reported as follows: Note: 2 (two) out of 3 (three) sub-activities in this activity are to be implemented in Year 1, but due to one reason or another, none of the required TORs of Program Development has been approved until the beginning month of October 2003. The two aub-activities are R.2.1. and R.2.2.: R.2.1. Developing Apprenticeship Programs in Industry. Several early contacts have been made with the surrounding industry to search for any opportunity to develop apprenticeship programs. The existing apprenticeship program with PT. INCO (a nickel--->

To be continued in the next page ……

| Activity R.2. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Background: (contnued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ----> mining industry in the area) is continuously maintained. The TOR of this Program Development for the first year has been approved.. . R.2.2. Developing Curriculum and Syllabus with a close industrial cooperation In coordination with the PIC of Activity R.1.and Activity E.2., a continuous “Workshop on Curriculum of Electrical Engineering Study Program Development” has been held along this year. The participation from the industrial world is apparent in the discussion via mailing-list (see the report on sub-activity R.1.1. in the previous page). In July 2003, sponsored by the Directorate General of Post and Telecommunication and several telecommunication operators, the Study Program held a seminar on the development of curriculum of Electrical Engineering Study program – especially in the telecommunication field of study. R.2.3. Developing Industrial Training and Studies Programs This sub-activity is scheduled to be implemented in Year 2. But since an opportunity to develop a relevant program came in the Year 1, this sub-activity is re-scheduled to begin earlier.. A "Training on the application of CYGNAL Microcontroller 51" by Ir.Irwan Tantu, MSc. was held on July 15-16, 2003 and attended by several students, mostly were laboratory assistants. This training has assisted the student to obtain more experiences, knowledge and skills in the application of microprocessor-based systems.The trainer is an alumnus of the Study Program, who is now an engineer at a computer software industry e-Production Solutions Inc. Houston Texas, USA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources required for year 2 : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activity | Cost Components |  |  | Rp. |  |  |  |  |  | Funding Source |  |  |  |  |  |
| R.2.1. | Program Development |  |  | 4.230.760,- |  |  |  |  |  | TPSDP |  |  |  | DRK |  |
| R.2.2. | Program Development |  |  | 5.769.240,- |  |  |  |  |  | TPSDP |  |  |  | DRK |  |
| R.2.3. | Program Development |  |  | 10.000.000,- |  |  |  |  |  | TPSDP |  |  |  | DRK |  |
|  | TOTAL |  |  | 20.000.000,- |  |  |  |  |  | TPSDP |  |  |  | DRK |  |
| Implementation Schedule (By Quarter) : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities/Sub-activities |  | Yr 1 |  |  |  |  |  | Yr 2 |  |  |  |  |  |  |  |
| R.2.1 Re-scheduled |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.2.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.2.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  | Baseline |  |  | Mid |  |  |  | Final |  |  |
| Percentage of alumni participating in the industrial apprenticeship program every graduation |  |  |  |  |  | 0% |  |  | 5% |  |  |  | 10% |  |  |
| Number of implemented Memorandum of Agreements (MOUs) on curriculum development with industries |  |  |  |  |  | N/A |  |  | 4 |  |  |  | 10 |  |  |
| Graduates’ waiting time before getting the first job |  |  |  |  |  | 11 months |  |  | 9 months |  |  |  | 5 months |  |  |
| First job salary (in Rupiahs) |  |  |  |  |  | Rp.712.400 |  |  | Rp.1.000.000 |  |  |  | Rp.1.500.000 |  |  |
| Sustainability : To continue with this apprenticeship program and the industrial relation after the final year of the project term, the following efforts could be done: - Each participant is asked to contribute for this program - Alumni Association could adopt this program If the industrial world can be convinced that this program is beneficial, the collaboration with the industrial world will continue. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. A. Toyib Rahardjo, M.Sc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1.3. Name of Activity: R.3. Developing NEW Classroom/Laboratory Teaching Materials

| ## Background: Due to the lack of adequate courses materials, laboratory equipment, access of information and advance technology skills; the alumni seem to lose the self-confidence, especially when they have to penetrate job market. This activity was originally planned for Year 2 implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ## Rationale: With this activity, it is expected that the alumni will have more ability and knowledge to compete with others to get their jobs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Objective: The activity proposed below will provide an opportunity for the lecturers and students to keep up with the current technological development. The alumni will have some opportunity to get world wide accepted certificates. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Mechanism and design: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## R.3.1. Improving the knowledge and skills of staff and student in the progress of cellular technology development: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ## R.3.1.1: Improving the staff and students’ practical skills and knowledge through a related industrial apprenticeship program |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ## R.3.1.2: Preparing the required hardware and software, including instructional materials and experimental guides. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ## R.3.1.3: Providing a competitive Teaching Grant for developing related laboratory course materials |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ## R.3.1.4: Implementing the laboratory course on cellular technology |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## R.3.2. Acquiring the CISCO Certified Network Associates (CCNA): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ## R.3.2.1: Instructors in-country training for CCNA. Candidates will be sent to an in-country CCNA Centre to participate in a two-month training program to obtain the Certificate of Instructor. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R.3.2.2: Preparing the required hardware, software and Internet link necessary to establish the center. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R 3.2.3: Developing the instructional materials for the training program |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R.3.2.4: Conducting the Local Assistants Training |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R.3.2.5: Implementing the regular training programs |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R.3.2.6: Conducting the standard tests for certification |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resource Required for year 2: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Sub-Activity | Cost Component |  |  |  | Rp. |  |  | US$ |  | Funding Source |  |  |
| R 3.1 |  | R 3.1.1 | Program Dev. |  |  |  | At cost |  |  |  |  | R.2.1 |  |  |
|  |  | R 3.1.2 | Equipment |  |  |  |  |  |  | 0,00 (Implemented) |  | TPSDP |  |  |
|  |  | R 3.1.3 | Teaching Grant |  |  |  | (Year 3) |  |  |  |  | TPSDP |  |  |
| ###### R.3.2. |  | R 3.2.1 | Staff Dev. |  |  |  | (Year 3) |  |  |  |  | TPSDP + DRK |  |  |
|  |  | R 3.2.2 | Equipment |  |  |  |  |  |  | 0,00 (Implemented) |  | TPSDP |  |  |
| Total Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation Schedule: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Sub-Activity |  | Yr 1 |  |  |  |  | Yr 2 |  |  |  |  |  |
| R 3.1 |  | R 3.1.1 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R 3.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R 3.1.3 |  |  |  |  |  |  |  |  |  |  |  | Year 3 |
|  |  | R.3.1.4 |  |  |  |  |  |  |  |  |  |  |  | Year 3 |
| To be continued in the next page …… |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Activity R.3. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Implementation Schedule:(continued) |  |  |  |  |  |  |  |  |  |  |  |  |
| R.3.2. | R 3.2.1 |  |  |  |  |  |  |  |  |  |  | Year 3 |
|  | R 3.2.2 |  |  |  |  |  |  |  |  |  |  |  |
|  | R 3.2.3 |  |  |  |  |  |  |  |  |  |  |  |
|  | R 3.2.4 |  |  |  |  |  |  |  |  |  |  |  |
|  | R.3.2.5 |  |  |  |  |  |  |  |  |  |  |  |
|  | R 3.2.6 |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity: |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity | Indicators |  |  |  |  | Baseline |  | Mid |  |  | Final |  |
| R 3.1. | Number of Apprenticeship participants a. Staff b. Student |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 0 |  | 2 persons |  |  | 5 persons |  |
|  |  |  |  |  |  | 0 |  | 8 persons |  |  | 16 persons |  |
|  | Number of graduates working in cellular technology |  |  |  |  | N/A |  | 1 person |  |  | 5 persons |  |
| R 3.2. | Number of CCNA Instructors |  |  |  |  | 0 |  | 2 persons |  |  | 2 persons |  |
|  | Number of CCNA certified associates |  |  |  |  | 0 |  | 20 persons |  |  | 80 persons |  |
| Sustainability: In the future, these activities will become sources of revenue for the Study Program. Local private universities and industries, as well as students and alumni, are expected to participate in the local training, to use the laboratories and to obtain the International Certification through these programs. |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge : Ir. H. Tahir Ali. |  |  |  |  |  |  |  |  |  |  |  |  |

1.4. Name of Activity: R.4. Enhancing Students’ Co-Curricular Activities and Additional Skills and Competencies

Background: A plan to enhance the student additional skills and competence should be proposed to improve the students' English competency, vocational, computer and internet skills. The establishment of student workshop facilities is also a part of this plan. From the polling (see the analysis at the end of Section 2 Environmental Setting, page III.B.1-8 and appendix III.10, page III-Ap-9 of the Revised Sub-Project Proposal) only about little bit more than 10 % of the students intended to work as entrepreneurs (8,71 %) or freelance workers (2,70 %) after they graduated. Regular programs/activities should be proposed to enhance the students' personality entrepreneurship as another part of the plan. The progress can be reported as follows: Note : One of the performance targets of this activity R.4. is the student participation in the National Technical and Scientific Contests/Competetion (see Revised-S.I.P., page II-11). The baseline is 0 (no participation), and the midterm target is participating in every other year. Better than the target, in this first year of the project term only, the students have participated in 2 (two) national contests, namely: - The Indonesian Robotic Contest in the University of Indonesia, Depok, May 3-7, 2003. (see http://www.unhas.ac.id/~robot/ for details) - The Ladder Programming National Contest in Maranatha Christian University, Bandung, mid-September 2003. R.4.1. Developing regular programs/activities to improve the Students’ English Technical Writing and Conversational Skills The TOR of this sub-activity has not been approved until the beginning of October, but a “one ---->

To be continued in the next page

| Activity R.3. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Background:(continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ---> month workshop on improving English skills” has been planned to be launched before mid-October. 2003. This workshop helps student to improve their English writing and conversation skills. This workshop is expected to be carried out once a year R.4.2. Developing regular training programs/activities to improve the Students’ Computer and Internet Skills This activity has carried out a workshop and contest on Ladder Programming. There were two teams have participated in a National Contest of Ladder Programming at Maranatha Christian University, Bandung. R.4.3. Establishing the Student Electrical and Electronic Workshop to improve the students’ vocational skills. This activity has carried out a workshop on computer hardware assembly and troubleshooting and also computer network installation. The procurement process of equipment and books for this sub-activity is taken care of at the SPMU level. R.4.4. Developing regular programs/activities to enhance Students’ Personality and Entrepreneurship A "Semi-Workshop on Personality Profile & The Secret to Ultimate Success for Students" has been held on June 21, 2003, attended by around 100 students. A professional presenter was invited from Surabaya to conduct the event. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Cost Components |  |  |  |  | Rp. |  |  |  | Funding Source |  |  |  |
| R.4.1. |  | Program Development |  |  |  |  | 2.000.000,- |  |  |  | TPSDP + DRK |  |  |  |
| R.4.2. |  | Program Development |  |  |  |  | 10.000.000,- |  |  |  | TPSDP + DRK |  |  |  |
| R.4.3. |  | Equipment |  |  |  |  | (Implemented) |  |  |  | TPSDP |  |  |  |
|  |  | Instructional Material |  |  |  |  | (Implemented) |  |  |  | TPSDP |  |  |  |
| R.4.4. |  | Program Development |  |  |  |  | 6.692.761,90 |  |  |  | TPSDP + DRK |  |  |  |
|  |  | TOTAL: |  |  |  |  | 18.692.716,90 |  |  |  | TPSDP |  |  |  |
| Implementation Schedule (By Quarter) : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Yr 1 |  |  |  |  |  | Yr 2 |  |  |  |  |  |  |
| R.4.1.(Developt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.1.(Implemt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.2.(Developt.) |  | Implemented |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.2.(Implemt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.4.(Developt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.4.(Implemt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No. | Indicators |  |  |  |  | Baseline |  |  | Mid |  |  |  | Final |  |
| 1 | TOEFL Score (average) |  |  |  |  | 403 |  |  | 450 |  |  |  | 500 |  |
| 2 | Percentage Internet users among students |  |  |  |  | no data |  |  | 50% |  |  |  | 95% |  |
| 3 | Participation in the National Technical and Scientific Contests/Competition |  |  |  |  | 0 |  |  | every other year |  |  |  | every year |  |
| 4 | Percentage of students who are motivated to become entrepreneurs after graduations |  |  |  |  | < 10% |  |  | 30% |  |  |  | 40% |  |
| Sustainability : All activities would be a regular student activities, and expected to generate revenues to support the continuity of student extra-curricular activities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Elyas Palentei, S.T., M.Eng. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1.5. Name of Activity: R.5. Improving the Teaching Staff’s academic qualifications and the Administrative Staff’s/Laboratory Technicians’ competency and skills

Background: 32.61% of the Study Program’s teaching staff are above 50 years old, 84.78% are alumni, only 4 (four) Ph.D.’s and only 2 (two) of those four Ph.D.'s are Professors. Teaching loads are very high due to the student-to-lecturer ratio, which is about 36.7. The composition and the qualifications of the teaching staffs do not support efficient and productive teaching and learning process. More importantly, most of the lecturers did not have any academic experiences other than their own college experience many years back. Consequently, all teaching materials and methods delivered by those lecturers are irrelevant to the progress of the electrical engineering technology. The implementation in the first year can be reported as follows: R.5.1. Improving the staffs’ academic qualification by attending degree-programs both overseas and domestic. - Domestic Degree Training (original plan, copied from the Revised SIP Appendix 1). Detailed Specifications : Staff Development - Domestic Degree Training – year 1. Name of Tentative Candidates; Field Of Study; Targeted University to apply. Indra Jaya *); Electrical Systems; ITS**. Ansar Suyuti *); Electrical Systems; ITS**. Ferry Sampetoding *); Telecommunication; ITB ***. *) Replaced Changed to: **) UGM ***)ITS The current status of each candidate is described as the following: - Mr.Yusran has replaced Mr.Ansar Suyuti (who was elected the Chairman of the Department earlier this year) and he has contacted a professor in Gadjah Mada University (UGM) and arranged all required documents for admission. Mr.Yusran’s research proposal is expected to be submitted by the end of October 2003. - Mrs.Hasniaty has replaced Mr.Indra Jaya (who was elected the Department Secretary earlier this year) and she has submitted her research proposal to UGM and she is waiting for a response from UGM. Mrs.Hasniaty’s research proposal is expected to be approved by the end of October 2003. - Mr.Indrabayu has replaced Mr.Ferry Sampetoding, who got a serious problem with his health. He has been accepted at the Department of Electrical Engineering, Sepuluh November Institute of Technology (ITS) Surabaya and has started his first semester in September 2003 for a two year Masters Degree program in Telecommunication. 2. Overseas Degree Training (original plan, copied from the Revised SIP, Appendix 3). # Detailed Specifications : Staff Development - Overseas Degree Training – year 1. Name of Tentative Candidates; Field Of Study; Targeted University to apply. Tadjuddin Waris; Electrical Power; Curtin University, Australia. Dewiani; Telecommunication; Curtin University, Australia. Syafruddin Syarif; Telecommunication; University of Newcastle, Australia. Samuel Panggalo; Telecommunication; University of Newcastle, Australia *). Andani Ahmad; Telecommunication; UTM, Malaysia **). Changed to: *) Curtin University, Australia **) UKM, Malaysia

To be continued in the next page ……

| Activity R.5. (continued) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Background (continued): The status of each candidate is as the following (this status keeps changing almost daily): - Mr. Tadjuddin Waris has obtained a letter of offer from Curtin University of Technology to enroll the Doctor of Philosophy program at School of Electrical and Computer Engineering and he is expected to arrive in Australia on February 2004. - Ms. Dewiani has obtained a letter of offer from Curtin University of Technology to enroll the Doctor of Philosophy program at School of Electrical and Computer Engineering and she is expected to arrive in Australia on February 2004. - Mrs. Samuel Panggalo has obtained a letter of offer from Curtin University of Technology to enroll the Doctor of Philosophy program at School of Electrical and Computer Engineering and he is expected to arrive in Australia on February 2004 - Mr. Syafruddin Syarif (who was appointed to chair a Special D3 Study Program for PT. TELKOM employees) has been replaced by Mr.Elyas Palantei, who has obtained a letter of offer from Griffith University, Australia and currently is preparing all required documents.Mr. Palantei is expected to arrive in Australia at the end of January 2004. - Mr.Andani Ahmad is still waiting for comments from his future advisor regarding his research proposal that has been submitted before. R.5.2. Improving the administrative staffs’ and laboratory technicians’ knowledge and skills by attending local vocational training programs. The TOR of this Staff Development was one of the four missing TORs. It has been re-submitted together with the other missing three, and now is waiting for an approval from the CPMU. Thus, this sub-activity remains in the stage of preparation to be implemented, but it is expected to have no obstacle. Once the TOR is approved, the sub-activity will run. R.5.3. Enlarging the staffs’ academic perspectives by attending international conferences and special domestic non-degree programs. Overseas Non-Degree Training (original plan, copied from the Revised SIP, Appendix 4). # Detailed Specifications : Staff Development - Overseas non-Degree Training - year 1. Name of Tentative Candidates; Field Of Study; Targeted University to apply. Rhiza S.Sadjad; Control System; International Conference, Singapore. This program has been implemented successfully. Mr. Rhiza S. Sadjad and Mr. Faisal A. Samman have presented their papers in a International Conference in Singapore in December 2002. Furthermore, Mr.Salama and Mr.M.Arif have attended and presented their papers at the International Event 2003, Conference on Electrical, Electronics, Communication and Information (CECI) – Seminar on Intelligent Technology and Its Application (SITIA) on July 17, 2003 in Surabaya, Indonesia |
| Resources required for year 2: |  |  |  |  |
| Activity | Cost Components | Rp. | US $ | Funding Source |
| R.5.1. | Staff Development | 59.500.000,- | 118,700.00 | TPSDP |
| R.5.2. | Staff Development | 36.950.000,- |  | TPSDP |
| R.5.3. | Staff Development |  | 4,800.00 | TPSDP |
|  | TOTAL: | 96.450.000,- | 123,500.00 |  |
| To be continued in the next page …… |  |  |  |  |

| Activity R.5. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Implementation Schedule (By Quarter) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Yr1 |  |  |  |  |  | Yr 2 |  |  |  |  |  |  |
| R.5.1. | S3 (overseas) |  | 5 Re-scheduled |  |  |  |  |  |  |  |  |  |  | 0 |
|  | S3 (domestic) |  | 2 |  |  |  |  |  |  |  |  |  |  | 0 |
|  | S2 (overseas) |  |  |  | 1 |  |  |  |  |  |  | 0 |  |  |
|  | S2 (domestic) |  | 1 |  |  |  |  |  | 0 |  |  |  |  |  |
| R.5.2. | Loc. voc. training |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.5.3. | Int’l Seminar/Tra. |  | 1 |  | 1 |  |  |  | 2 |  |  |  |  |  |
|  | Dom.Non-Deg. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  | Baseline |  |  |  | Mid |  |  | Final |  |
| Number of Ph.D. (S-3 Degrees) holders |  |  |  |  |  | 4 |  |  |  | 5 |  |  | 8 |  |
| Number of Masters Degree holders |  |  |  |  |  | 16 |  |  |  | 25 |  |  | 35 |  |
| Number of papers published in Int’l Journal |  |  |  |  |  | 0 |  |  |  | 1 |  |  | 4 |  |
| Number of self-repaired laboratory equipment |  |  |  |  |  | 0% |  |  |  | 25% |  |  | 70% |  |
| Service-time at the Department Office (e.g. the process of issuing academic transcripts) |  |  |  |  |  | 1 day |  |  |  | - |  |  | 5 minutes |  |
| Sustainability : Staff Development is always a long term investment that will last. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Prof.DR.Ir.Muh.Tola, M.Eng |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

2. Academic Atmosphere

| Code | Name of Activity |  |
| --- | --- | --- |
| A.1. | Special Events, Meetings and Dialogues: |  |
|  | A.1.1. | Improving teaching methods by providing Teaching Grants |
|  | A.1.2. | Improving the students’ research (skripsi) qualities by providing Student Grants |
|  | A.1.3. | Improving the staffs’ research qualities by providing Research Grants |
|  | A.1.4. | Developing a teaching and learning process evaluation system involving students |
|  | A.1.5. | Developing the staffs’ advising abilities by providing a Guidance and Counseling Training program. |
|  | A.1.6. | Academic Dialogue and other special events involving all staffs and students. |
|  | A.1.7. | Academic Meetings. |
| A.2. | Enhancing student's learning skills and reading habits |  |

2.1. Name of Activity: A.1. Special Events, Meetings and Dialogues

Background: The relation among students, lecturers and staff is an essential factor of academic atmosphere. Due to heavy loads and tight class schedule, the interaction between students and lecturers is generally very limited, except in the supervision of the skripsi. The relation between the Electrical Engineering Student Association (HME) and the academic staff does not seem as having created a conducive environment to build a high-quality teaching-learning process. The progress of this activity can be described per-sub-activity as follows:

To be continued in the next page ……

| Activity A.1.(continued) |  |  |  |
| --- | --- | --- | --- |
| Background (continued): A.1.1. Improving teaching methods by providing Teaching Grants to the achievers in a competitive scheme There are 2 (two) Teaching Grants allocated for Year 1, competed by at least 6 (six) proposals. It was unexpected that there were 9 (nine) proposals submitted by the staffs, indicating the high motivation among staffs to improve their teaching methods. The two grantees eventually are two important fundamental courses, namely Analog Electronics and Engineering Mathematics, conducted by the total of 3 (three) lecturers... A.1.2. Improving the students’ research qualities by providing Student Grants to the achievers in a competitive scheme The number of submitted Student Grant proposals was 33 proposals, which is 10 % more than the expected 30 proposals. The allocated number of grantees for the Year 1 is 10 (ten) projects, which is fully taken by 20 (twenty) students. Most projects are in the area of Telecommunication and Computer technology. A.1.3. Improving the staffs’ research qualities by providing Research Grants to the achievers in a competitive scheme The number of Research Grants proposal submitted by academic staff was 6 (six) proposals, 2 (two) of them were awarded as has been allocated for Year 1. Each granted project is involving 3 (three) staffs and at least 4 (four) students. One is a research project in the area of Power Engineering and the other is in the area of Control Engineering. A.1.4. Developing a teaching and learning process evaluation system involving students The design of an evaluation system has been proposed, but there has not been any chance to discuss it among the staff. The only established teaching and learning process evaluation system right now is the classroom monitoring system for the student and staff attendance. A.1.5. Developing the staffs’ advising abilities by providing a Guidance and Counseling Training program. The TOR of this sub-activity is one of the missing TORs on their way to the CPMU. New TOR has been re-submitted. The program is ready to run, once the TOR is approved. This sub-activity is planned to be arranged together with the Activity E.1. A.1.6. Academic Dialogue and other special events involving all staffs and students, including sport tournaments, engineering expo, and special events to honor the best lecturers, the best students, the employee of the year, etc. Except for the special events to honor the best students, best lecturers, etc., all other special events have been successfully arranged as routine annual events and traditions. A.1.7. Academic Meetings: Staff and Teaching Assistants, Staff and Laboratory Technicians/Assistants. Much effort has been made to arrange all categories of academic meetings attended by all relevant groups. A new organizational structure within the Study Program called “Board of Assistant” (Dewan Assisten) has been established to help the Study Program to better manage the Laboratory and Teaching Assistants. |  |  |  |
| Resources required for year 2 : |  |  |  |
| Activity | Cost Components | Cost (Rp.) | Source of Funding |
| A.1.1. | Teaching Grant (1 of Rp20,000,000) | 20.000.000,00 | TPSDP |
| A.1.2. | Student Grants (10 of Rp. 5,0000,000) | 50.000.000,00 | TPSDP |
| A.1.3. | Research Grants (2 of Rp30,000,000) | 60.000.000,00 | TPSDP |
| A.1.5. | Program Development | 6.000.000,00 | TPSDP + DRK |
|  | TOTAL | 136.000.000,00 |  |
| To be continued in the next page …… |  |  |  |

| Activity A.1.(continued) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Implementation Schedule (By Quarter) : |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Yr 1 |  |  |  |  | Yr 2 |  |  |  |  |  |
| A.1.1 |  |  |  |  |  |  |  |  |  |  |  |
| A.1.2 |  |  |  |  |  |  |  |  |  |  |  |
| A.1.3. |  |  |  |  |  |  |  |  |  |  |  |
| A.1.4 |  |  |  |  |  |  |  |  |  |  |  |
| A.1.5 |  |  |  |  |  |  |  |  |  |  |  |
| A.1.6 |  |  |  |  |  |  |  |  |  |  |  |
| A.1.7 |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  | Baseline |  | Mid |  |  | Final |  |
| Frequency of the special events |  |  |  |  | Every other year |  | 1 per year |  |  | 2 per year |  |
| Participation in national academic/scientific events for students |  |  |  |  | N/A |  | Every other year |  |  | Every year |  |
| Number of scientific papers published in national and international journal per year |  |  |  |  | N/A |  | 4 |  |  | 8 |  |
| Number of academic seminars and conferences hosted by the Study Program |  |  |  |  | 1 – 2 per year |  | 3 per year |  |  | 6 per year |  |
| Sustainability : In order to keep up all activities running regularly and periodically, All components of study program are expected to participate in all activities regularly. Thus, these leads to the sustainability of the academic atmosphere. |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. Zaenab Muslimin |  |  |  |  |  |  |  |  |  |  |  |

2.2. Name of Activity: A.2. Enhancing student's learning skills and reading habits

Background: The condition of the Study Program’s library is not favorable for the advancement of student’s learning skills and reading habits indicated by the low percentage of students coming in for reading or checking-out books. The explanation behind this condition is that the library has: - Very limited collections of references, those that are available are out of date (11 to 20 years old) - Limited capacity of bookshelves, so many collections are not kept in order. - Reading room is cold, humid and very inconvenient At the end of the first year term of the project, the status of this activity can be reported as follows: A.2.1. Preparing the library room condition for better reading convenience A.2.2. Making a better arrangement of book collections. A.2.3. Enriching book collections and the latest published journals.. A.2.4. Establishing and maintaining a computerized library database system integrated to the Department Network. The resources for the implementation of all the above sub-activities are taken care of at the SPMU level. The bidding processes are still proceeding. Once all resources become available, all the related works will be ready to carry on. A.2.5. Developing and enhancing the students’ learning skills. The TOR for this sub-activity has not been entirely approved. Minor corrections should be made. This main target of this sub-activity is the new student body. In some aspects the nature of this sub-activity is similar to the sub-activity R.4. 4.

To be continued in the next page ……

| Activity A.2. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Resources required for year 2 : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Cost Components |  |  |  | Rp. |  |  | US$ |  |  |  | Funding Source |  |  |  |
| A.2.1. | Civil Works |  |  |  | 93.353.808,60 |  |  |  |  |  |  | TPSDP |  |  | DRK |
| A.2.2. | Furniture |  |  |  | 13.100.000,00 |  |  |  |  |  |  | TPSDP |  |  |  |
| A.2.3. | Instruction Materials |  |  |  | 3.401.640,50 |  |  | 8.567,70 |  |  |  | TPSDP |  |  |  |
| A.2.4. | Equipment |  |  |  | 4.750.000.00 |  |  |  |  |  |  | TPSDP |  |  |  |
| A.2.5. | Program Development |  |  |  | 12.000.000,00 |  |  |  |  |  |  | TPSDP |  |  | DRK |
|  | TOTAL |  |  |  | 122.605.449,10 |  |  | 8.567,70 |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter) : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Yr 1 |  |  |  |  |  | Yr 2 |  |  |  |  |  |  |  |  |
| A.2.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  | Baseline |  |  |  | Mid |  |  | Final |  |  |
| The number of students visiting in the library (students/day) |  |  |  |  |  | 10 |  |  |  | 15 |  |  | 22 |  |  |
| The number of books check out(books/day) |  |  |  |  |  | 9 |  |  |  | 15 |  |  | 18 |  |  |
| The number of students reading in the library (students/day) |  |  |  |  |  | 2 |  |  |  | 5 |  |  | 10 |  |  |
| Sustainability: All facilities and infrastructures are a long term investment that will still exist even after the project is over. For the continuity of the learning skills training program after the project is over, contribution from the students’ parent is expected. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. Hj. Sri Mawar Said |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

3. Efficiency and Productivity

| Code | Name of Activity |
| --- | --- |
| E.1. | Improving the quality of the classroom teaching and learning process (including the improvement of the qualifications of the Teaching Assistants) |
| E.2. | Expanding the Capacity of the Basic Laboratory Courses: Laboratory I and Laboratory II (Including the Improvement of the Qualifications of the Laboratory Assistants) |

3.1. Name of Activity: E.1. Improving the quality of the classroom teaching and learning process (including the improvement of the qualifications of the Teaching Assistants)

| Background: Since the end of the Engineering Acceleration Project, the quality of the classroom teaching and learning process tends to decline. This is - among others - due to the increasing number of student population. Moreover, the bureaucracy of the university does not allocate sufficient funding for lecturers’ overtime and incentives. For this particular reason, lecturers used to try to avoid burden they have by accommodating larger students in one class. The status of this activity at the end of the first year term of the implementation is as follows: E.1.1. Identifying problems and socialize them to all components in meetings and discussions. This sub-activity is in line with A.1.4., A.1.6. and A.1.7. described in previous pages E.1.2. Establishing a solid teaching-assistantship. A new organizational structure within the Study Program called “Board of Assistant” ---------- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To be continued in the next page …… |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity E.1. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Background (continued): -- (Dewan Assisten) has been established to help the Study Program to better manage the Laboratory and Teaching Assistants. The Board of Assistant will provide a solid ground for the establishment of strong laboratory and also teaching assistantship. E.1.3. Improving the quality of teaching and learning process, especially in the utilization of Internet for education, communication media and educational technology. The TOR for this sub-activity has not been entirely approved. The procurement of the equipment is still proceeding. Fortunately the PIC of this Activity E.1. is granted a Teaching Grant for his course, so naturally thes sub-activity will start from there. ###### E.1.4. Optimizing room utilization The civil works as well as the procurement of the furniture related to this sub-activity is still in the bidding stages at the SPMU level. Currently, most classrooms have been equipped permanently with Overhead Projectors. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources required for year 2 : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity | Cost Components |  |  |  | Rp |  |  | US$ |  |  |  | Funding Source |  |  |  |
| E.1.1. | Program Development |  |  |  | At Cost |  |  |  |  |  |  | Others |  |  |  |
| E.1.2. | Program Development |  |  |  | 10.000.000,00 |  |  |  |  |  |  | TPSDP |  |  | DRK |
| E.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Equipment |  |  |  | 50.575.000,00 |  |  |  |  |  |  | TPSDP |  |  |  |
| E.1.4. | Civil Works |  |  |  | 73.435.019,00 |  |  |  |  |  |  | TPSDP |  |  | DRK |
|  | Furniture |  |  |  | 26.600.000,00 |  |  |  |  |  |  | TPSDP |  |  |  |
| TOTAL |  |  |  |  | 160.610.019,00 |  |  |  |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter) : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity | Yr 1 |  |  |  |  |  | Yr 2 |  |  |  |  |  |  |  |  |
| E.1.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.1.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.1.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  | Baseline |  |  |  | Mid |  |  | Final |  |  |
| Meeting and discussion (times/month) |  |  |  |  |  | - |  |  |  | 2 |  |  | 4 |  |  |
| Recruited Teaching Assistants (students/year) |  |  |  |  |  | - |  |  |  | 30 |  |  | 50 |  |  |
| Participation in trainings (persons/year) |  |  |  |  |  | - |  |  |  | 20 |  |  | 40 |  |  |
| Student-to-lecturer ratio |  |  |  |  |  | 25:1 |  |  |  | 18:1 |  |  | 12:1 |  |  |
| Excess loads per semester (SKS) |  |  |  |  |  | 150 |  |  |  | 75 |  |  | 0 |  |  |
| Classrooms (rooms) |  |  |  |  |  | 5 |  |  |  | 9 |  |  | 9 |  |  |
| Percentage of students who are satisfied with the teaching and learning process. |  |  |  |  |  | N/A |  |  |  | 50% |  |  | 95% |  |  |
| Sustainability: The improvement of efficiency and productivity of the classroom teaching and learning process will reduce educational costs, so in the long run the benefit will return to the Study Program and to the community. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir.H.Subaer Kanata |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

3.2. Name of Activity: E.2. Expanding the Capacity of the Basic Laboratory Courses: Laboratory I and Laboratory II (Including the Improvement of the Qualifications of the Laboratory Assistants).

Background: Basic laboratory courses (Laboratory I and II) provide 31 experiments in 4 (four) laboratories, i.e. Basic Circuit Laboratory (9 exp.), Radio Telecommunication and Microwave Laboratory (10 exp.), Computer Software Laboratory (3 exp.), and Electrical Machines Laboratory (6 exp.) [see Appendix III.37 on page III-Ap-20]. These laboratory courses are very crowded, they are always conducted in 1 or 2 shifts per day by a group of 4 to 10 students per experiment using very limited modules and equipment – both in terms of the quantity and quality – and limited laboratory spaces experiments. The facilities were intended to accommodate only 100 admitted student per year, but since 1995 have been forced to accept three times the capacity. Moreover, the schedule of those laboratory courses is very tight causing Laboratory I and III (odd semester) and Laboratory II and IV (even semester) unable to be committed at the same time, as the consequence of that, supported equipments should be used almost continuously. The laboratory courses do not serve their purpose to provide students with practical experiences because they have very short time in the laboratory. Upgrading and repairing the number of modules, equipment and renovation and reposition of the room's function will enable the provision of laboratory courses to reach an almost ideal circumstances, for instance: the lab courses can be conducted by 1 shift/day, 3 students/group, and Laboratory I and III (odd semester) and Laboratory II and IV (odd semester) can be conducted at the same time. This activity was originally planned to be implemented entirely in the first year of the project. The actual status of the activity at the end of the first year is as follows: Note: The sub-activities of this Activity E.2. is similar to those of Activity R.1.. The difference is in the laboratory courses taken care of. The Activity R.1. discussed previously was designed to update the course materials of advance Laboratory III and IV, while this Activity E.2. wss proposed to expand the capacity of basic Laboratory I and II. E.2.1. Assessing the existing laboratories condition, mainly in terms of organizational and management aspects, environmental and utilities setting, and the quality of laboratory course materials. The Term of Reference (TOR) of the Program Development related to this sub-activity E.2.1. has not been approved until the beginning of October 2003 when the draft of this report is written, but this sub-activity has indicated some progress to be reported here. The Person in Charge (PIC) of this Activity E.2., in cooperation with the PIC of Activity R.2. and R.1., has carried out a “Workshop on Curriculum of Electrical Engineering Study Program Development” along the year 2003. The workshop is planned to be held all year long – including a series of open discussions via the alumni mailing-list (see http://groups.yahoo.com/group/iatel-unhas/messages/ for details) in the Internet participated by alumni who mostly work in industry - to produce a renewed curriculum of the Study Program implemented in 2004. This new curriculum will accommodate the TPSDP plan to renew the basic laboratory courses Laboratory I and Laboratory II, which are the main targets of this Activity E.2. So far, the workshop has produced an initial draft of the new curriculum. E.2.2. Preparing the standard workplace and required utilities in the laboratories. The bidding process of the procurement of the laboratory furniture has been proceeding smoothly at the SPMU level and while this report is written, the bidding committee is still evaluating the bidding documents submitted by several bidders. The recommendation will be soon submitted to the CPMU. Concerning the civil works related to this Activity E.2., the bidding process is almost completed, the renovation of the laboratory building facilities is planned to begin in January 2004 at the latest. E.2.3. Repairing and renewing the existing experiment modules, instruments and parts. Expanding the capacity of the laboratories serving the Laboratory I and II courses. E.2.4. Commissioning test of the new laboratory equipment. The two sub-activities above are related to the procurement of the laboratory equipment implemented in the Year 1. The bidding process for the procurement of the equipment for the

To be continued in the next page ……

| Activity E.2. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Background (continued): -- first year – which has been combined with the procurement for the second year in an ICB package – still continues to proceed. E.2.5. Developing experiment guides and related laboratory assistant training materials. The TOR of this sub-activity still needs minor correction, however, this sub-activity has been partly implemented using other available resources. E.2.6. Implementing and evaluating the updated experiment modules for Laboratory I and II courses This should be done after the delivery of the procured equipment, presumably early next year. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources required for year 2: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activity | Cost Components |  |  |  | Rp |  |  |  | US $ |  |  | Source of Funding |  |  |  |  |  |
| E.2.1. | Program Development |  |  |  | 0,00 |  |  |  |  |  |  | TPSDP |  |  | DRK |  |  |
| E.2.2. | Furniture |  |  |  | 0,00 (Implemented) |  |  |  |  |  |  | TPSDP |  |  |  |  |  |
|  | Civil Works |  |  |  | 57.165.000,00 |  |  |  |  |  |  | TPSDP |  |  | DRK |  |  |
| E.2.3. | Equipment |  |  |  | 0,00 (Implemented) |  |  |  | 0.00 (Implemented) |  |  | TPSDP |  |  |  |  |  |
| E.2.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.5. | Program Development |  |  |  | 6.000.000,00 |  |  |  |  |  |  |  |  |  | DRK |  |  |
| Total |  |  |  |  | 63.165.000,00 |  |  |  | 0.00 |  |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activity |  | Yr 1 |  |  |  |  |  | Yr 2 |  |  |  |  |  |  |  |  |  |
| E.2.1. |  | Delayed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.6. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  | Baseline |  |  |  | Mid |  |  | Final |  |  |  |
| Number of students per-group |  |  |  |  |  |  | 4-10 |  |  |  | 3-6 |  |  | 2-4 |  |  |  |
| Repaired, updated and renewed experiment modules and test instruments |  |  |  |  |  |  | 0% |  |  |  | 50% |  |  | 100% |  |  |  |
| Sustainability : Staff, students and laboratory assistants are expected to maintain and develop these basic laboratory in the long run. They should be self-sufficient in repair and maintenance. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. H.A. Rasjid Muhammad |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

4. Access and Equity

| Code | Name of Activity |  |
| --- | --- | --- |
| AE. | Improving the access and equity of the Study Program for students originated from remote areas in the Eastern Region of Indonesia and other less economically advantageous communities. |  |
|  | AE.1 | Recruiting and Socializing in Remote Areas in the Region of Indonesia |
|  | AE.2. | Developing a Matriculation Program for New Students from Remote Areas |
|  | AE.3 | Administering and Mediating Student Financial Aids Programs |

4.1. Name of Activity:  AE. Improving the access and equity of the Study Program for students originated from remote areas in the Eastern Region of Indonesia and other less economically advantageous communities.

| Background: The function of a higher education institution is to accommodate the needs of the people to acquire the skills and knowledge. This should include the people from the less economically advantageous and from remote areas. It is a well known fact that there is a significant gap in the mastery of basic sciences between potential students from suburb and rural area, from down-town and remote places. This gap has made a inequality of opportunity among people to access a higher institution. This activity is not funded by TPSDP sources. The status at the end of first year term of the project is as follows: Note: This Activity AE has been taken care of at the university level under a program called “Partnership Program” (Program Kemitraan). In this program, the university - in cooperation with the surrounding county governments (Pemerintah Kabupaten) - is recruiting new students from various area in the region. Those new students are admitted without having to participate in the traditional admission test (SPMB a.k.a. UMPTN). AE.1. Recruiting and Socializing in Remote Areas in the Eastern Region of Indonesia AE.2. Developing a Matriculation Program for New Students from Remote Areas AE.3. Administering and Mediating Student Financial Aids Programs The Study Program should be involved in the recruitment process of “Program Kemitraan”. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Resources required for year 2: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Cost Components |  |  |  | Rp. |  |  |  |  |  | Funding Source |  |  |
| AE.1., 2 and 3 |  | Program Development |  |  |  | At Cost |  |  |  |  |  | Others |  |  |
| Implementation Schedule (By Quarter) : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Yr 1 |  |  |  |  |  |  | Yr 2 |  |  |  |  |  |  |
| AE.1. | Taken care of by the university |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AE.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AE.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  | Baseline |  |  | Mid |  |  | Final |  |
| Percentage of students admitted from remote areas |  |  |  |  |  |  | No data |  |  | 5% |  |  | 10% |  |
| Academic performance of matriculation program participants (average first year GPA) |  |  |  |  |  |  | No data |  |  | 2.75 |  |  | 3.00 |  |
| Number of fellowships for students from remote area |  |  |  |  |  |  | 0 |  |  | 4 |  |  | 8 |  |
| Sustainability: At the end of the project, it is expected that co-operations with the external parties such as provincial governments, NGOs, companies, alumni, professional association, etc. to take care of this program will continue. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. Gassing, MT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

5. Internal Management And Organization

| Code | Name of Activity |  |
| --- | --- | --- |
| IMO | Improving the Department’s administration system |  |
|  | IMO.1. | Establishing the Study Program’s Management Information System and Database |
|  | IMO.2. | Establishing an Effective Teaching-Learning Process Monitoring and Evaluation System |

5.1. Name of Activity: IMO Improving the Department’s administration system

| Background: One of the problems faced by the Study Program is in handling and processing data for academics and students administration needs. Only 5 (five) department administrative staffs daily serve the needs of around 1000 students. Data lost, improper handling and inaccuracy are not uncommon problems. The status at the end of the first year is as follows: Note: The resources required for this Activity are all in the form of procurement of equipment included in the Year 1 (combined with Year 2) ICB package, whose bidding process is still proceeding. The expected date of delivery is early next year. On the other hand, at the university level, an ISS TPSDP project entitled “Management Information Systems” (MIS) is in progress. According to the Project Coordinator of the MIS Project, the Study Program will be one of the participating sites of his project. Any development of information system in the Study Program should be under the MIS project coordination . IMO.1. Establishing the Study Program’s Management Information System and Database The Study Program has developed a computer network connecting all laboratories and offices. This network has a 24 hour access to the Internet, hence, students and academic staff can utilize the Internet for educational purpose. Moreover, the Study Program has built a database system that stores the data of students including their profiles, taken SKS and their current GPA. This database system is planned to be connected later on to the university-wide network developed by the MIS project. IMO.2. Establishing an Effective Teaching-Learning Process Monitoring and Evaluation System So far, the Study Program has implemented a teaching-learning process monitoring system (limited to the attendance record of both lecturers and students) and the result of monitoring is posted weekly on the announcement board. At the end of the semester, the Study Program is planning to evaluate the teaching-learning process based on the result of monitoring. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Resources required for year 2 : |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity | Cost Components |  |  |  |  | Rp |  |  |  |  | Funding Source |  |  |
| IMO.1. | Equipment |  |  |  |  | 0,00 (Implemented) |  |  |  |  | TPSDP |  |  |
| IMO.2. | Equipment |  |  |  |  | 0,00 (Implemented) |  |  |  |  | TPSDP |  |  |
|  | TOTAL: |  |  |  |  | 0,00 |  |  |  |  |  |  |  |
| Implementation Schedule (By Quarter) : |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Yr 1 |  |  |  |  |  | Yr 2 |  |  |  |  |  |  |
| IMO.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IMO.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  | Baseline |  |  |  | Mid |  |  | Final |  |
| Service time |  |  |  |  | 1 day |  |  |  |  |  |  | 5 minutes |  |
| Data Archive |  |  |  |  | 14 days |  |  |  |  |  |  | Every Minute |  |
| Monitoring and Evaluation |  |  |  |  | Non available |  |  |  |  |  |  | Available |  |
| Sustainability : Students participation in system maintenance and development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person in charge: Ir. Indra Jaya Mansyur, MT |  |  |  |  |  |  |  |  |  |  |  |  |  |

Chapter 2.3. The SECOND YEAR IMPLEMENTATION PLAN

2.3.1. PROJECT ORGANIZATION

The organizational set-up of the Project will reflect the on-going process that has been started since the preparation of the Self-Evaluation Report of the TPSDP Batch 1 in the year 2000. The structure of the organization is clearly described in Figure II-2. There are 11 (eleven) Persons in Charge, each one for each activity. Those Persons in Charge produced the list of sub-activities to improve RAISE++ as elaborated previously in Chapter 2.2, so it is clear that they have been involved since the planning stages of this project.

Quality Assurance

Dr. Ir. H. Nadjamuddin Harun, MS

Prof. Dr. Ir. H.M. Arief, Dipl.Ing.

|  |  | The Study Program Project Coordinator Dr.Ir.H. Rhiza S. Sadjad, MSEE |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Project Secretary: Muhammad Niswar, ST, MIT |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  |  |  |  |  | PERSONS IN CHARGE: |  |  |
| R.1. Advance Laboratory Courses Update |  |  |  |  |  |  |  |  |  | Ir. Hj. Nien K. Nauman |  |  |
| R.2. Industrial Relation Programs |  |  |  |  |  |  |  |  |  | Ir. A. Toyib Rahardjo, M.Sc |  |  |
| R.3. NEW Teaching/Laboratory Courses Development |  |  |  |  |  |  |  |  |  | Ir. H. Tahir Ali |  |  |
| R.4. Student Co-Curricular Activities |  |  |  |  |  |  |  |  |  | Elyas Palentei, ST, M.Eng.*) |  |  |
| R.5. Staff Composition and Qualification Improvement |  |  |  |  |  |  |  |  |  | Prof. Dr. Ir. M. Tola, M.Eng. |  |  |
| A.1. Departmental Meeting and Dialogue |  |  |  |  |  |  |  |  |  | Ir. Zaenab Muslimin |  |  |
| A.2. Student’s Learning and Reading Skills Enhancement |  |  |  |  |  |  |  |  |  | Ir. Hj. Sri Mawar Said |  |  |
| E.1. Classroom Teaching-Learning Process Improvement |  |  |  |  |  |  |  |  |  | Ir. H. Subaer Kanata |  |  |
| E.2. Basic Laboratory Courses Expansion and Quality Improvement |  |  |  |  |  |  |  |  |  | Ir. H.A. Rasjid Muhammad |  |  |
| AE Remote Area “Reaching-Out” Program |  |  |  |  |  |  |  |  |  | Ir. Gassing, MT |  |  |
| IMO Department’s MIS and Database Development |  |  |  |  |  |  |  |  |  | Ir. Indra Jaya Mansyur, MT |  |  |
|  |  |  |  | *) To be replaced (Ph.D. candidate, leaving to Australia) |  |  |  |  |  |  |  |  |
|  | Figure II-2 The Organizational Structure of the Project at the Study Program level |  |  |  |  |  |  |  |  |  |  |  |

The person who is now the Chairman of the Task Force - that was formed by the Department to take care of the preparation of the Study Program’s Self Evaluation Report and the TPSDP Sub-Project Proposal, both Batch 1 and Batch 2 - will lead the organizational structure of the project at the Study Program level as the Project Coordinator. He will be responsible also as a contact person or representative of the Study Program at the University level. A Project Secretary helps him to take care of the administrative aspects of the project.

Since this project is an activity-based project then the main parts of the project organization are the Persons in Charge of all activities. All the persons in charge have been involved at the preparation stage of this Sub-Project Proposal. They started by writing the background and the rationale of each activity they are going to take care of whenever the project is granted. After those were clear, then they continued with the planning of the activities, including preparing the budget allocation plan. The only change of the organization structure of the first year term is the Person in Charge for Activity R.4.. Mr. Elyas Palantei, S.T., M.Eng. is expected to leave at the end of January 2004 to Australia.

2.3.2. ACTIVITY and SCHEDULING

Details of all planned activities in this project have been thoroughly discussed in previous sections in terms of the sub-activities. Basically at the second year term of the implementation of this project, most activities will be scheduled as the continuation of the activities originally planned to be implemented at the first year term. The activities that were already planned to be implemented in the second year term of the project are to be implemented as planned.

2.3.3. MONITORING and EVALUATION MECHANISM

The principle of the "Total Quality Management" (TQM) will be applied in all monitoring and evaluation mechanism of this project. It means that all monitoring and evaluation mechanism will be embedded in all sub-activities without exception.

There are at least 2 (two) categories of monitoring activities, namely the monitoring of the physical implementation of the proposed project itself, and the monitoring of the educational process as the result of the project. The latter (including monitoring of the laboratory activities, classroom activities, the teaching and learning process, student extra-curricular and co-curricular activities, etc.) will become parts of the Activity IMO (see page Revised-SPP II-17), and the follow-up of this activity will be taken care of by Activity E.1. (see Revised SPP page II-12). The results of this monitoring mechanism will be the mid-term and the final-term data to compute the performance indicators discussed previously.

A built-in mechanism will be applied to all activities led by each Person in Charge, including the procurement process of all laboratory equipment and experiment modules, the implementation of staff development sub-activities, administration, civil works and teaching facilities improvement. All procurement within the project plan should be monitored closely. This will include the process of annual budget revisions, the preparation of bidding documents, the bidder selection, up to testing and commissioning and after sales services and user training if necessary. The monitoring mechanism for all civil works implementation, for instance, should include the selection of building consultants, the physical design and cost-estimation, the bidding and selection of contractors, the implementation supervisory activities and commissioning.

A continuous (at least weekly, or more often if necessary) evaluation mechanism should be applied to the project implementation. All Persons in Charge should prepare their reports at least in a weekly basis to the Project Coordinator. All performance indicators should be compiled every semester and presented in a general staff meeting to determine any progress made. The fourth general staff meeting will be the mid-term project. All mid-term performance targets will be evaluated to determine whether the project should be continued to the next half term or just terminated there. If the project continues, then over-all revisions should be made to secure the achievement of all final performance targets and the sustainability of this project.

At the end of the fourth year of the project implementation, a thorough evaluation should be made in order to guarantee the public accountability of this project. This evaluation may have to involve all stakeholders, including the students' parental-representatives, the industrial world, the local and central government, and all other concerned parties. The Study Program may be planning to implement the international standard of higher education accreditation systems - such as the ABET criteria - at this stage.  The final evaluation will be the commencement of the end of the project and at the same time it will become a mechanism to build the commitment to work together for the long future of the Study Program. The Quality Assurance Team will closely supervise all those mechanisms.

Chapter 2.4. PROPOSED BUDGET

The implementation of the first year budget plan is shown in Figure II-3. More than 74 % of the total budget has been committed, the rest is supposed to be carried out to the second year.

Figure II-3

Implementation of the Proposed Budget Plan 2003 (in Rupiah)

Figure II-4 shows the budget plan for the second year term, which is detailed in terms of activities in Figure II-5.

.

Figure II-4

Proposed Budget for the Second Year Term 2004

Figure II-5

Proposed Budget for the Second Year Term 2004 (per-Activity)