###### Chapter III: Strengthening The Existing Study Programs

###### Chapter 3.1.1. Electrical Engineering Study Program

A. BACKGROUND

After it moved to the new campus with all new facilities in 1985, the Electrical Engineering Study Program of Hasanuddin University, Makassar (occasionally in this Chapter is referred to as "the Study Program") stated its vision and mission as follows:

The Study Program’s VISION is to be the Center of Development and Implementation of the Electrical Engineering Technology and to become a leading engineering education institution in the country. Its MISSION is to graduate professionals who are able to advance their own technical skills and knowledge, and to adopt the development of technology.

The mission was carried out very well especially when a 10-year-long project called the Engineering Acceleration Project (Proyek Percepatan Insinyur, PPI) was launched in 1986. However; since the project ended in 1996, the Study Program has been constantly suffering from the quality degradation. The vision has become so blurring and the mission is so impossible; so only its long history, the high quality it used to have and the perseverance of all staffs that have helped maintaining the Study Program's performance up to a certain level. Without a careful rescue plan, the Self-Evaluation Report has shown that the performance will not last long in the future.

As has been concluded from the SWOT and Force-Field Analysis in Revised-Self Evaluation Report (SER) Chapter III.B.1. (see page III.B.1-1 to III.B.1-4 of the Revised Sub-Project Proposal), there are 3 (three) major obstacles - among others - that are supposed to be controllable factors of  improving the quality of the Study Program, i.e.:

- The obsolescence of the laboratory equipment and laboratory course materials for advance laboratory courses,

- Inadequate quantity of the laboratory equipment and laboratory course materials for basic laboratory courses, and

- The problem of teaching staff composition and qualification.

Those 3 (three) main issues above are the core of problems the Study Program is facing, and have been translated into strategic issues to develop several proposed activities (see Strategic Issues in Chapter III.B.2 Revised Inception Plan on page III.B.2-1 of the Revised Sub-Project Proposal) that will be detailed in the following Chapter 3.1.2. IMPROVING RAISE++ .

B. THE STRATEGY AND THE OBJECTIVE

All the staff's high motivation to work together is the primary asset the Study Program has. This has been shown by the staff's response to the announcement of this project (see Appendix III.2 on page III-Ap-3 of the Revised Sub-Project Proposal). At all socialization events mentioned, 90% of the staff were in attendance. Even in the very early stage of the Self-Evaluation Report preparation for the TPSDP Batch 1, the process has reflected the firm commitment to come together. This should be carried on to the next stage, i.e. the preparation of this Sub-Project Proposal of the TPSDP Batch 2 and - if the project is granted - to the implementation of the project. The main strategy is to harvest the participation of all components to produce a list of activities - not a "list of wants" or a "procurement list" - as early as possible. For instance, on the issues regarding the laboratories, each laboratory was asked to start by preparing the list of experiments for laboratory courses, then based on each experiment, a list of equipment required was developed (see Appendix II.H.I to IV on page II-Ap-11 to 20 of the Revised Sub-Project Proposal for details). No equipment procurement is supposed to be proposed by any laboratory without a proposed experiment for a laboratory course.

Implementation Plan

R

A

I

S

E

+

+

Performance Targets

Proposed Budget

PROJECT BENEFIT

and ECONOMIC ANALYSIS

SE-REPORT

SWOT

Force-Field

Analysis

R.1.

R.2.

R.3.

R.4.

R.5.

A.1.

A.2.

E.1.

E.2.

AE

IMO

PROPOSED ACTIVITIES

STRATEGIC

ISSUES

Figure III-1 Line of Thought of the Preparation of the Sub-Project Proposal

Figure III-1 shows the line of thought in preparing this Sub-Project Proposal. After a long series of discussions on the results of the self-evaluation process, including the discussions with the TPSDP reviewers during the site-visit and negotiations, the Study Program came up with 11 (eleven) proposed activities:

- To improve relevance: 5 (five) activities

- To improve academic atmosphere: 2 (two) activities

- To improve efficiency and productivity: 2 (two) activities

- To improve access and equity: 1 (one) activity

- To improve internal management and organization: 1 (one) activity

[Note: In the previous documents of this Sub-Project, one may notice that there used to be 4 (four) activities to improve relevance and 3 (three) activities to improve efficiency and productivity. After a long and intensive discussion, it was decided to change the main aspect of the activity of improving the staff qualification (activity E.3.) from improving the efficiency and productivity to improving the relevance].

C. PERFORMANCE INDICATOR

The general outcome of those eleven proposed activities will be quality improvements that are indicated by performance targets as shown in Table III-1. The increase of average NEM, for instance, is believed to be influenced mainly by improving access and equity as well as the quality enhancement as the consequences of the implementation of other activities. Hence, this indicator is omitted.

### Table III-1 Main Indicators for performance targets presented in their frequency ranges

| Indicator | Baseline | Midterm | Final |
| --- | --- | --- | --- |
|  | (%) |  |  |
| GPA |  |  |  |
| Percentage of graduates with GPA > 3.0 | 40.79 | 46.50 | 50.00 |
| Percentage of graduates with GPA between 2.5 and 3.0 | 56.35 | 52.50 | 49.50 |
| Percentage of graduates with GPA < 2.5 | 2.86 | 1.00 | 0.50 |
| TOEFL SCORE |  |  |  |
| Percentage of students with TOEFL score > 500 | 5.53 | 16.60 | 37.80 |
| Percentage of students with TOEFL score between 400 and 500 | 38.13 | 54.80 | 57.20 |
| Percentage of students with TOEFL score < 400 | 56.34 | 28.60 | 5.00 |
| LENGTH OF STUDY |  |  |  |
| Percentage of graduates with length of study > 5 years | 77.64 | 50.80 | 19.00 |
| Percentage of graduates with length of study between 4.5 and 5 years | 19.14 | 30.00 | 35.50 |
| Percentage of graduates with length of study < 4.5 years | 3.22 | 19.20 | 45.50 |
| WAITING TIME FOR THE FIRST JOB |  |  |  |
| Percentage of graduates who waited for their first jobs within 6 months | 13.60 | 25.00 | 50.00 |
| Percentage of graduates who waited for their first jobs within 6 to 11 months | 51.20 | 45.00 | 40.00 |
| Percentage of graduates who waited for their first jobs for more than 11 months | 35.20 | 30.00 | 10.00 |
| FIRST JOB MONTHLY SALARY |  |  |  |
| Percentage of graduates whose first job monthly salary > Rp. 1.2 millions | 7.20 | 45.00 | 70.00 |
| Percentage of graduates whose first job monthly salary between Rp. 0.6 and 1.2 millions | 50.40 | 35.00 | 20.00 |
| Percentage of graduates whose first job monthly salary < Rp. 0.6 millions | 42.40 | 20.00 | 10.00 |

Activities to improve efficiency and productivity will be directly and indirectly indicated by the increase of the graduates’ average GPA. These activities are also supposed to shorten the length of study as indicated by the average length of study. The average TOEFL scores, the graduates’ waiting time before getting the first job and the first job salary will indicate the improvement in relevance.

All proposed activities in this project are generally planned to boost most of the performance target indicators to yield a better result. Previously the performance targets were presented by the average values of the main indicators as suggested by the Guidelines. But, the incremental increase of the performance indicators have seemed “too modest” in comparison to the amount of capital invested in this project, and the average values may not really represent the actual condition. With a large student population, the presentation of the main indicators of the performance target in their frequency ranges or distribution – as presented in Table III-1 - will give a better perspective.

The average of NEM score's baseline data is 47.1 with standard of deviation 6.0. Improving the relevance (R) of the educational process to the job-market and industrial needs can increase the NEM scores of the admitted students. Naturally, when the relevance (R) is improving, the number of applicants to the Study Program will increase, resulting tougher competition at the new student admittance. A larger number of new students with high NEM scores will be admitted, and this will affect the academic atmosphere (A) at the Study Program. Another way of achieving this target is by creating some campaign programs about the Study Program to the High Schools at the surrounding area.

The average of graduates' GPA taken from the last 4 (four) academic years is 2.94, distributed as shown in Table III-1. It is targeted to improve the distribution. This performance target indicates the improvement of the academic atmosphere (A) (e.g. by upgrading teaching facilities and classroom-facilities, developing lecturers' teaching skills and students' learning skills and creating competitiveness among students).

Encouraging students to read more reference books in English and urging lecturers to use English in their classes - among others - will help to improve students' English proficiency indicated by their TOEFL scores. This is a part of activities that will improve the relevance (R) of the Study Program. At the beginning of the project, the average of TOEFL scores of students whose credit earnings are 120 sks or more is 403, this is fairly high, considering that the students did not make any preparation due to the very short notice before the test. The distribution of the TOEFL scores is targeted to be improved by the implementation of a special program proposed as one of the student co-curricular activities (see  sub-activity R.4.1).

The average graduates' length of study is 5.67 years at the beginning of the project. This can be shortened at the end of project, and the distribution is expected to be better, by improving the  efficiency and productivity (E) of the educational process.  This target can be achieved by improving the teaching and learning process (see Activity E.1.) and to create more effective laboratory scheduling. In fact, the length of study has 2 (two) components, i.e. the classroom-courses study time and the final undergraduate project (skripsi) time. In order reduce the latter, the intensive interaction between supervisors and students should be enforced and the adequate laboratory equipment should be available. The baseline data of standard deviation can be reduced by continuous academic advisors' supervising on their students' study program planning and monitoring in order to detect the weak students. Special attention must be given to this kind of students to push them to study harder. Another factor that could influence the length of study time was the student academic leaves, which in most cases were caused by the lack of funding. Students' involvement in research and teaching grant activities are expected to be one of the possible remedies to reduce student academic leaves. An aggressive program to collect student scholarships (e.g. from alumni, industry, local and regional government) should be planned to help this problem out.

Survey and direct interviews have shown that the waiting time to get the first job is 11 months in average, which is a rather long time. This indicator is influenced heavily by the unemployment rate in the market, which is closely related to the country economic situation. Assuming a better economic growth, then additional efforts to improve the students' English proficiency and computer skills, as well as continuous adjustments of the curriculum toward industrial world orientation, will give the graduates a strong penetration to the job market.  This will automatically reduce the waiting time to the first job. It is expected that the waiting time to get the first job will be reduced and the distribution will look better also at the end of the project.

Table II-2.  Additional indicators for performance targets

| Indicator | Baseline | Midterm | Final |
| --- | --- | --- | --- |
| Ratio between applicants and admissions | 9.3% | 9% | 8% |
| Average duration of completing skripsi | 9 months | 8 months | 6 months |
| Average active students with GPA less than 2.5 | 4.8% | 4.6% | 4.3% |
| Average drop out students | 1.66% | 1.60% | 1.50% |
| Productivity (Graduates/Population) | 11.08% | 15.5% | 17% |
| Average teachers attendance at classroom | 85% | 87% | 90% |

The factors that have affected the graduates' first job salary, such as the national and local economic growth, were beyond the Study Program's scope of control, but improving the relevance (R) of the Study Program in many ways will give the competitive advantages to the graduates so that they could ask for a higher salary on their first jobs.

The Study Program was accredited C in 1998, and only recently it was up-graded to B. It is strongly believed that if all activities are implemented in the TPSDP according to the proposed plans, the Study Program will be accredited A.

Additional indicators as presented in Table III-2 are thought to be the direct impact of all proposed activities as described in details in the following Chapter 3.1.2. IMPROVING RAISE++. In addition to that, each proposed activity has its own performance indicators also.

Chapter 3.1.2. Improving RAISE++

General Report

The lack of coordination at the university level reported in the Year 1 Annual Report has continued to the second year term of the project, even seemed to get worse in many aspects. The Study Program Project Coordinator was only invited twice to SPMU meetings, i.e. in the preparation of the SIP in the beginning of the second year term, and in the preparation of this Annual Report. The SPMU Director always refused to communicate with the Project Coordinator. Throughout the year, the SPMU Director made many important decisions related to the Study Program activities alone by himself, without even giving the Project Coordinator a telephone call, let alone giving him a chance to discuss the matter deeply. The SPMU Director’s management style has been seen as the main reason – among others – of the Study Program’s very low performance at the second year term of the project.

The worst among many cases of the Study Program’s non-performing project implementation is the cancellation of overseas degree program participation – a Ph.D. candidacy – due to a contract violation made by the project management. The problem of internal management at the university level has also caused the lack of operational funds at the Study Program level. One of the consequences is the lack of funding to support a tracer study to evaluate the graduates. This explains the non-availability of the two related main performance indicators, i.e. the waiting time before getting the first job and the first job’s monthly salary, in this report. The problem of internal management at the university level has also caused the stagnation of the bidding process of the procurement of equipment and teaching materials both for Year 1 and Year 2, the International Competitive Bidding (ICB) as well as the International Shopping (IS). The submission of the Term of References (TORs) of the Program Development has been very late because the SPMU has made no clear directive to the Persons of Charge (PICs) of the activities in how to create a good TOR.

Despite the fact that the SPMU has never been trying to solve the internal management problem at the university level, the Study Program continuously puts all efforts to maintain the project operation. Throughout the second year, 4 (four) Ph.D. candidates and 1 (one) Masters candidate have left abroad as the implementation of the overseas degree programs. In addition to that, 2 (two) domestic degree programs for Masters have also been implemented as planned. The staff development program has also successfully implemented 1 (one) domestic (another one is in progress) and 2 (two) overseas non-degree training programs. The participation in the competition to receive the research, teaching and student grants has remained very high in the second year, indicating the enthusiasm of the staff to get involved in this project. The renovation of the building facilities has been successfully completed as the civil work of the first year term, and the bidding process of the second year term is in progress.

The procurement of equipment has been anticipated by a major change in the format of the laboratory courses. Consequently, there should be a major modification in the curriculum. Several workshops have been held to work this out, and the Study Program has produced a proposal to split its curriculum into 4 (four) new Study Programs. The proposal has been submitted to the university senate at the end of 2004. The new curriculum is expected to be implemented in 2005.

The negotiation at the beginning of the second year term has reached an agrrement to simplify the implementation of the 12 (twelve) Program Developments into 4 (four) groups of Program Developments, with each group only requires 1 (one) submitted and approved TOR. The 4 (four) groups of Program Developments are listed as the following::

- Group of Program Developments related to student activities, including sub-activities R.4.1, R.4.2, R.4.4 and A.2.5.

- Group of Program Developments  related to curriculum development, including sub-activities R.1.1, R.1.5 and E.2.5

- Group of Program Developments related to industrial linkages including sub-activities R.2.1, R.2.2 and R.2.3.

- Group of Program Development related to teaching improvement activities, including sub-activities E.2 and A.1.5

However, this report is organized according to the list of 11 (eleven) RAISE++ activities, with all the 12 (twelve) Program Developments described within the 11 (eleven) activities.

1. Relevance

| Code | Name of Activity |  |
| --- | --- | --- |
| R.1. | Improving, updating and renewing the quality of the modules, materials and delivery of the advance laboratory courses: Laboratory III and Laboratory IV (including the improvement of the qualifications of the Laboratory Assistants). |  |
| R.2. | Enhancing the industrial relation in the surrounding area: |  |
|  | R.2.1. | Developing Apprenticeship Programs in Industry |
|  | R.2.2. | Developing Curriculum and Syllabus with a close cooperation with Industry |
|  | R.2.3. | Developing Industrial Training and Studies Programs |
| R.3. | Developing NEW Classroom/Laboratory Teaching Materials: |  |
|  | R.3.1. | Cellular Telecommunication |
|  | R.3.2. | CISCO Certified Network Associate Training Center Development |
| R.4. | Enhancing Students’ Co-Curricular Activities and Additional Skills and Competencies: |  |
|  | R.4.1. | English Competency: Technical and Engineering Writing Skills |
|  | R.4.2. | Computer and Internet Skills |
|  | R.4.3. | Student Electrical Workshop |
|  | R.4.4. | Students’ Personality Enhancement and Entrepreneurship Training Programs |
| R.5. | Improving the Teaching Staff’s academic qualifications and the Administrative Staff’s competency and skills: |  |
|  | R.5.1. | Domestic and Overseas Degree Programs S2, S3 |
|  | R.5.2. | Local Vocational Trainings for Administrative Staffs and Laboratory Technicians |
|  | R.5.3. | International Conferences and Domestic Special Non-Degree Programs |

1.1. Name of Activity: R.1. Improving, updating and renewing the quality of the modules, materials and delivery of the advance laboratory courses: Laboratory III and Laboratory IV (including the improvement of the Laboratory Assistants qualifications).

a. Description and objectives: The structure of curriculum requires advance laboratory courses Laboratory III and Laboratory IV to be taken at the fifth and the sixth semester by the students of different Sub-Study Programs in different 11 (eleven) laboratories. These two laboratory courses are designed to support the core and advance courses provided by each Sub-Study Program (see Chapter III.1.B. Section 11 Curriculum on page III.B.1-16 of the Revised Sub-Project Proposal). There has been no serious updating of both laboratory teaching materials and laboratory equipment since 15 years ago when the Study Program moved from the old campus. The obsolescence of both the teaching materials and the equipment is apparent, which makes the laboratory courses irrelevant to the rapid progress of electrical engineering technology as well as the demand of the job-market. Lack of sufficient funding to maintain and update old equipment has made most laboratory equipment and instruments are not functioning appropriately as they are supposed to be.

To be continued in the next page ……

| Activity R.1. (continued) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| a. Description and objectives (cont’d): Upgrading, repairing and updating laboratory teaching materials in accordance with the rapid progress of electrical engineering technology will improve the competitiveness of the graduates These activities are necessary in order to develop the graduates’ technological and professional skills which are closely related to the job-market demand. The main objective of this activity is to improve the graduates’ competitiveness in the job-market. |  |  |  |  |  |
| Resources required: |  |  |  |  |  |
| Sub-activity | Cost Components | Rp | US $ | Source of Funding |  |
| R.1.1. | Program Development | 10.000.000,00 |  | TPSDP | DRK |
| R.1.2. | Furniture | 21.650.800,00 |  | TPSDP |  |
|  | Civil Works | 155.589.681,00 |  | TPSDP | DRK |
| R.1.3. | Equipment | 436.432.500,00 | 261,526.26 | TPSDP |  |
| R.1.4. |  |  |  |  |  |
| R.1.5. | Program Development | 10.000.000,00 |  | TPSDP |  |
|  | Total | 633.672.981,00 | 261,526.26 |  |  |

b. 1. Achievement (in general): The civil works of the first year term has been successfully implemented so that most laboratories have their new room lay-out to accommodate the laboratory courses. The bidding process for the second year term is in progress. The laboratory furniture ordered for the first year term of the project has also been delivered, and the bidding process for the second year term is also in progress. The department has produced the draft of a new curriculum planned to be implemented beginning in 2005, to split the study prgram into 4 (four) study programs. The draft has been submitted to the university senate to get an approval. In the new curriculum there is a major change in the format of laboratory courses. Separate courses Laboratory I, II, III and IV will be integrated into classroom courses. About 25 to 50% laboratory experiment modules – especially those which are relevant - have been repaired and refurbished to accommodate a special D3 program called “Partnership D3 Program for PT. TELKOM employees”. These modules are also used by the S1 students while waiting for the delivery of new equipment from TPSDP procurement. To sum up, performance indicators of this activity does not show any significant improvement so far because most sub-activities are difficult to be implemented without new equipment that the study program has proposed to be procured in this project. The bidding process for the procurement of laboratory equipment is not completed yet. However, since some laboratories have been renewed their experiment module, hence, there is a slight improvement in the indicator of repaired, updated & renewed experiment modules and test instrument about 25%. (This improvement, of course, still below the midterm target (50%)) b.2. Achievement (described per sub-activity): R.1.1. Assessing the existing laboratories condition, mainly in terms of organizational and management aspects, environmental and utilities setting, and the quality of laboratory course materials.

To be continued in the next page ……

Activity R.1. (continued)

b.2. Achievement (described per sub-activity) (cont’d, sub-activity R.1.1): The Term of Reference (TOR) of the Program Development related to this sub-activity R.1.1. is combined into the same TOR of Program Developments related to sub-activities R.1.5 and E.2.5 Unfortunately, until this report is written, the TOR has not been approved. However; this sub-activity has carried out a “Workshop on Curriculum of Electrical Engineering Study Program Development” along the year 2004. The workshop has formed a committee to reform the organizational and management aspect of the laboratory including mechanism to recruit the laboratory assistant, procedures to attending laboratory course for student and evaluation system for student. Two major changes of the curriculum that have been proposed are the split of the study program into 4 (four) study programs and the integration of laboratory courses into classroom courses. R.1.2. Preparing the standard workplace and required utilities in the laboratories. The procurement of the laboratory furniture for the first year term has been completed and now program study has been utilizing the furniture in laboratory classes. Concerning the civil works related to this Activity R.1., the renovation of the laboratory building facilities for the first year term has completed in March 2004, and the bidding process of the second year term is in progress. . R.1.3. Repairing and renewing the existing experiment modules, instruments and parts. At least two laboratories, namely: Basic Electrical Engineering Lab and Telecommunication Lab have renewed their experiment modules. Those experiment modules were renewed by D3 students from the “Partnership D3 Program for PT. TELKOM employees”. as parts of their final projects and fully supoorted by the program. The modules are also used by the regular S1 students for their laboratory courses. Figure III-2 Examples of Renewed Experiment Modules

To be continued in the next page ……

Activity R.1. (continued)

b.2. Achievement (described per sub-activity) (cont’d): R.1.4. Commissioning test of the new laboratory equipment. The two sub-activities above are related to the procurement of the laboratory equipment. Apparently, the bidding process for the procurement of the equipment for the second year has been combined with the procurement for the first year in an ICB package. The bidding committee has been recommended to CPMU regarding qualified bidder after the bidding process has proceed. Currently, we are waiting a decision from CPMU regarding the result of bidding process. Therefore the equipments are expected to be delivered at the end of this year (2004).

R.1.5. Developing experiment guides and related laboratory assistant training materials. The Term of Reference (TOR) of the Program Development related to this sub-activity R.1.5. is combined into the same TOR of Program Developments related to sub-activities R.1.1 and E.2.5 The TOR has not been approved, however; this sub-activity requires the delivery of the laboratory equipment in order to be implemented. Until this report is written, no laboratory equipment has been delivered. R.1.6. Implementing and evaluating the updated experiment modules for Laboratory III and IV courses This sub-activity is waiting for the delivery of the laboratory equipment.

c. Obstacles and actions taken to overcome: It is difficult to maintain the implementation of this activity on schedule, especially the sub-activity R.1.1., which requires the approval of the TOR of Program Development. The curriculum is necessarily modified before the renovation of the laboratory takes place, because all new laboratory courses should be in line with the curriculum. The process of restructuring the curriculum should involve many elements including academic staff, student, industries and government. To accommodate the interest of all elements, it requires a scheduling that fits with their time and this is quite difficult to set up. To deal with this problem, the use of internet media/mailing list is obviously very helpful. To discuss all topics related to the curriculum reform, many alumni working in various workplaces such as industries, government office and universities, have involved in an open and continuous discussion via mailing list (see http://groups.yahoo.com/group/iatel-unhas/messages/ for details). The delivery of the laboratory equipment is almost two years behind schedule, while most activities related to this Activity R.1. depend on the delivery. Since the procurement process of laboratory equipment is taken care of at the university level, then the internal management of SPMU should be fixed and improved to overcome this obstacle in the future.

d. Future Improvement Plan: The modification of the Program Development TOR for sub-activity R.1.1., R.1.5 and E.2.5 is to be submitted as soon as possible before the end of this year. The activity should be entirely re-scheduled to anticipate the procurement process of the furniture and equipment (ICB and IS), and the implementation of the civil works. The internal management of the SPMU should be fixed and improved.

To be continued in the next page ……

| Activity R.1. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| e. Impact of the activity: This activity has encouraged all staff to restructure the Study Program curriculum and syllabii, with the involvement and participation of all elements, especially alumni. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activity | Yr 1 |  |  |  | Yr 2 |  |  |  | Yr 3 |  |  |  |  |  | Yr 4 |  |  |  |  |  |
| R.1.1. |  |  |  | Re-scheduled, waiting for the delivery of the laboratory equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.6. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  |  | Baseline |  |  | Mid |  |  | Status |  |  | Final |  |
| Repaired, updated and renewed experiment modules and test instruments |  |  |  |  |  |  |  |  |  | 0% |  |  | 50% |  |  | 25-50% |  |  | 100% |  |
| Percentage of graduates working in their related fields |  |  |  |  |  |  |  |  |  | N/A |  |  | 40% |  |  | N/A |  |  | 60% |  |
| Person in charge: Ir. Hj. Nien K. Nauman |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1.2. Name of Activity: R.2. Enhancing the industrial relation in the surrounding area.

| a. Description and objectives: The Study Program has a very limited collaboration with local companies and industries yielding no solid linkage with the surrounding environment Job-market in most industries requires industrial experience in the recruitment of fresh graduates. There is an indication that a number of alumni were fired from work right after their probation. Many fresh graduates were not sufficiently confident to enter the job-market due to their very low experience in industrial world. The apprenticeship program designed in this activity will enhance the industrial relation of the Study Program that will be expanded into close collaboration with industry in curriculum development, training and studies. This activity will provide the students and the fresh graduates some industrial certifications that will be useful for entering the job-market. This activity will improve the fresh graduates’ self confidence in entering the job-market. Closer relation with industry will give a better shape of the curriculum design and course syllabi in terms of the industrial relevance. The objective of this activity is to establish a strong industrial apprenticeship program in order to strengthen the industrial relation of the Study Program and to enhance relevance in terms of industrial relation. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Resources required : |  |  |  |  |
| Sub-activity | Cost Components | Rp. | Funding Source |  |
| R.2.1. | Program Development | 30.000.000,00 | TPSDP | DRK |
| R.2.2. | Program Development | 19.000.000,00 | TPSDP | DRK |
| R.2.3. | Program Development | 16.666.666,33 | TPSDP | DRK |
|  | TOTAL | 65.666.666,33 | TPSDP | DRK |
| b. 1. Achievement (in general): The Study Program has successfully maintained its linkages with the industry. As an example, a one-day Workshop on “The Industrial Approach of Teaching Process Control & Instrumentation” was held in Hasanuddin University campus on May 1, 2004 by the Study |  |  |  |  |
| To be continued in the next page …… |  |  |  |  |

Activity R.2. (continued)

b. 1. Achievement (in general) (cont’d): Program for introducing the products of Syntek Group, Malaysia. This workshop was attended by the industrial practitioners from the surrounding area and has led to the submission of a USD 1.4 million project proposal to the Ministry of Energy and Natural Resources. Linkages with the industrial world are also established and maintained through channels created by the alumni network.

b. 2. Achievement (described per sub-activity): R.2.1. Developing Apprenticeship Programs in Industry. Several early contacts have been made with the surrounding industry to search for any opportunity to develop apprenticeship programs. The existing apprenticeship program with PT. INCO (a nickel mining industry in the area) is continuously maintained which is indicated by the attendance of one of our staff in an apprenticeship program at PT.INCO since August 2004. The TOR of this activity has been approved, however, there is a mistake in the total budget that should be reconfirmed with CPMU. R.2.2. Developing Curriculum and Syllabus with a close industrial cooperation The development of the new curriculum proposed by the Study Program to be implemented in 2005 has involved the industrial world informally through the channels of alumni. R.2.3. Developing Industrial Training and Studies Programs This sub-activity was scheduled to be implemented this year (Year 2). But since an opportunity to develop a relevant program came in the Year 1, this sub-activity was re-scheduled to begin earlier.. A "Training on the application of CYGNAL Microcontroller 51" by Ir.Irwan Tantu, MSc. was held on July 15-16, 2003 and attended by several students, mostly were laboratory assistants. This training had assisted the student to obtain more experiences, knowledge and skills in the application of microprocessor-based systems.The trainer is an alumnus of the Study Program, who is now an engineer at a computer software industry e-Production Solutions Inc. Houston Texas, USA

c. Obstacles and actions taken to overcome: Similar to other activities, the main obstacle is in the writing and the submission the TORs of the Program Development. The Year-2 Revised-SIP requires the submission of only 1 (one) TOR for the 3 (three) Program Developments related to this activity. Even the 1 (one) TOR has not been successfully approved untul this report is written. The lack of resources becomes apparent since none of the TORs were approved until beginning of October 2003. Actions taken to overcome this problem included the re-location of resources, available both from internal and external sources, and the re-schedulling of the sub-activities. Gathering information from graduates became burdensome to the Study Program because for some unknown reason none of the graduates has returned the questionaire to provide some information with regard to their salary and their waiting time to get their first jobs. However; the Study Program is planning to do another approach to get the information, if the necessary funding for the new approach is available from the budget.

d. Future Improvement Plan: To overcome the problem of writing the TOR to obtain the approval of Program Development, the project at the Study Program level is considering to conduct an intensive training or workshop attended by the PICs of all activities.

To be continued in the next page ……

| Activity R.2. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| e. Impact of the activity: the participation of the industrial world in the educational processs of the Study Program has evidently made a lot of positive impacts in broadening the perspectives of both students and staff on the real world. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activities | Yr 1 Re-scheduled |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  | Yr 4 |  |  |  |  |
| R.2.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.2.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.2.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  | Baseline |  |  |  | Mid |  |  |  | Status |  |  |  | Final |  |  |
| Percentage of alumni participating in the industrial apprenticeship program every graduation |  |  |  |  |  | 0% |  |  |  | 5% |  |  |  |  |  |  |  | 10% |  |  |
| Number of implemented Memorandum of Agreements (MOUs) on curriculum development with industries |  |  |  |  |  | N/A |  |  |  | 4 |  |  |  |  |  |  |  | 10 |  |  |
| Graduates’ waiting time before getting the first job |  |  |  |  |  | 11 months |  |  |  | 9 months |  |  |  |  |  |  |  | 5 months |  |  |
| First job salary (in Rupiahs) |  |  |  |  |  | Rp.712.400 |  |  |  | Rp.1.000.000 |  |  |  |  |  |  |  | Rp.1.500.000 |  |  |
| Person in charge: Ir. A. Toyib Rahardjo, M.Sc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1.3. Name of Activity: R.3. Developing NEW Classroom/Laboratory Teaching Materials

| ## a. Description and objectives: Due to the lack of adequate courses materials, laboratory equipment, access of information and advance technology skills; the alumni seem to lose the self-confidence, especially when they have to penetrate job market. With this activity, it is expected that the alumni will have more ability and knowledge to compete with others to get their jobs. The objective of this activity is to provide an opportunity for the lecturers and students to keep up with the current technological development. The alumni will have some opportunity to get world wide accepted certificates. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Resource Required: |  |  |  |  |  |
| Activity | Sub-Activity | Cost Component | Rp. | US$ | Funding Source |
| R 3.1 | R 3.1.1 | Program Dev. | At cost |  | R.2.1 |
|  | R 3.1.2 | Equipment |  | 21,230.00 | TPSDP |
|  | R 3.1.3 | Teaching Grant | 20.000.000,00 |  | TPSDP |
| ###### R.3.2. | R 3.2.1 | Staff Dev. | 41.250.000,00 |  | TPSDP + DRK |
|  | R 3.2.2 | Equipment |  | 13,700.00 | TPSDP |
| Total Cost |  |  | 61.250.000,00 | 34,930.00 |  |
| Note: The procurement process of equipment was scheduled to begin in the Year 2, but the ICB mechanism required to combine the procurement process with the Year 1, so it was expected that the equipment for this activity would have been available earlier in 2004. Unfortunately, until the end of 2004, no equipment has been delivered. |  |  |  |  |  |
| b. Achievement (described per sub-activity): (This activity is planned to be implemented in the third year). No achievement can be reported, only very early preparation has been made. R.3.1. Improving the knowledge and skills of staff and student in the progress of cellular technology development |  |  |  |  |  |
| To be continued in the next page …… |  |  |  |  |  |

| Activity R.3. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| : b. Achievement (described per sub-activity) (sub-activity R.3.1. cont’d) R.3.1.1: Improving the staff and students’ practical skills and knowledge through a related industrial apprenticeship program R.3.1.2: Preparing the required hardware and software, including instructional materials and experimental guides. R.3.1.3: Providing a competitive Teaching Grant for developing related laboratory course materials R.3.1.4: Implementing the laboratory course on cellular technology R.3.2. Acquiring the CISCO Certified Network Associates (CCNA): R.3.2.1: Instructors in-country training for CCNA. Candidates will be sent to an in-country CCNA Centre to participate in a two-month training program to obtain the Certificate of Instructor. R.3.2.2: Preparing the required hardware, software and Internet link necessary to establish the center. R 3.2.3: Developing the instructional materials for the training program R.3.2.4: Conducting the Local Assistants Training R.3.2.5: Implementing the regular training programs R.3.2.6: Conducting the standard tests for certification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c. Obstacles and actions taken to overcome: N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d. Future Improvement Plan: N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| e. Impact of the activity: N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity | Sub-Activity | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  |  | Yr 4 |  |  |  |  |
| R 3.1 | R 3.1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R 3.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R 3.1.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R.3.1.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.3.2. | R 3.2.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R 3.2.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R 3.2.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R 3.2.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R.3.2.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | R 3.2.6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity | Indicators |  |  |  |  |  |  | Baseline |  |  |  | Mid |  |  | Status |  |  |  | Final |  |  |
| R 3.1. | Number of Apprenticeship participants a. Staff b. Student |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | 0 |  |  |  | 2 |  |  | 1 |  |  |  | 5 persons |  |  |
|  |  |  |  |  |  |  |  | 0 |  |  |  | 8 |  |  |  |  |  |  | 16 persons |  |  |
|  | Number of graduates working in cellular technology |  |  |  |  |  |  | N/A |  |  |  | 1 |  |  | N/A |  |  |  | 5 persons |  |  |
| R 3.2. | Number of CCNA Instructors |  |  |  |  |  |  | 0 |  |  |  | 2 |  |  | 0 |  |  |  | 2 persons |  |  |
|  | Number of CCNA certified associates |  |  |  |  |  |  | 0 |  |  |  | 20 |  |  | 0 |  |  |  | 80 persons |  |  |
| Person in charge : Ir. H. Tahir Ali. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1.4. Name of Activity: R.4. Enhancing Students’ Co-Curricular Activities and Additional Skills and Competencies

| a. Description and objectives: A plan to enhance the student additional skills and competence should be proposed to improve the students' English competency, vocational, computer and internet skills. The establishment of student workshop facilities is also a part of this plan. From the polling (see the analysis at the end of Section 2 Environmental Setting, page III.B.1-8 and appendix III.10, page III-Ap-9 of the Revised Sub-Project Proposal) only about little bit more than 10 % of the students intended to work as entrepreneurs (8,71 %) or freelance workers (2,70 %) after they graduated. Regular programs/activities should be proposed to enhance the students' personality entrepreneurship as another part of the plan. These programs/activities will assist students to improve their skills in English, computer, internet, vocational, entrepreneurship, and self-personality. The objective of this activity is to produce graduates mastering English, computer, Internet, vocational, entrepreneurship, and self-personality that will enable them to compete in the job market |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Resources required : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Cost Components |  |  |  |  |  |  |  |  | Rp. |  |  |  |  | Funding Source |  |  |  |  |  |  |  |  |
| R.4.1. |  | Program Development |  |  |  |  |  |  |  |  | 14.600.000,00 |  |  |  |  | TPSDP + DRK |  |  |  |  |  |  |  |  |
| R.4.2. |  | Program Development |  |  |  |  |  |  |  |  | 40.000.000,00 |  |  |  |  | TPSDP + DRK |  |  |  |  |  |  |  |  |
| R.4.3. |  | Equipment |  |  |  |  |  |  |  |  | 31.875.000,00 |  |  |  |  | TPSDP |  |  |  |  |  |  |  |  |
|  |  | Instructional Material |  |  |  |  |  |  |  |  | 6.000.000,00 |  |  |  |  | TPSDP |  |  |  |  |  |  |  |  |
| R.4.4. |  | Program Development |  |  |  |  |  |  |  |  | 30.511.428,57 |  |  |  |  | TPSDP + DRK |  |  |  |  |  |  |  |  |
|  |  | TOTAL: |  |  |  |  |  |  |  |  | 122.986.428,57 |  |  |  |  | TPSDP |  |  |  |  |  |  |  |  |
| b. 1. Achievement (in general): In the first year term of the project, this activity was implemented successfully. The SIP of the second year term of the project required the submission of only 1 (one) TOR for the 3 (three) Program Developments R.4.1., R.4.2. and R.4.3., which is not completely approved yet until this report is written, However; most sub-activities have been implemented using other sources of fundings and support (not from the project) and also most performance indicators of this activity have shown an improvement. Students’ Average TOEFL Score has increased slightly from score of 403 (Baseline) to 426. The students have participated in the National Technical and Scientific Contests/Competition every year. For the second time, students have participated and passed the pre-qualification in the Indonesian Robotic Contest in the University of Indonesia, Depok 2004. This indicates a high motivation among students to conduct a research and development in the field of robotics. Furthermore, the percentage of Internet users among students has increased significantly after the establisment of additional Internet connection in the Faculty of Engineering in the mid-2004. All laboratories have Internet connectivity and students can access the Internet almost for free and search references related to their taken courseworks. While waiting for the delivery of the equipment, the Student Electrical and Electronic Workshop has been established and gets contracts to work in several projects around the campus. b. 2. Achievement (described per sub-activity): R.4.1. Developing regular programs/activities to improve the Students’ English Technical Writing and Conversational Skills The TOR of the Program Development related to this sub-activity was submitted together with the TOR of Program Developments related to sub-activities R.4.2. and R.4.2.4, but only the part proposing sub-activity R.4.2. has been approved. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To be continued in the next page |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity R.4. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b. 2. Achievement (described per sub-activity) (cont’d): R.4.2. Developing regular training programs/activities to improve the Students’ Computer and Internet Skills The part of TOR of the Program Development related to this sub-activity has been approved at the end of October 2004 and this activity is scheduled to be implemented before the end of the year of 2004.. R.4.3. Establishing the Student Electrical and Electronic Workshop to improve the students’ vocational skills. The equipment for this sub-activity was included in the Year 1 International Shopping (IS) bidding process, but has not been delivered until this report is written. However; the Workshop itself has been established by the students’ initiatives and the encouragement from the PIC of this activity. Several projects around the campus, including the installation of computer network and data-base, have been completed by this Workshop. R.4.4. Developing regular programs/activities to enhance Students’ Personality and Entrepreneurship The TOR of the Program Development related to this sub-activity was submitted together with the TOR of Program Developments related to sub-activities R.4.1. and R.4.2..2, but only the part proposing sub-activity R.4.2. has been approved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c. Obstacles and actions taken to overcome: The PIC of this activity, who has successfully implemented most sub-activities during the first year term of the project, has left the country to pursue his Ph.D. degree. The new PIC who succeeded him still needs sometime to adjust, so that the TOR for this activity was submitted only recently, and was partially approved by the CPMU. The rest of the TOR should be modified and re-submitted. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d. Future Improvement Plan: PIC should have submitted TOR earlier as well as CPMU should have given a feedback of TOR as soon as possible |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| e. Impact of the activity: The activity has improved the knowledge and a skills of the students as well as their motivation to conduct research and participation in the national contests related to their field. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Activity |  | Yr 1 |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  |  | Yr 4 |  |  |  |  |  |
| R.4.1.(Developt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.1.(Implemt.) |  |  |  |  |  | Partly re-scheduled |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.2.(Developt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.2.(Implemt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.4.(Developt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.4.(Implemt.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No. | Indicators |  |  |  |  |  |  |  | Baseline |  |  |  | Mid |  |  |  |  | Status |  |  | Final |  |  |  |
| 1 | TOEFL Score (average) |  |  |  |  |  |  |  | 403 |  |  |  | 450 |  |  |  |  |  |  |  | 500 |  |  |  |
| 2 | Percentage Internet users among students |  |  |  |  |  |  |  | no data |  |  |  | 50% |  |  |  |  |  |  |  | 95% |  |  |  |
| 3 | Participation in the National Technical and Scientific Contests/Competition |  |  |  |  |  |  |  | 0 |  |  |  | every other year |  |  |  |  | every year |  |  | every year |  |  |  |
| 4 | Percentage of students who are motivated to become entrepreneurs after graduations |  |  |  |  |  |  |  | < 10% |  |  |  | 30% |  |  |  |  |  |  |  | 40% |  |  |  |
| Person in charge: Faizal A. Samman, ST, MT. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1.5. Name of Activity: R.5. Improving the Teaching Staff’s academic qualifications and the Administrative Staff’s/Laboratory Technicians’ competency and skills

| a. Description and objectives: 32.61% of the Study Program’s teaching staff are above 50 years old, 84.78% are alumni, only 4 (four) Ph.D.’s and only 2 (two) of those four Ph.D.'s are Professors. Teaching loads are very high due to the student-to-lecturer ratio, which is about 36.7. The composition and the qualifications of the teaching staffs do not support efficient and productive teaching and learning process. More importantly, most of the lecturers did not have any academic experiences other than their own college experience many years back. Consequently, all teaching materials and methods delivered by those lecturers are irrelevant to the progress of the electrical engineering technology. This activity will include both degree training and non-degree training programs, both domestic and overseas, for the teaching staff as well as for the administrative staff and laboratory technicians. Hence, this activity will be directly beneficial to the teaching and learning process – both classroom and laboratory courses – due to the improvement of the staff qualification, competency and skills. The objective of this activity is mainly to increase the number of Master’s and Ph.D.-degree holders to make up the composition and the qualifications of the staff. In addition to the degree-program, the non-degree programs will provide a new academic experience for the staff that will surely enrich their teaching materials and methods. Non-degree programs for administrative staff and laboratory technicians will up-grade their skills and knowledge, so it will certainly improve their services to the study program |  |  |  |  |
| --- | --- | --- | --- | --- |
| Resources required: |  |  |  |  |
| Activity | Cost Components | Rp. | US $ | Funding Source |
| R.5.1. | Staff Development | 59.500.000,00 | 118,700.00 | TPSDP |
| R.5.2. | Staff Development | 36.950.000,00 |  | TPSDP |
| R.5.3. | Staff Development |  | 4,800.00 | TPSDP |
|  | TOTAL: | 96.450.000,00 | 123,500.00 |  |
| b.1. Achievement (in general): In the second year term of the project, this activity has taken most of the time and energy of the project management at the Study Program level due to the fact that the management at the higher level did not seem to give full support to the implementation of this activity. In fact, 1 (one) of the Ph.D. candidates for the Overseas Degree Program should be returned home because the project management at the higher level did not hesitate to make a contract violation. Inspite the unwillingness of the project management at the university level to encourage all candidates, apparently most part of this activity has been successfully implemented. Apparently, most performance indicators of this activity have shown improvement The number of Ph.D holders has increased considerably from 4 staffs (Baseline) to 6 staffs (above the mid-term project target of 5 staffs) and the number of Master degree holders has increased dramatically from 16 staffs (Baseline) to 35 staffs (which is actually the final year target). Even though there has been no paper published in any international journal as targetted, but 3 (three) papers have been published in international conference proceedings. |  |  |  |  |
| To be continued in the next page |  |  |  |  |

Activity R.5. (continued)

b.2. Achievement (described per sub-activity): R.5.1. Improving the staffs’ academic qualification by attending degree-programs both overseas and domestic. - The current status of Domestic Degree Training.Program: Detailed Specifications : Staff Development - Domestic Degree Training – year 2. Name of Candidates; Field Of Study, Degree; Status. Indra Bayu; Telecommunication, Masters; Third Semester at ITS. Indar Chaerah Gunadin; Electrical Systems, Masters; First Semester at ITS. 2. The current status of Overseas Degree Training. Program # Detailed Specifications : Staff Development - Overseas Degree Training – year 2. Name of Candidates; Field Of Study, Degree; Status. Tadjuddin Waris; Electrical Power, Ph.D.; Research at Curtin University, Perth WA, Australia in progress, completing the first semester. Samuel Panggalo; Telecommunication, Ph.D. Elyas Palantei; Telecommunication, Ph.D; Research at Griffith University, Brisbane , Australia in progress, completing the first semester. Hasniaty; Electrical System, Ph.D.; Research at UKM, Kualalumpur, Malaysia, in progress, completing the first semester. Wardi; Telecommunication, Masters; Completing English Language Bridging Program at the University of Southern Australia, Adelaide, Australia. R.5.2. Improving the administrative staffs’ and laboratory technicians’ knowledge and skills by attending local vocational training programs. This sub-activity was planned to be implemented in the first year term of the project, but the TOR was missing on the way to the CPMU, so then it was agreed to be rescheduled to the second year term. But until this report is written, there is no progress can be reported. This sub-activity will become necessary when the laboratory and office equipment are nearly delivered. R.5.3. Enlarging the staffs’ academic perspectives by attending international conferences and special domestic non-degree programs. Two staffs have presented their papers in two different international conferences in France and Malaysia. Dr.Salama Manjang has attended and presented his paper entitled “Performance of Seni-Rubber for HV Insulator under Natural Tropical Ageing” in the International Conference on Solid Die-electric (ICSD) 2004 in France. Prof. Muh. Tola has attended and presented his paper entitled “Implementation and Policy of Marine Pollution Prevention in Indonesia” in the 4th Regional Conference on Marine Technology 2004, Malaysia..The domestic non-degree program for staff has been implemented by the participation of Faizal A. Samman in “Workshop and Training Program on the Design of Low-Power High-Speed Digital VLSI“ (August 23 to November 5 2004) ITB Bandung and Baharuddin M. Diah in “PLC-based Industrial Automatization Training Program” in Bandung (for the latter, the application is in progress).

To be continued in the next page

| Activity R.5. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| c. Obstacles and actions taken to overcome: In almost all cases of both the overseas and the domestic degree training candidacy, obstacle came from the SPMU and CPMU’s “tight policy” on this matter that has given the hard time both to the project at the Study Program level and the candidates to prepare the implementation of the program. Furthermore, even after the candidates settled at their designated universities, they all complained that the SPMU did not put any effort to create a good way of communicating with them and healthy atmosphere to benefit their studies,. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d. Future Improvement Plan Both CPMU and SPMU should act more supportive and give more positive attitude toward the candidacy process of all proposed Degree Programs. SPMU should maintain well communication among candidates in order to help them to carry out their study successfully. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| e. Impact of the activity: There is no indication that the implementation of the activity in the first year has any impact to the Study Program except that there is a rather significant increasing of the staff’s working hour and complicated staff teaching placement, which is fully expected and anticipated since the beginning of the project.. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Yr 1 |  |  |  |  | Yr 2 |  |  |  |  |  |  | Yr 3 |  |  |  |  |  | Yr 4 |  |  |  |  |  |  |
| R.5.1. | S3 (overseas) |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |
|  | S3 (domestic) |  |  | 2 | Mostly Implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |
|  | S2 (overseas) |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |
|  | S2 (domestic) |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |
| R.5.2. | Loc. Voc. Training |  | Re-scheduled, waiting for the lab.equipment delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.5.3. | Int’l Seminar/Tra. |  | 1 |  | Partly Implemented |  |  | 1 |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |
|  | Dom.Non-Deg. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  | Baseline |  |  |  | Mid |  |  |  |  | Status |  |  |  |  | Final |  |  |  |
| Number of Ph.D. (S-3 Degrees) holders |  |  |  |  |  |  |  |  | 4 |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 8 |  |  |  |
| Number of Masters Degree holders |  |  |  |  |  |  |  |  | 16 |  |  |  | 25 |  |  |  |  | 35 |  |  |  |  | 35 |  |  |  |
| Number of papers published in Int’l Journal |  |  |  |  |  |  |  |  | 0 |  |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 4 |  |  |  |
| Number of self-repaired laboratory equipment |  |  |  |  |  |  |  |  | 0% |  |  |  | 25% |  |  |  |  | 25-50% |  |  |  |  | 70% |  |  |  |
| Service-time at the Department Office (e.g. the process of issuing academic transcripts) |  |  |  |  |  |  |  |  | 1 day |  |  |  |  |  |  |  |  | N/A |  |  |  |  | 5 min. |  |  |  |
| Person in charge: Prof.DR.Ir.H. Muh.Tola, M.Eng |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

2. Academic Atmosphere

| Code | Name of Activity |  |
| --- | --- | --- |
| A.1. | Special Events, Meetings and Dialogues: |  |
|  | A.1.1. | Improving teaching methods by providing Teaching Grants |
|  | A.1.2. | Improving the students’ research (skripsi) qualities by providing Student Grants |
|  | A.1.3. | Improving the staffs’ research qualities by providing Research Grants |
|  | A.1.4. | Developing a teaching and learning process evaluation system involving students |
|  | A.1.5. | Developing the staffs’ advising abilities by providing a Guidance and Counseling Training program. |
|  | A.1.6. | Academic Dialogue and other special events involving all staffs and students. |
|  | A.1.7. | Academic Meetings. |
| A.2. | Enhancing student's learning skills and reading habits |  |

2.1. Name of Activity: A.1. Special Events, Meetings and Dialogues

| a. Description and objectives: The relation among students, lecturers and staff is an essential factor of academic atmosphere. Due to heavy loads and tight class schedule, the interaction between students and lecturers is generally very limited, except in the supervision of the skripsi. The relation between the Electrical Engineering Student Association (HME) and the academic staff does not seem as having created a conducive. environment to build a high-quality teaching-learning process Regular academic meetings between academic staff and students will enhance the relationship among all components of the Study Program. Developing staffs' abilities in advising students, i.e. by equipping the staffs with guidance and counseling skills, can strengthen this relationship. Competitive schemes in the process of awarding Teaching, Research and Student Grants are expected to enhance the healthy academic atmosphere. A fair teaching and learning process evaluation system with students' involvement shall be carried out to complete the activity. The objective of this activity is to build a strong relationship among all components of the Study Program in order to improve the academic atmosphere Resources required |  |  |  |
| --- | --- | --- | --- |
| Activity | Cost Components | Cost (Rp.) | Source of Funding |
| A.1.1. | Teaching Grant (1 of Rp20,000,000) | 20.000.000,00 | TPSDP |
| A.1.2. | Student Grants (10 of Rp. 5,0000,000) | 50.000.000,00 | TPSDP |
| A.1.3. | Research Grants (2 of Rp30,000,000) | 60.000.000,00 | TPSDP |
| A.1.5. | Program Development | 6.000.000,00 | TPSDP + DRK |
|  | TOTAL | 136.000.000,00 |  |
| b. 2. Achievement (in general)): This activity has performed very well. The success of the first year term has continued to the second year, indicated mainly by the enthusiatic participation of students and staff in the competitive Teaching, Research and Student Grants. The performance indicators have shown improvement as targetted for the mid-term achievement. |  |  |  |
| To be continued in the next page |  |  |  |

Activity A.1. (continued)

. b. 2. Achievement (described per sub-activity): A.1.1. Improving teaching methods by providing Teaching Grants to the achievers in a competitive scheme There are only 1 (one) Teaching Grants allocated for Year 2, competed by 3 (three) proposals submitted by the staffs. This indicates the high motivation among staffs to improve their teaching methods. The grantees eventually is an important advanced course, namely Integrated Circuit (IC) Technology, conducted by the total of 3 (three) lecturers. A.1.2. Improving the students’ research qualities by providing Student Grants to the achievers in a competitive scheme The number of submitted Student Grant proposals was 40 proposals and the allocated number of grantees for the Year 2 is 10 (ten) projects, which is fully taken by 20 (twenty) students. Most projects are in the area of Electrical Power System and Telecommunication. A.1.3. Improving the staffs’ research qualities by providing Research Grants to the achievers in a competitive scheme The number of Research Grants proposal submitted by academic staff was 9 (nine) proposals, 2 (two) of them were awarded as has been allocated for Year 2. Each granted project is involving 3 (three) staffs and at least 4 (four) students. One of the two is a research project in the area of Power Engineering and the other is in the area of Mechatronics.. A.1.4. Developing a teaching and learning process evaluation system involving students An evaluation system design has been proposed by an alumnae who just recently completed her Masters Degree in the University of Twente, Netherland and her proposed evaluation system will be discussed among staffs. The only established teaching and learning process evaluation system right now is the classroom monitoring system for the student and staff attendance. A.1.5. Developing the staffs’ advising abilities by providing a Guidance and Counseling Training program. The TOR of this sub-activity is one of the missing TORs on their way to the CPMU. New TOR has been re-submitted. The program is ready to run, once the TOR is approved. This sub-activity is planned to be arranged together with the sub-activity E.1.2./E.1.3. The 2004 SIP required the submission of only one TOR for both activity. A.1.6. Academic Dialogue and other special events involving all staffs and students, including sport tournaments, engineering expo, and special events to honor the best lecturers, the best students, the employee of the year, etc. Except for the special events to honor the best students, best lecturers, etc., all other special events have been succesfully arranged as routine annual events and traditions.. A.1.7. Academic Meetings: Staff and Teaching Assistants, Staff and Laboratory Technicians/Assistants. Much effort have been made to arrange all categories of academic meetings attended by all relevant groups. A new organizational structure within the Study Program called “Board of Assistant” (Dewan Assisten) has been established to help the Study Program to better manage the Laboratory and Teaching Assistants.

To be continued in the next page ……

| Activity A.1. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| c. Obstacles and actions taken to overcome: Among others, this activity has the slightest obstacles, however, it requires the participation of the majority of the staff to be more effective. Originally, it was planned that the TPSDP Project Coordinator at the Study Program should have been the same person as the Chairman of the Department (who is also - in this case - the Head of the Study Program), so that an activity like this one would have been easier to manage. In fact, there was a change in the CPMU’s policy regarding this matter, it was decided that the TPSDP Project Coordinator should not be also the Chairmain of the Department. Thus, sub-activities such as A.1.4., A.1.6. and A.1.7. should be administered in a very close coordination with the Chairman of the Department, otherwise the purpose of these activity in creating the academic atmosphere will not be accomplished. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d. Future Improvement Plan: This activity needs more participation of the staff and the students. Coordination with the management structure of the Study Program is necessary, especially to implement the sub-activities A.1.4., A.1.6. and A.1.7. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| e. Impact of the activity: The success of encouraging the students and staff to participate in the Teaching Grants, Research Grants and Student Grants competitive scheme has a significant impact on the academic atmosphere within the Study Program’s environment, i.e. to increase the staff and students motivation to improve the quality of the learning and teaching process. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  |  | Yr 4 |  |  |  |  |
| A.1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  | Baseline |  |  | Mid |  |  | Status |  |  |  | Final |  |  |
| Frequency of the special events |  |  |  |  |  |  |  | Every other year |  |  | 1 per year |  |  | 1 per year |  |  |  | 2 per year |  |  |
| Participation in national academic/scientific events for students |  |  |  |  |  |  |  | N/A |  |  | Every other year |  |  | Every year |  |  |  | Every year |  |  |
| Number of scientific papers published in national and international journal per year |  |  |  |  |  |  |  | N/A |  |  | 4 |  |  |  |  |  |  | 8 |  |  |
| Number of academic seminars and conferences hosted by the Study Program |  |  |  |  |  |  |  | 1 – 2 per year |  |  | 3 per year |  |  | 1 per year |  |  |  | 6 per year |  |  |
| Person in charge: Ir. Zaenab Muslimin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

2.2. Name of Activity: A.2. Enhancing student's learning skills and reading habits

| a. Description and objectives: The condition of the Study Program’s library is not favorable for the advancement of student’s learning skills and reading habits indicated by the low percentage of students coming in for reading or checking-out books. The explanation behind this condition is that the library has:very limited collections of references, those that are available are out of date (11 to 20 years old) and very limited capacity of bookshelves, so many collections are not kept in order. The reading room is cold, humid and very inconvenient The library needs to improve its collection to attract students to come and to improve their learning skills. The library needs more bookshelves to keep all book well and neat, otherwise there will be many books spread over the floor and on the table. The library needs fixing and renovation in order to create a better and more convenient learning environment. The objective of this activity is to enhance the students’ learning skills and makes reading as their primary habit and to reduce the length of study |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Resources required : |  |  |  |  |  |
| Activities | Cost Components | Rp. | US$ | Funding Source |  |
| A.2.1. | Civil Works | 93.353.000,00 |  | TPSDP | DRK |
| A.2.2. | Furniture | 13.100.000,00 |  | TPSDP |  |
| A.2.3. | Instruction Materials | 3401.640,50 | 8.567,70 | TPSDP |  |
| A.2.4. | Equipment | 4.750.000.00 |  | TPSDP |  |
| A.2.5. | Program Development | 12.000.000,00 |  | TPSDP | DRK |
|  | TOTAL | 122.605.449,10 | 8.567.70 |  |  |
| b.1. Achievement (in general): The budget for the civil works and procurement of furniture for this activity is allocated for the second year of project term. The bidding process is in progress. The bidding process for the procurement of instructional materials (books and journals) has been in progress since the first year of project term, but until tis report is written, no delivery has been made. b.2. Achievement (described per sub-activity): A.2.1. Preparing the library room condition for better reading convenience (Bidding process for civil works is in progress) A.2.2. Making a better arrangement of book collections. (Bidding process for procurement of furniture is in progress) A.2.3. Enriching book collections and the latest published journals.. (Bidding process for procurement of books and journals is in progress) A.2.4. Establishing and maintaining a computerized library database system integrated to the Department Network. (Waiting for the delivery of the equipment procured through Year 1 IS bidding process).. A.2.5. Developing and enhancing the students’ learning skills. The SIP 2004 has required that the TOR of Program Dvelopment related to this sub-activity A.2.5 is combined into only 1 (one) TOR with the TORs related to Activity R.4. .The TOR has been submitted and waiting for the approval. |  |  |  |  |  |
| c. Obstacles and actions taken to overcome: Besides the obstacle in the writing and the submission of the TOR similar to other sub-activities with Program Development as the required resource, minor obstacle has occurred in the scheduling. This sub-activity A.2.5. is supposed to be implemented not long after the new academic year started when new students come. Coordination with Activity R.4. and the student body was apparently useful to overcome this problem.. |  |  |  |  |  |
| To be continued in the next page …… |  |  |  |  |  |

| Activity A.2. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| d. Future Improvement Plan: There should be a better coordination with the student body in terms of scheduling this sub-activity. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| e. Impact of the activity: Unmeasurable at the moment. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Yr 1 |  |  |  | Yr 2 |  |  |  | Yr 3 |  |  |  |  |  | Yr 4 |  |  |  |  |
| A.2.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.3. |  | Slightly Re-scheduled |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  | Baseline |  |  | Mid |  |  | Status |  |  | Final |  |  |
| The number of students visiting in the library (students/day) |  |  |  |  |  |  |  | 10 |  |  | 15 |  |  |  |  |  | 22 |  |  |
| The number of books check out(books/day) |  |  |  |  |  |  |  | 9 |  |  | 15 |  |  |  |  |  | 18 |  |  |
| The number of students reading in the library (students/day) |  |  |  |  |  |  |  | 2 |  |  | 5 |  |  |  |  |  | 10 |  |  |
| Person in charge: Ir. Hj. Sri Mawar Said |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

3. Efficiency and Productivity

| Code | Name of Activity |
| --- | --- |
| E.1. | Improving the quality of the classroom teaching and learning process (including the improvement of the qualifications of the Teaching Assistants) |
| E.2. | Expanding the Capacity of the Basic Laboratory Courses: Laboratory I and Laboratory II (Including the Improvement of the Qualifications of the Laboratory Assistants) |

3.1. Name of Activity: E.1. Improving the quality of the classroom teaching and learning process (including the improvement of the qualifications of the Teaching Assistants)

a. Description and objectives: Since the end of the Engineering Acceleration Project, the quality of the classroom teaching and learning process tends to decline. This is - among others - due to the increasing number of student population. Moreover, the bureaucracy of the university does not allocate sufficient funding for lecturers’ overtime and incentives. For this particular reason, lecturers used to try to avoid burden they have by accommodating larger students in one class. The first thing to do to increase the quality of the classroom teaching and learning process is to socialize the vision and mission of the Study Program to all part of departments (lecturers, students, and staffs). Providing high quality classroom facilities, upgrading students-to-lecturer ratio gradually, and decreasing the number of incoming students may also help the situation. In addition to that, high quality teaching-assistantship is a very important factor to support the quality improvement effort. The objective of this activity is to develop effective classroom teaching and learning process that will produce higher quality graduates.

To be continued in the next page ……

| Activity E.1. (continued) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Resources required : |  |  |  |  |  |
| Activity | Cost Components | Rp | US$ | Funding Source |  |
| E.1.1. | Program Development | At Cost |  | Others |  |
| E.1.2. | Program Development | 10.000.000,00 |  | TPSDP | DRK |
| E.1.3. |  |  |  |  |  |
|  | Equipment | 50.575.000,00 |  | TPSDP |  |
| E.1.4. | Civil Works | 73.435.019,00 |  | TPSDP | DRK |
|  | Furniture | 26.600.000,00 |  | TPSDP |  |
| TOTAL |  | 160.610.019,00 |  |  |  |
| b. 1. Achievement (in general): The performance indicators have shown an improvement, for example the student-to-lecturer ratio has declined considerably from 25:1 (Baseline) to 14:1 which is better than the mid-term target (18:1). Furthermore, the number of classrooms is increased from 5 rooms to 9 rooms, which is actually the final target. Most classrooms are air-conditioned to create a better teaching and learning environment. b. 2. Achievement (described per sub-activity): E.1.1. Identifying problems and socialize them to all components in meetings and discussions. This sub-activity is in line with A.1.4., A.1.6. and A.1.7. described in previous pages. E.1.2. Establishing a solid teaching-assistantship. A new organizational structure within the Study Program called “The Board of Assistant” (Dewan Assisten) has been established to help the Study Program to better manage the Laboratory and Teaching Assistants. The Board of Assistant will provide a solid ground for the establishment of strong laboratory and also teaching assistantship. As required by SIP 2004 the TOR of the Program Development related to this sub-activity is proposed together with the TOR related to the sub-activities A.1.5 and E.1.3 to provide an integrated Teaching Improvement Workshop both for staff and assistants. The TOR has been submitted and is waiting for approval. E.1.3. Improving the quality of teaching and learning process, especially in the utilization of Internet for education, communication media and educational technology. SIP 2004 has required that the TOR of the Program Development related to this sub-activity is proposed together with the TORs related to the sub-activities A.1.5 and E.1.2 to provide an integrated Teaching Improvement Workshop both for staff and assistants. The TOR has been submitted and is waiting for approval. The procurement of the equipment is still in progress. Fortunately the PIC of this Activity E.1.is granted a Teaching Grant for his course in first year, so naturally this sub-activity has started from first year. Beside PIC, some of the lecturers utilize the internet infrastructures for teaching learning process. For information, Hasanuddin University has a distance learning program as a collaboration with the School On Internet (SOI) Project in Japan. The Study Program has participated in one of SOI courses entitled ”Advanced Internet Technology: Internet Operation” that was held in October 2004 and attended by 28 students. The students have actively participated in the class which was indicated by the large number of students who submitted their assignments. |  |  |  |  |  |
| To be continued in the next page …… |  |  |  |  |  |

| Activity E.1. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| b. 2. Achievement (described per sub-activity)(cont’d): E.1.4. Optimizing room utilization The civil works as well as the procurement of the furniture related to this sub-activity is in progress. However; most classrooms have been equipped permanently with Overhead Projectors and Air Conditioning, hence, classroom becomes more comfortable to carry out the teaching and learning process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c. Obstacles and actions taken to overcome: Except of the problem of writing and submitting the TOR, no obvious obstacle is indicated so far. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d. Future Improvement Plan: The role of the Board of Assistant should be enhanced to give straight forward solutions to many problems in the teaching and learning process. Lecturer should utilize the internet as media for teaching learning process. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| e. Impact of the activity: No significant impact is indicated as far as the teaching and learning process is concerned, however, the establishment of the Board of Assistant does give a slight change to the relation among staff, assistants and students. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  | Yr 4 |  |  |  |  |  |
| E.1.1. | Slightly Re-scheduled |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.1.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.1.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  | Baseline |  |  |  | Mid |  |  | Status |  |  | Final |  |
| Meeting and discussion (times/month) |  |  |  |  |  |  |  |  | - |  |  |  | 2 |  |  |  |  |  | 4 |  |
| Recruited Teaching Assistants (students/year) |  |  |  |  |  |  |  |  | - |  |  |  | 30 |  |  |  |  |  | 50 |  |
| Participation in trainings (persons/year) |  |  |  |  |  |  |  |  | - |  |  |  | 20 |  |  |  |  |  | 40 |  |
| Student-to-lecturer ratio |  |  |  |  |  |  |  |  | 25:1 |  |  |  | 18:1 |  |  | 14:1 |  |  | 12:1 |  |
| Excess loads per semester (SKS) |  |  |  |  |  |  |  |  | 150 |  |  |  | 75 |  |  |  |  |  | 0 |  |
| Classrooms (rooms) |  |  |  |  |  |  |  |  | 5 |  |  |  | 9 |  |  | 9 |  |  | 9 |  |
| Percentage of students who are satisfied with the teaching and learning process. |  |  |  |  |  |  |  |  | N/A |  |  |  | 50% |  |  |  |  |  | 95% |  |
| Person in charge: Ir.H.Subaer Kanata |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

3.2. Name of Activity: E.2. Expanding the Capacity of the Basic Laboratory Courses: Laboratory I and Laboratory II (Including the Improvement of the Qualifications of the Laboratory Assistants).

a. Description and objectives: Basic laboratory courses (Laboratory I and II) provide 31 experiments in 4 (four) laboratories, i.e. Basic Circuit Laboratory (9 exp.), Radio Telecommunication and Microwave Laboratory (10 exp.), Computer Software Laboratory (3 exp.), and Electrical Machines Laboratory (6 exp.) [see Appendix III.37 on page III-Ap-20]. These laboratory courses are very crowded, they are always conducted in 1 or 2 shifts per day by a group of 4 to 10 students per experiment using very limited modules and --

To be continued in the next page ……

| Activity E.2. (continued) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| a. Description and objectives: (cont’d) --- equipment – both in terms of the quantity and quality – and limited laboratory spaces. The facilities were intended to accommodate only 100 admitted student per year, but since 1995 have been forced to accept three times the capacity. Moreover, the schedule of those laboratory courses is very tight causing Laboratory I and III (odd semester) and Laboratory II and IV (even semester) unable to be committed at the same time, as the consequence of that, supported equipments should be used almost continuously. The laboratory courses do not serve their purpose to provide students with practical experiences because they have very short time in the laboratory. Upgrading and repairing the number of modules, equipment and renovation and reposition of the room's function will enable the provision of laboratory courses to reach an almost ideal circumstances, for instance: the lab courses can be conducted by 1 shift/day, 3 students/group, and Laboratory I and III (odd semester) and Laboratory II and IV (odd semester) can be conducted at the same time. Repairing/increasing/additional number of modules/equipment will enable to improve the number of shifts from 2 to 1 shift per day and to improve the number of students per group from (4-10) students to (3-6) students per group Renovating and reposition of room's function will enable to increase the number of groups/experiment/day from 1 group/experiment/day to 2 groups/experiment/day and to make shorter time range of experiments because Laboratory (I and III) and laboratory (II and IV) are running together. The objective of this activity is to equip graduates with a practical understanding of Basic Electrical Engineering courses. |  |  |  |  |  |  |
| Resources required: |  |  |  |  |  |  |
| Sub-activity | Cost Components | Rp | US $ | Source of Funding |  |  |
| E.2.1. | Program Development | 0,00 |  | TPSDP | DRK |  |
| E.2.2. | Furniture | 0,00 (implemented) |  | TPSDP |  |  |
|  | Civil Works | 57.165.000,00 |  | TPSDP | DRK |  |
| E.2.3. | Equipment | 0,00 (implemented) | 0,00 (implemented) | TPSDP |  |  |
| E.2.4. |  |  |  |  |  |  |
| E.2.5. | Program Development | 6.000.000,00 |  |  | DRK |  |
| Total |  | 63.165.000,00 | 0,00 |  |  |  |
| b. 1. Achievement (in general): The sub-activities of this Activity E.2. is similar to those of Activity R.1.. The difference is in the laboratory courses taken care of. The Activity R.1. discussed previously was designed to update the course materials of advance Laboratory III and IV, while this Activity E.2. was proposed to expand the capacity of basic Laboratory I and II. b. 2. Achievement (described per sub-activity) E.2.1. Assessing the existing laboratories condition, mainly in terms of organizational and management aspects, environmental and utilities setting, and the quality of laboratory course materials. The Term of Reference (TOR) of the Program Development related to this sub-activity E.2.1. has never been approved and it needed to be modified. This sub-activity, however, is necessary to anticipate the delivery of the equipment. The SIP 2004 required to combine the submission of the TOR related to this sub-activity with TORs related to sub-activities E.2.5., R.1.1 and R.1.5. The TOR has been submitted and is waiting for approval. |  |  |  |  |  |  |
| To be continued in the next page |  |  |  |  |  |  |
| Activity E.2. (continued) |  |  |  |  |  |  |
| b. 2. Achievement (described per sub-activity)(cont’d): . E.2.2. Preparing the standard workplace and required utilities in the laboratories. The procurement of the laboratory furniture has been completed and now the Study Program has been utilizing the furniture in laboratory class. Concerning the civil works related to this Activity E.2.2., the renovation of the laboratory building facilities has completed in March 2004. E.2.3. Repairing and renewing the existing experiment modules, instruments and parts. Expanding the capacity of the laboratories serving the Laboratory I and II courses. At least two laboratories, namely: Basic Electrical Engineering Lab and Telecommunication Lab have renewed their experiment modules. Those experiment modules were renewed by D3 students from the “Partnership D3 Program for PT. TELKOM employees”. as parts of their final projects and fully supoorted by the program. The modules are also used by the regular S1 students for their laboratory courses Figure III-3 More Examples of Renewed Experiment Modules E.2.4. Commissioning test of the new laboratory equipment. This sub-activity and also part of sub-activity E.2.3. above are related to the procurement of the laboratory equipment. Apparently, the bidding process for the procurement of the equipment for the second year has been combined with the procurement for the first year in an ICB package. The bidding committee has recommended to CPMU regarding qualified bidders after completing the evaluation process. Currently, we are waiting for a decision from CPMU regarding the result of the bidding process. Therefore the equipment are in early 2005. E.2.5. Developing experiment guides and related laboratory assistant training materials. As required by SIP 2004, the Term of Reference (TOR) of the Program Development related to this sub-activity E.2.5. is combined into the same TOR of Program Developments related to sub-activities R.1.1 and R.1.5. The TOR has not been approved, however; this sub-activity requires the delivery of the laboratory equipment in order to be implemented. Until this report is written, no laboratory equipment has been delivered |  |  |  |  |  |  |
| To be continued in the next page |  |  |  |  |  |  |

| Activity E.2. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| b. 2. Achievement (described per sub-activity)(cont’d): E.2.6. Implementing and evaluating the updated experiment modules for Laboratory I and II courses This should be done after the delivery of the procured equipment, presumably at the end of year 2004 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c. Obstacles and actions taken to overcome: It is difficult to maintain the implementation of this activity on schedule, especially the sub-activity E.2.1., which requires the approval of the TOR of Program Development. The curriculum is necessarily modified before the renovation of the laboratory takes place, because all new laboratory courses should be in line with the curriculum. The process of restructuring the curriculum should involve many elements including academic staff, student, industries and government. To accommodate the interest of all elements, it requires a scheduling that fits with their time and this is quite difficult to set up. To deal with this problem, the use of internet media/mailing list is obviously very helpful. To discuss all topics related to the curriculum reform, many alumni working in various workplaces such as industries, government office and universities, have involved in an open and continuous discussion via mailing list (see http://groups.yahoo.com/group/iatel-unhas/messages/ for details). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d. Future Improvement Plan: The modification of the Program Development TOR related to sub-activities E.2.1. and E.2.5 in combination with R.1.1. and R.1.5 is to be submitted as soon as possible before the end of 2004. The activities themselves should be entirely re-scheduled to anticipate the procurement process of the furniture and equipment (ICB), and the implementation of the civil works. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| e. Impact of the activity: This activity has encouraged all staff to restructure the Study Program curriculum and syllabii, with the involvement and participation of all elements, especially alumni. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-activity | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  |  | Yr 4 |  |  |  |  |
| E.2.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.2. | Delayed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2.6. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  | Baseline |  |  |  | Mid |  |  | Status |  |  | Final |  |  |
| Number of students per-group |  |  |  |  |  |  |  | 4-10 |  |  |  | 3-6 |  |  |  |  |  | 2-4 |  |  |
| Repaired, updated and renewed experiment modules and test instruments |  |  |  |  |  |  |  | 0% |  |  |  | 50% |  |  |  |  |  | 100% |  |  |
| Person in charge: Ir. H.A. Rasjid Muhammad |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

4. Access and Equity

| Code | Name of Activity |  |
| --- | --- | --- |
| AE. | Improving the access and equity of the Study Program for students originated from remote areas in the Eastern Region of Indonesia and other less economically advantageous communities. |  |
|  | AE.1 | Recruiting and Socializing in Remote Areas in the Region of Indonesia |
|  | AE.2. | Developing a Matriculation Program for New Students from Remote Areas |
|  | AE.3 | Administering and Mediating Student Financial Aids Programs |

4.1. Name of Activity:  AE. Improving the access and equity of the Study Program for students originated from remote areas in the Eastern Region of Indonesia and other less economically advantageous communities.

| a. Description and objectives: The function of a higher education institution is to accommodate the needs of the people to acquire the skills and knowledge. This should include the people from the less economically advantageous and from remote areas. It is a well known fact that there is a significant gap in the mastery of basic sciences between potential students from suburb and rural area, from down-town and remote places. This gap has made a inequality of opportunity among people to access a higher institution. It is a social obligation for the Study Program to make an effort to close the gap mention in the background. Socialization of the Study Program will open the opportunity wider to any potential student coming from the remote area and lower economic level, particularly in the Eastern Regionof Indonesia. Developing materials and methods of matriculation sessions intended primarily for recruited students are necessary to be committed in order to equalize their basic scientific knowledge. Negotiating and persuading local government or companies to set up funding for those student is also needed. The objective of this activity is to close the gap of opportunity among people in acquiring knowledge and skills from a higher education institution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Resources required : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  |  | Cost Components |  |  |  |  |  | Rp. |  |  |  |  |  |  |  |  |  | Funding Source |  |  |  |  |
| AE.1., 2 and 3 |  |  | Program Development |  |  |  |  |  | At Cost |  |  |  |  |  |  |  |  |  | Others |  |  |  |  |
| b. Achievement (described per sub-activity): Note: This Activity AE has been taken care of at the university level under a program called “Partnership Program” (Program Kemitraan). In this program, the university - in cooperation with the surrounding county governments (Pemerintah Kabupaten) - is recruiting new students from various area in the region. Those new students are admitted without having to participate in the traditional admission test (SPMB a.k.a. UMPTN). AE.1. Recruiting and Socializing in Remote Areas in the Eastern Region of Indonesia AE.2. Developing a Matriculation Program for New Students from Remote Areas AE.3. Administering and Mediating Student Financial Aids Programs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c. Obstacles and actions taken to overcome: N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To be continued in the next page |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity AE. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d. Future Improvement Plan: The Study Program should be involved in the recruitment process of “Program Kemitraan”. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| e. Impact of the activity: N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Yr 1 |  |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  | Yr 4 |  |  |  |  |  |
| AE.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AE.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AE.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  |  |  | Baseline |  |  | Mid |  |  | Status |  |  |  |  | Final |  |
| Percentage of students admitted from remote areas |  |  |  |  |  |  |  |  |  |  | No data |  |  | 5% |  |  |  |  |  |  |  | 10% |  |
| Academic performance of matriculation program participants (average first year GPA) |  |  |  |  |  |  |  |  |  |  | No data |  |  | 2.75 |  |  |  |  |  |  |  | 3.00 |  |
| Number of fellowships for students from remote area |  |  |  |  |  |  |  |  |  |  | 0 |  |  | 4 |  |  |  |  |  |  |  | 8 |  |
| Person in charge: Ir. Gassing, MT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

5. Internal Management And Organization

| Code | Name of Activity |  |
| --- | --- | --- |
| IMO | Improving the Department’s administration system |  |
|  | IMO.1. | Establishing the Study Program’s Management Information System and Database |
|  | IMO.2. | Establishing an Effective Teaching-Learning Process Monitoring and Evaluation System |

5.1. Name of Activity: IMO Improving the Department’s administration system

| a. Description and objectives: One of the problems faced by the Study Program is in handling and processing data for academics and students administration needs. Only 5 (five) department administrative staffs daily serve the needs of around 1000 students. Data lost, improper handling and inaccuracy are not uncommon problems. The advantages of having an automatic and integrated management information system and database are: easier to make data updating, faster academic data processinga nd accessible from the network. The objective is to develop a management information system and database for academics and students |  |  |  |
| --- | --- | --- | --- |
| Resources required : |  |  |  |
| Activity | Cost Components | Rp | Funding Source |
| IMO.1. | Equipment | 63.539.965,00 | TPSDP |
| IMO.2. | Equipment | 20.244.985,00 | TPSDP |
|  | TOTAL: | 83.764.950,00 |  |
| b. 1. Achievement (in general): The resources required for this Activity are all in the form of procurement of equipment included in the Year 1 International Shopping package. The bidding progress is still in. progress and at the final stage. The expected date of delivery is early 2005. At the university level, an ISS TPSDP project entitled “Management Information Systems” (MIS) |  |  |  |
| To be continued in the next page |  |  |  |
| Activity IMO. (continued) |  |  |  |
| is in progress. According to the Project Coordinator of the MIS Project, the Study Program will be one of the participating sites of his project. Any development of information system in the Study Program should be under the MIS project coordination b. 2. Achievement (described per sub-activity): IMO.1. Establishing the Study Program’s Management Information System and Database The Study Program has developed a computer network connecting all laboratories and offices. This network has a 24 hour access to the Internet, hence, students and academic staff can utilize the Internet for educational purpose. Moreover, the Study Program has built a database system that stores the data of students including their profiles, taken SKS and their current GPA. This database system is planned to be connected later on to the university-wide network developed by the MIS project. |  |  |  |
| IMO.2. Establishing an Effective Teaching-Learning Process Monitoring and Evaluation System So far, the Study Program has implemented a teaching-learning process monitoring system (limited to the attendance record of both lecturers and students) and the result of monitoring is posted weekly on the announcement board. At the end of the semester, the Study Program is planning to evaluate the teaching-learning process based on the result of monitoring. |  |  |  |
| c. Obstacles and actions taken to overcome: N/A |  |  |  |
| d. Future Improvement Plan: - Regarding the establishment of the MIS and Database system, a better coordination with the MIS Project at the university level as well as at the Faculty of Engineering level should be developed. The Study Program has proposed to the Dean of Engineering to appoint a network manager who is going to take care of the whole Faculty of Engineering computer network, including all MIS and Database in each Study Program. The Dean has appointed a staff to be in charge as the network manager. - The PIC of this Activity IMO should co-operate with the PIC of Activity A.1. and E.1. to develop and/or to adopt a reliable teaching and learning process monitoring and evaluation system that involving students as much as possible. |  |  |  |
| e. Impact of the activity: The obvious impact of the establishment of the computer network is the increasing usage of the Internet by the students and academic staff. It is believed this will be beneficial to the learning and teaching process at the Study Program. The early development of an MIS and Database system at the Study Program has evidently improved the quality of the services provided by .the administrative staff at the Department office both to students and academic staff. |  |  |  |
| To be continued in the next page |  |  |  |

| Activity IMO. (continued) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| f. Implementation Schedule (By Quarter): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Yr 1 |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  | Yr 4 |  |  |  |  |
| IMO.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IMO.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance indicators of Activity : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  | Baseline |  |  |  | Mid |  |  |  | Status |  |  | Final |  |  |  |
| Service time |  |  |  |  |  | 1 day |  |  |  | - |  |  |  |  |  |  | 5 minutes |  |  |  |
| Data Archive Update |  |  |  |  |  | 14 days |  |  |  | - |  |  |  |  |  |  | Every Minute |  |  |  |
| Monitoring and Evaluation |  |  |  |  |  | N/A |  |  |  | - |  |  |  |  |  |  | Available |  |  |  |
| Person in charge: Ir. Indra Jaya Mansyur, MT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |