STRENGTHENING THE EXISTING STUDY PROGRAM

D3 ELECTRONIC ENGINEERING STUDY PROGRAM

SUB-PROJECT IMPLEMENTATION PLAN (SIP)

TABLE OF CONTENTS

| Chapter | Title | Page |
| --- | --- | --- |
|  | Identification | ii |
|  | Table of Contents | iii |
|  | List of Figures | iv |
|  | List of Tables | v |
| I | General Information | I-1 |
| 1.1. 1.2. 1.3. | University Objectives and Priorities | I-1 |
|  | Sub-Project Management Unit (SPMU) Organization | I-4 |
|  | University Proposed Budget | I-5 |
| II | Strengthening the Existing Study Program | II-1 |
| 2.1. | D3 Electronic Engineering Study Program | II-1 |
|  | A. Background | II-1 |
|  | B. Objectives and Strategy | II-2 |
|  | C. Performance Indicator | II-3 |
| 2.2. | Improving RAISE++ | II-7 |
|  | 1. Relevance | II-7 |
|  | 2. Academic Atmosphere | II-11 |
|  | 3. Internal Management and Organization | II-14 |
|  | 4. Efficiency and Productivity | II-15 |
|  | 5. Access and Equity | II-18 |
| 2.3. | Three and a Half Year Implementation Plan | II-21 |
|  | A. Project Organization | II-21 |
|  | B. Activity and Scheduling | II-22 |
|  | C. Monitoring and Evaluation Mechanism | II-24 |
| 2.4. | Proposed Budget | II-24 |
| 2.5. | Three and a Half Year Disbursement Plan | II-25 |
|  | List of Appendices |  |

STRENGTHENING THE EXISTING STUDY PROGRAM

D3 ELECTRONIC ENGINEERING STUDY PROGRAM

SUB-PROJECT IMPLEMENTATION PLAN (SIP)

LIST OF FIGURES

| Chapter | Title | Page |
| --- | --- | --- |
| I | General Information |  |
|  | - Figure I.1. SPMU Organization | I-4 |
| II | Strengthening the Existing Study Program |  |
|  | - Figure II.1. The organizational Structure of the Project at the Study Program Level | II-21 |

STRENGTHENING THE EXISTING STUDY PROGRAM

D3 ELECTRONIC ENGINEERING STUDY PROGRAM

SUB-PROJECT IMPLEMENTATION PLAN (SIP)

LIST OF TABLES

| Chapter | Title | Page |
| --- | --- | --- |
|  | Table of Contents | iii |
|  | List of Figures | iv |
|  | List of Tables | v |
| I | General Information |  |
|  | - Table I.1. Summary of 3,5 Years Proposed Budget of All Programs | I-6 |
|  | - Table I.2. Summary of 3,5 Years Budget by Component of All Programs | I-7 |
|  | - Table I.3. First Year University Proposed Budget | I-8 |
|  | Appendices Chapter I |  |
| II | Strengthening the Existing Study Program |  |
|  | - Table II.1. Main Indicators for Performance Targets | II-3 |
|  | - Table II.2. Auxiliary Performance Indicators | II-4 |
|  | - Table II.3. Job description of responsibility of the implementing officers | II-22 |
|  | - Table II.4. Schedule of Activities | II-23 |
|  | - Table II.5. Breakdown of Budget by Activities and by Project Component | II-26 |
|  | - Table II.6. Summary of the Total Proposed Budget | II-27 |
|  | - Table II.7. Summary of the Annual Budget Year 2004 | II-28 |
|  | Appendices Chapter II |  |

APPENDICES

CHAPTER II